## PIC Action Items
# | Date | Resp. | Action | Priority | Due | Completed
2a | 2002-10-03 | PIC | Determine if that V2.x database is suitable to track PIC issues -Committee members should review proposed changes by 12/3 |  | 2003-01-03 | 2003-01-14
2b | 2002-12-02 | PIC | Review proposed changes to v2.x database to support changes for PIC database -Committee members should review the database screen shot by 12/3 and email any proposed changes to the PIC list by 12/3 (refer to PIC example screen.doc). We will decide the database design and finalize require with Mike in San Antonio. |  | 2003-12-03 | 2003-01-16
4 | 2002-10-03 | Ken/Freida | Schedule agenda to review mission/charter with ARB and Board -ARB review 2 p.m. ET 11/21/02 (The ARB approved) -Board review 12:00 p.m.ET 12/2/02 (Board approved 12/2/02) |  |  | 2002-12-02
5 | 2002-10-03 | PIC | Read the MnM Decision making Document; be prepared to discuss in San Antonio. Is it workable, if not what do we need to tweak it to work for PIC? -Added to agenda San Antonio -12/16/02: Half have reviewed but all plan to review by San Antonio meeting |  | 2003-01-03 | 2003-01-14
6 | 2002-10-03 | Ken | Write a scenario for Point of Order as an example for the Co-Chair Handbook. |  | 2003-01-03 | 2003-01-14
7 | 2002-10-03 | Freida | Ask HQ to post the Co-Chair Handbook to the PIC web. -Posted but subsequently deleted; need to repost -Posted 12/3/02 |  |  | 2002-12-03
8 | 2002-10-03 | PIC | Discuss Guiding Principals -On agenda San Antonio -12/2/02: Ken asked members to think of guiding principals prior to the next meeting. Please email suggestions to the PIC list, or bring to San Antonio. As an example of guiding principals, we now have scope and charter, but a guiding principal might be, “we aren’t trying to make the process cumbersome”. Guiding principals should aid in expectation setting. Another example: “all opinions shall be heard. Guiding principals are the foundation of the group, they are unchanging. -12/16/02: Ken will post sample to PIC list and invited others to post straw list examples. |  |  | 2003-01-16
9 | 2002-11-18 | Chuck/Karen | Determine how to forward Bylaws process issues to PIC (agenda topic for San Antonio) -12/16/02: Chuck/Karen are reviewing and will forward process issues to PIC. |  |  | 2003-01-14
11 |  | Ken | Post calendar on the web (due dates, conference calls) 4/30/03 - would like to do this uniformly across committees |  | 2003-05-31
12 | 2002-12-06 | PIC | Develop Action Plan for top 4 PIC Survey Items
12.1 | 2002-12-06 | Ken, Joann, Jenny | Create Decision Making Document 9/8/03 - TSC Adopted; 9/9/03 - Board Appointed Committees Adopted |  |  | 2003-09-09
12.2 | 2002-12-06 | Freida, Joann | Ballot (Education) Update 9/2/03: Joann, Freida, Karen Van and Mike Craig worked as task force to revise template utilizing feedback from Cleveland Co-chair meeting. New template used Ballot 5 in August 2003
12.3 | 2002-12-06 | AMS, Ken | Workload Distribution
13 | 2002-12-06 | Freida | Request TSC agenda time San Antonio for update on PIC Survey |  |  | Complete
12.4 |  |  | Issues pertaining to the drivers influencing HL7 work and committees
14 | 2002-12-06 | Freida | Create interim tracking method for PIC suggestions |  |  | 2003-01-14
15 | 2003-01-14 | Freida | Freida to ask Board if we can use HL7 logo on Process Points publication. (Response: Yes, as long as it is clear Process Points is a PIC (not HL7) publication. |  |  | 2003-01-14
16 | 2003-01-14 | Ken | Draft Point of Order/Process Points and publish to list. |  |  | 2003-04-16
17.1 | 2003-01-14 | Freida/Ken | Look at the by-laws to understand what is meant by a “board appointed committee” and what the membership is and means. 4/30/03 - Refer to January Workgroup minutes for details. |  |  | Closed
17.2 | 2003-01-14 | Freida/Ken | Freida will talk to Ken and synch up on membership of the PIC and confirm/clarify it with the board. |  |  | 2003-01-16
18 | 2003-01-14 | Ken? | Create generic Decison Making Template. Include in the Decision Making Template: organizational structure, e.g., the type of committee (Board appointed, SIG, TC), whether co-chairs are appointed or elected, whether members are appointed or elected, whether the meetings are open or closed, etc. |  |  | Commplete
19 | 2003-01-14 | Freida | Ask Mike to post the final approved Mission/Charter to the PIC Web (emailed request 1/25) | High |  | 2003-02-28
20.2 | 2003-01-14 | Freida/Karen | Include Process Points in Co-Chair Training Materials Update 9/2/03: Is it preferable to add a portal for co-chair updates vs. continual maual updates? |  | 2003-08-31
21.1 | 2003-01-14 | Ken | Draft article re: Point of Information for Process Points (2nd suggestion for Cleveland meeting). Post on PIC list for committee to ratify. (Cleveland meeting is 4/27/2003; PIC could review on 4/7 or 4/21 conference call.) |  | 2003-04-27 | 2003-04-21
21.2 | 2003-01-14 |  | Draft article re: for future Process Points. Suggestions for Process Points: 3rd suggestion: Decision Making Document; 4th suggestion: Revisiting Decisions. |  | 2003-09-07 | 2003-09-10
22 | 2003-01-14 | Klaus/Chuck | Are proxy votes acceptable for ANSI? [1/14/03 Q3]
23 | 2003-01-14 | Ken | Document per committee discussion Q3; present to committee for concurrence (Refer to 1/14/03 minutes)
24 | 2003-01-14 | Ed Hammond | Meet with PIC in Cleveland to discuss organization; "Ed will try to provide a written document on organization and reorganization before the April meeting in Cleveland" |  |  | 2003-04-30
25 | 2003-01-16 | Ken | Categorize action list for web database (for Mike Craig) | High |  | 2003-02-17
26 | 2003-01-16 | Freida | Determine if By-law changes require other actions (e.g. ANSI audit?) - no per Karen |  |  | 2003-02-10
27 | 2003-01-16 | Joan/Ken | Finalize PIC Decision Making Document and submit to PIC list for review |  |  | 2003-02-24
28 | 2003-01-16 | Freida/Ken | Talk with Board/Chuck re: how PIC can assist with PnP review, e.g. offer peer review in advance, Board members to meet with PIC or PIC with Board. -Partially complete; Chuck to advise PIC list of section where members can assist; PIC members to contact Chuck if they can assist with PnP review. |  |  | Close
29 | 2003-01-16 | PIC | PIC members asked to review the bylaws and policies and procedures |  |  | Close
30 | 2003-02-17 | Ken | Look into webcast for Co-chair training
31 | 2003-02-17 | Ken | Schedule Peer Review conference call; post invite to general list and info to the web. |  |  | 2003-02-24
32 | 2003-02-03 | Freida | Determine if the PIC conference call time should be 4 p.m. (e.g. drop the alternating 10 a.m. time) |  |  | 2003-04-01
33 | 2003-03-13 | Ken/Freida | Determine if there is a way to know if a person has declared membership in a committee for Proxy purposes Freida checked with Karen; info not readily availble from the web |  |  | Closed
34 | 2003-02-03 | Chuck | Complete/post bylaws review -PIC agenda 4/30 -Joan volunteered to assist |  | 2003-04-15 | Close
35 | 2003-02-03 | PIC | Contact Chuck if can assist with PnP administrative review -Joan has volunteered |  |  | Close
36 | 2003-02-03 | Chuck | Post list of "work to do" to PIC listserve detailing secitons of the PnP document where help can best contribute |  |  | Close
37 | 2003-02-24 | Ken | Revise Decision Making Document based on 2/24 Peer Review with goal to finalize 3/17. |  |  | 2003-04-07
38 | 2003-02-24 | Freida | Add PIC issue regarding format of Peer Review form |  |  | 2003-03-16
39 | 2003-02-24 | Abdul-Malik | Research Roberts rules re: shifiting presiding chair: suggest alternate wording Update 9/2/03: FH spoke with AMS; he researched but no further action is required by PIC. |  | 2003-03-17 | 2003-09-02
40 | 2003-04-07 | Robert | Examples of quorum/voting scenarios |  |  | 2003-04-21
41 | 2003-04-21 | Joan | Create 3x5 cards to collect improvement suggestions Cleveland meeting Update 9/2/03: Joan took action item |  |  | 2003-09-08
42 | 2003-04-30 | PIC | Look into other collaborative tools 4/18/30 - Ken demoed product for AMS, Woody, Freida |  |  | 2003-09-10
43 | 2003-09-02 | Freida | Freida to e-mail Karen/HQ about the Thursday joint meeting with Publishing on Ballot issues |  |  | 2003-09-02
44 | 2003-09-02 | Ken | Ken to Develop Process Points and distribute to list. |  |  | 2003-09-05
45 | 2003-09-02 | Gavin | Gavin will hammer 3 paragraphs for Process Points to discuss ballot |  |  | 2003-09-05
46 | 2003-09-02 | Joan | Joan to complete the integrated grid and deliver to Freida |  |  | 2003-09-05
47 | 2003-09-02 | Joan | Joan will attempt to produce a form to collect PIC items |  |  | 2003-09-05
48 | 2003-09-02 | Freida | Freida to provide copies for TSC meeting: Generic Decision Making Practices, Generic Agenda template, Consolidated Grid, and Consolidated Agenda |  |  | 2003-09-05
49 | 2003-09-10 | Joan | Communicate PIC Interim Issue # to Martin Kernberg
50 | 2003-09-10 | Ken | Review Roberts Rules for revisiting decisions (majority vote issues)
51 | 2003-09-10 | Freida | Work with headquarters (Karen) to define what entails "proxy certification"
52 | 2003-09-10 | Ken | Draft letter to HQ to commend Mike Craig on activities
53 | 2003-09-10 | Robert | Draft letter Letter to Mark to reinstate the Electronic Services Committee to focus on process support for HL7 community worldwide
54 | 2003-09-10 | PIC | PIC Clarify where Decision Making documents should be posted to theWeb
55 | 2003-09-11 | Freida | Draft proposal to Board for PIC's role in Bylaws and PnP review |  | 2003-10-06
56 | 2003-09-11 | Freida | Email TSC list to ask for time slots needed for PIC representative to discuss Decision Making Practices with committees at San Diego Workgroup Meetig
57 | 2003-09-11 | Freida | Freida to convey to John that PIC would like to see a broader involvement in the online ballot resolution development with John as final authority.
58 | 2003-09-11 | Freida | Ask Mark McDougall to announce PIC Open Mic session each workgroup
59 | 2003-09-11 |  | Create special flyer for open mic ses session to include PIC logo
60 | 2003-10-06 | PIC | Define method to collect/publish Process Points (possibly web based?)
61 | 2003-10-06 | Ken/Freida | Confirm with Karen who "owns" co-chair vote process, e.g. is it TSC (vs. defined in Decision Making Practices)
62 | 2003-10-06 | Ken | Create blank proxy forms for use at workgroup meeting
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Ongong PIC Action Items
# | Date | Resp. | Action | Priority | Due
3 | 2002-10-03 | PIC | Review Mission/Charter each meeting |  | 2003-01-03
20.1 | 2003-01-14 | PIC | Collect/publish Process Points