## Goal A
A. Develop innovative measures to reduce costs and redirect resources for the best results.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Constrain administrative growth in contracted services to preserve funding available for direct service delivery. | POS administrative ceiling established at 15% for 2003. Nearly all providers are expected to submit budgets at or below the established ceiling. | Work with POS agencies to identify ways to further reduce administrative costs beyond the established administrative ceiling. | • Introduce a "tiered" approach to achieving desired efficiencies. • Facilitate the use of "listening sessions" to promote understanding and gain feedback in this process. • Send out reports, notifications, and letters to all POS agencies notifying them of change in practice and administrative ceiling status. | • Reduce agency contracted administrative cost by relevant "tiered" percentage. • 95% of agencies at or below the established administrative percentage. | Edjuana, G.P. Foster
Uniform Unit Rate | Contract managers establish the unit rate for services in their contracts. The Department typically pays POS providers on a 1/12 basis of their contract total. Unit rates are typically established on an historical basis with COLA increases established in the budget process. There is no direct correlation between units, unit rate and provider payment. | •Pilot a uniform unit rate policy in up to four clusters of services with the same target population. •Strengthen the tie between outputs and reimbursement to recognize the level of services we purchase. •Equitable remuneration between providers of similar services. | •Develop unit rate/define level of service that the Department is willing to fund •Develop a process to RFP for services that have been under contract •Identify service clusters to pilot this model. | •Budget savings of $200,000 •RFPs and/or contracts developed for uniform unit rate service clusters •Unit production within 10% of the amount specified in contracts for service clusters in this pilot. | Jean Kuehn, Committee Chair Contract implementation 01/01/04.

## Goal B
B. Assess performance and cost-effectiveness of services; and improve quality in those areas where quality measures are established.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Provide timely, accurate, integrated fiscal information to DCDHS Administration, Program Management, Accounting and Budget of the developmental disabilities SDS System. | Various systems have been functioning independently and without coordination. A review of the systems is being performed to determine how they are interrelated and to verify their effectiveness. | Integrated financial systems (program allocation, accounting, auditing and budget) to provide timely and accurate budget control. | •Document the current service, financial, and budget management operating systems. •Test the operating system for compliance with management assumptions •Develop a set of recommended changes to current system. •Gain approval for proposed modifications. •Design new and/or modifications to existing systems and supporting materials. •Train staff in use of system changes and materials •Implement changes •Monitor system as modified for compliance. | •System documentation is completed •Administration/program management receives consistent and accurate financial reports. •Budget variances are eliminated. •Collect baseline data on number of days required for client enrollment and payment system entry. | Fiscal Services Manager, Sandy Bennett
Intranet Development (DCInet) | We are in early development, deployment expected to begin in late 2003. | Well functioning Intranet team in place, policies and procedures established, organizational protocol created to develop and support system | Develop intra-departmental DCInet team. • Identify business process or products for Intranet deployment. • Create Intranet policies and procedures. • Develop business process | Business processes developed •50% of documents that have department-wide appeal on DCInet. •30% of documents identified by divisions on DCInet | FMS staff and David Carlson
Budget Database Development | The department develops several financial documents to prepare, monitor, and analyze the annual budget. These documents are paper stand-alone documents. They are compiled and entered into a series of spreadsheets that have to be linked together to produce a budget document. | To complete the budget database that will provide a common repository for key staff to enter budget data and to discontinue the use of multiple spreadsheets. | • Identify needs to be met by the budget database (project plan) Complete the current database project in Access database •Lay out plans to roll the budget database into the information system | Database deployed Staff trained on the database | Ken Baun, Edjuana Ogden, Steve Delain, G.P. Foster
Contract Compliance Database Development | The department collects data from the POS agencies in a primarily paper format. The data is stored in folders in file cabinets. There is no central repository of the data. | To develop a contract compliance database that will capture expense summary report data, personnel schedules, and budget reports data. | • Identify needs to be met by the Contract Compliance Database (project scope) • Identify reports to be generated by the database and staff to distribute reports • Identify users of the database and add relevant security • Build structure with Department of Administration - Info Mgmt to meet electronic reporting needs • Add contract compliance audit/review tracking | • Contract compliance data housed electronically in a single database • All financial data captured in a single database • Meet established percentage completion of multiphase project, to be defined in project plan. | Edjuana Ogden, Ken Baun
Conversion of Contract Compliance database to a SQLServer back end | With the number of potential users on the Contract Compliance database, and the amount of data to be stored, a more robust database engine will be desirable | The Access "back-end" database that contains the data will be replaced by a SQLServer database. The Access "front-end" database that contains the user interface will be retained. | IT staff time will have to be identified and allocated. IT staff will need to be trained in the conversion process. | The database has a SQLServer back-end | Ken Baun, Jon Hatley
Conversion of DCDHS to Citrix computing environment | Conversion of Department to Citrix started Feb 2003. Full implementation not expected until into 2004 | All staff using Citrix on a single server network | Work with Information Management to identify and resolve issues as each office is converted. | • Current office specific servers are eliminated and everyone is on a single server network. • 100% of staff converted to working in Citrix environment. | Joe Mundschau
SACWIS Implementation | SACWIS delayed. Conversion efforts scheduled to resume in the fall of 2003. | SACWIS will be fully converted, operational and deployed with historical dataset. | • Re-engage DCDHS staff (both program and IT). • Hire consultant to perform conversion activities. • Meet regularly with new State/AMS conversion team. | • SACWIS system operational and staff trained on SACWIS. • Data that staff need is converted. • February 2004 conversion deadline is reached. | Lori Bastean, G. P. Foster
Web-enabled Information System | Contract has been established with Stratagem and work has begun. Will take well into 2004 | Mental Health POS agencies will enter and update unit of service and consumer status dataset data over the web. | Complete development of business rules, work with contractor to implement. | 50% of our Mental Health POS agencies will enter and maintain their client service records and consumer status dataset data over the web. | Lori Bastean, G.P. Foster
POS Contract Administrative Cost Compliance | New administrative cost definitions and guidelines were introduced in 2002. Compliance review implementation scheduled to begin in 2003. At least 7% of POS agencies will be reviewed and tested for compliance in this area. | Increased POS provider understanding and 95% compliance with established administrative cost ceiling. | • Add contract language to support changes in county expectations and operations as it relates to contract compliance. • Continue compliance reviews • Develop consistent/uniform internal procedures for enforcing contract guidelines • Analyze data to evaluate priorities for revised procedures and provider training | •Fewer inconsistencies and exceptions between programs and contracts. •Compliance Reviews will increasingly reveal higher percentages of administrative cost compliance as well as compliance with administrative cost guidelines. | Edjuana Ogden
Implement the POS compliance audit/review plan (desk or field). | Nonexempt POS agencies are required by contract to have an external financial audit done annually. Department audit/reviews are still needed. Department audits/reviews of POS service providers are rarely conducted. | Review at least 7% of POS agencies annually. | • Collaborate with Department staff, State and external auditors in implementing the plan. • Determine the annual focus. • Develop most appropriate tests to be performed. • Assess staff resources to meet chosen target. • Develop uniform working document for staff use when completing review process. • Explore other resources to bridge remaining gap. | Review at least 7% of POS agencies. | Edjuana Ogden
Health Insurance Portability and Accountability Act (HIPAA) | Oversight Committee that includes staff from all divisions has been formed. Basic information has been shared with staff. We continue to learn more about the impact on each system. Subcommittees have been formed to address the privacy and transaction rule requirements with the intent to meet the 2003 target dates. Brenda Brown has been identified as the Department's privacy officer. A separate privacy officer has been identified for Badger Prairie Health Care Center. The committee will meet as needed since the detailed impact of this law on each system is not entirely known we will continue to monitor compliance and keep apprised of additional rules as they are implemented as well as changes/updates to current rules. HIPAA is a moving target. | 100% compliance with the privacy rule by established effective date: April 14, 2003. 100% compliance with Transaction by established effective date: October 16, 2003. Compliance with Security Standards established effective date: April 21, 2005. Continued compliance with HIPAA Rules and changes as they roll out. | •Maintain contact with State DHFS to obtain updated information on systems affected by this law. •Keep apprised of changes to existing rules and components identified but currently in the federal rule making process. •Develop strategies for compliance with additional components as implementation dates are established. •Investigate opportunities for reimbursement of implementation costs through MA or other potential revenue sources | •Zero complaints/grievances due to non-compliance. | Oversight Committee Brenda Brown, Chair
Outcome Measures | •CYF - four broad outcomes have been identified across most services - AODA programs have State established outcome measures •EA - performance based contracting with State •ACS - identified 2 primary outcome measures, performance measures currently in development. State has identified a consumer data set in the Mental Health area that has some outcome measures and is to be utilized by all counties. | Short-term: In 2003, in the AODA and Mental Health areas produce baseline reports. Long-term: Have performance measures be one tool to use in evaluating the performance of the Department and associated providers in delivering consumer services. | •Develop a phased (multi-year) approach to implementing performance based contracting for purchased services. •Establish an oversight committee to assure an integrated approach across the Department; •Provide training in outcome measures to all stakeholders; •Develop a repository for the data collection; •Identify resources for the analysis of the data; •Collect baseline data and refine acceptable performance levels and review processes. •Centralize consumer satisfaction surveys within the Department •Department must continue to make substantial investments in infrastructure necessary to monitor and track the fiscal and outcome data. | •Report baseline data for AODA and Mental Health programs, 2003. •Report on results of consumer satisfaction surveys for CYF and ACS, 2004. •Long -term goal: Department is able to annually produce reports on outcomes across the identified service areas. | Jean Kuehn, 2004

## Goal C
C. Become a more culturally competent agency to meet the needs of diverse consumer populations.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Unlearning Racism Initiative To help staff unlearn and reduce the subtle and not so subtle ways in which racism manifests in life and at work. | 12-14% diverse staffing across the Department. Eleven staff attended the Unlearning Racism Workshop put on by the YWCA in 2002. Ten staff attended the Changing Face of Diversity Workshop put on by the Madison EOC. Several Department brown bag discussions have occurred to ascertain the level of interest in having this training being conducted in the HSD. Forty staff attended a half day discussion session to look at the Unlearning Racism training to determine receptivity to the training direction. The general sentiment is that this training should proceed. The film was excellent and the discussion that followed was viewed as useful to improve on cultural competency and inter-race relationships. | To develop a deeper understanding of differences by exploring personal perceptions and issues concerning race, conflict and internalized racism. To build a better diverse work environment where everyone views Dane County Human Services Department as culturally appropriate and culturally responsive agency. To help provide better services to diverse clientele with greater understanding of the issues faced by diverse populations in order to develop better trusting work relationship with clients. | Conduct 15 Unlearning Racism Workshops with 20 Department participants per session. Session will be a mixture across divisions, classifications and where possible will be racially balanced. Develop mechanism for continued and ongoing communication for participants. | All 15 sessions were conducted follow up mechanisms were developed to ensure continuity of unlearning racism work. | Brenda Brown. Sessions will start up again in February 2004 and will be complete by December 31, 2004.

## Goal E
E. Develop targeted legislative initiatives to increase sustainable funding streams.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Legislative Partnerships: Expand development of strategic legislative partnerships with other human services groups to secure increases in Birth to Three, Youth Aids, Community Aids and Economic Assistance funding. | We regularly work with a variety of groups on issues of mutual interest. | Join with these groups to develop a shared legislative agenda that can be presented in a unified manner to raise the visibility and impact of the agenda with legislators and the governor. | Facilitate or participate in regular gathering(s) of key human services advocacy groups and associations as well as officials from other counties to identify common issues of concern and opportunities for cooperation. | Meetings will result in development of a shared human services agenda for action in the 2005-2007 biennial budget and other legislative action that will result in increases in these key-funding areas. | DCDHS Communications Manager and Dane County lobbyist will coordinate these the meeting(s).
Human Services Reform Cmte: (proposed in Gov’s 2003-2005 biennial budget) | Gov’s 2003-2005 budget proposes formation of a committee to advise the DHFS Secretary on ways to reform the way human services programs are funded and administered across the state. | Assuming the creation of the committee is approved in the final 2003-2005 budget, Dane County should be an active participant in the discussions and advocate for reforms that adequately fund required services and clearly spell out state and county responsibilities. | Dane County will need to be a participant on the committee or provide input through other sources such as WCA or WCHSA. | Dane County’s input is received by the committee and included in the final report. | DCDHS Communications Manager will lobby for inclusion of our department on the advisory committee.
Nursing Home Funding: Develop new state/federal funding stream(s) for county and municipal nursing homes, including Badger Prairie Health Care Center. | Current IGT mechanism for claiming Federal funds to support supplemental state payments to county and municipal nursing homes is being phased out over the next five years. | A replacement-funding source should be discussed and agreed on prior to the 2005-2007 state biennial budget being drafted. | Work with DHFS, other counties and municipalities that operate nursing homes and statewide associations such as WACH and WAHSA to develop alternative funding methods that will recognize the important and unique role of county and municipal nursing homes in the continuum of care for people with disabilities and mental illnesses. | New funding sources will be proposed by DHFS and will be included in the Governor’s proposed 2005-2007 biennial budget. | DCDHS Communications Manager and BPHCC Administrator will lead this effort in 2003-2004.