## 3rd quarter
Department: Department of Environment and Natural Resources
Agency: Environmental Management Bureau - Central Office
Division: Office of the Secretariat - National Solid Waste Management Commission
3rd Quarter Accomplishment Report
PROGRAM/ PROJECT/ ACTIVITY | PERFORMANCE | TARGETS |  |  |  | Annual | Targets | Accom. | Accom. | Remarks
-1 | INDICATORS | Q1 | Q2 | Q3 | Q4 | Target | Q3 | Q3 | to date
I. Policy Formulation
1. Finalization NSWM Framework | NSWM Framework finalized (no.) |  | 1 |  |  | 1 | - | - | 1 finalized
draft
2. Finalization NSWM Status Report | NSWM Status Report finalized (no.) | 1 |  |  |  | 1 | - | - | re-encoding | edited the parameters for the status report
of data
3. Formulation of guidance documents | Draft guidelines formulated (no.) | 2 |  | 2 | 2 | 6 | 2 | 1 | 1 | Implementing guidelines for the ESWM Act of RA 9003
| Writeshops conducted (no.) | 1 | 1 | 1 | 1 | 4 | 1 | - |  | moved to the 4th quarter
4. Finalization of SWM guidance | SWM guidance document
documents | finalized (no.) |  |  | 2 | 2 | 4 | 2 | - |  | moved to the 4th quarter
II. Information Education and Communication
1. Preparation, publication and | IEC Materials printed (no.) | 2 | 2 | 3 | 1 | 8 | 3 | 5 | 7 | Reprinting of the ff. IEC materials
reproduction of various IEC | [9 empty] | The Three R's of Solid Waste Management
materials | [9 empty] | Waste Generation
The Guiding Principles of Solid Waste Management
Waste An Unwanted Extra
Printing of "Idol ko si Kap"
| IEC materials distributed (no.) | 5000 | 5000 | 5000 | 5000 | 20000 | 5000 | 5000 | 15000 | IEC Materials such as posters, leaflets, and copies
of RA 9003 were distributed to the region,
researchers, and schools
2. Conduct of fora/ seminar/ | For a/ Seminar/ training/ lectures
training/ lectures/ on SWM | conducted (no.) | 45 | 20 | 20 | 20 | 105 | 20 | 36 | 108 | see attached sheet
3. TV/ Radio Plugs | Movie/ TV Plugs aired (no.) |  |  |  | 4 | 4 | - | - |  | c/o EEID
| Radio plug aired (no.) |  |  |  | 1 | 1 | - | - |  | c/o EEID
4. Cross visits | Cross Visits/ Observations trips | 2 | 2 | 2 | 2 | 8 | 2 | 3 | 7 | with DENR-SAID employees Sun Valley MRF,
| conducted (no.) | [8 empty] | and Valenzuela controlled dump (2 sites)
with the 2nd batch of trainees from the kingdom
of Bhutan, to the Philam MRF, and Clark SLF (2 sites)
with ADB Team in Payatas, Doña Petra d/s, Lupang
Arenda d/s, Catmon d/s, Tanza, Navotas CDF, and
Bagumbong d/s, Caloocan City
5. In-house training for NSWMC staff | In-house training conducted (no.) |  | 1 | 1 | 1 | 3 | 1 | 1 | 1 | Seminar on Land-use & site planning in UP NIGS
III. Provision of Technical and Financial Assistance for SWM
1. Provision of financial assistance | MRF assistance facilitated (no.) |  | 2 | 2 | 2 | 6 | 2 | - | 3 | Facilitated the MOA of the ff. to be established in 4th quarter
in the establishment of Materials | [9 empty] | Muñoz City | Iloilo City
Recovery Facilities | [9 empty] | Palayan City | Las Piñas City
[10 empty] | Smokey Mountain | Tacurong City, Sultan Kudarat
Mun. of Linamon
2. Evaluation, Assessment and | Project proposals evaluated (no.) |  |  |  |  | 12 | 3 | 15 | 26 | SWM Plan, Tapay, Capiz | Payatas Dumpsite conversion
Monitoring of SWM facilities/ | [9 empty] | MRF FS, Sorsogon City | RCI Plasma Gasification
programs of LGUs, NGAs, POs | [9 empty] | Landfill gas utilization project | Del Monte Phils., Bukidnon
(controlled dumps, sanitary landfill, | [9 empty] | Gender Development & SWM - ERDB | KP Industries
Materials Recovery Facilities and | [9 empty] | Waste Pliant Garbage Disposal | MRF Palayan City, Nueva Ecija
other SWM programs/ facilities) | [9 empty] | FJ Electric Resistant - Type Melting | MRF Muñoz city, Nueva Ecija
[10 empty] | MRF Gloria, Oriental Mindoro | Compressed Waste Disposal
[10 empty] | MRF Tacurong City, Sultan Kudarat | Technology
| SWM facilities/ programs |  |  |  |  | 22 | 7 | 9 | 28 | Calapan, Oriental Mindoro MRF | Calamba, Laguna CDF
| assessed (no.) | [8 empty] | Gloria, Oriental Mindoro MRF | Calamba, Laguna MRF
[10 empty] | Palayan City, Nueva Ecija MRF | Antipolo City CDF w/ MRF
[10 empty] | Muñoz City, Nueva Ecija MRF | Tanauan, Batangas CDF
DRT, Bulacan SLF
| SWM facilities/ programs | 3 | 3 | 3 | 3 | 36 | 10 | 10 | 26 | Paradahan, Tanza, Cavite CDF (ACP)
| monitored (no.) | [8 empty] | Rodriguez, Rizal CDF (2x)
Tanza, Navotas, CDF
Luneta Park MRF (DOT-NPDC)
Obando, Bulacan CDF
EMB Region II
Payatas Water Quality Monitoring
Water Sampling in Tabaco City
Water Sampling in Sorsogon City
| Progress reports evaluated (no.) | 4 | 7 | 7 | 4 | 11 | 3 | 3 | 9 | Malacañang MRF
Tanza, Navotas CDF
All EMB Regions (16)
3. Provision of technical assistance in the | LGUs assisted in M.M. (no.) | 2 | 3 | 3 | 3 | 11 | - | - | 14 | Accomplished (continuing activity)
implementation of Ecological Solid Waste | LGUs assisted outside M.M. (no.) |  |  |  |  | 18 | 5 | 49 | 49 | coordination with Regional offices on
Management | [9 empty] | the LGU-wide ESWM (continuing activity)
| NGAs assisted(no.) | 5 | 6 |  |  | 24 | 6 | 10 | 23 | Office of the Ombudsman
Department of Social Welfare & Development
Department of Transportation - National Parks
Development Commission
Department of Finance
Sandigan Bayan
League of Provinces
Liga ng mga Barangay
Department of Science & Technology
Commission on Higher Education
| DENR offices assisted(no.) | 4 | 5 | 5 | 4 | 26 | - | - | 26 | Accomplished 1st quarter
IV. Maintenance and updating of the SWM information system |  | 6 | 6 | 6 | 6
1. Maintenance and Updating of the | SWM database updated (no.) | 10 | 16 |  |  | 1 | 1 | 1 | 1 | The SWM profile database was
SWM database
2. Maintenance and Updating of | Web page updated (no.) |  |  |  |  | 1 | 1 | 1 | 1 | A new NSWMC database has been uploaded
NSWMC Web page | [9 empty] | http://www.emb.gov.ph/nswmc
V. Enforcement of the IRR of RA 9003
1. Complaints acted upon | Inspection reports submitted(no.) |  |  |  |  | 33 | 10 | 7 | 25 | Inspected/ investigated the ff. sites:
Brgy. Langgam, San Pedro, Laguna CDF (pilotage)
Sahud Ulan, Tanza, Cavite CDF Scrapper's Association (2x)
Bauan, Batangas open dump
Brgy. Ampid II, San Mateo, Rizal open dump
Brgy. San Dionisio, Parañaque open dump
Brgy. San Marttin de Pores, Parañaque EW Center
Brgy. Payatas, Quezon City Dumpsited
VI. The National Ecology Center |  | 7 | 8 | 10 | 8
National Ecology Center pavillion | Informal Settlers relocated (no.) |  |  |  |  | 37 | 37 | 37 | 37 | Accomplished
| DENR vehicles relocated (no.) |  |  |  |  | 51 | - | - | 51 | Accomplished as of 2nd qtr.
| Pavillion constructed (no.) |  | 37 |  |  | 1 |  |  |  | under construction
Prepared by:
Noted by:
RAYMOND P. BLAQUERA
Planning Officer II
ALBERT A. MAGALANG
Executive Director

## Training (2)
Trainings conducted on ESWM
1 | 2nd batch of Bhutan delegates
2 | Amigo Terrace Hotel, Iloilo City (8 municipalities)
3 | Brgy. Malvar, Malacañang Complex
4 | Cagayan de Oro Conference
5 | Calamba SWM Planning
6 | Carmelray Techno Park, Calamba City
7 | Cebu City, (all health care institutions, & DOH ROs)
8 | Central Luzon State University, Muñoz City
9 | Commission on Higher Education
10 | CSWM Board of Trece Martirez, Cavite
11 | Department of Finance
12 | Department of Social Welfare & Development
13 | Department of Transportation - National Parks
14 | Development Commission
15 | Enviornmental Forum for NGOs, Andaya Hall, Congress
16 | Environmental Commitment forum
17 | League of Provinces
18 | Liga ng mga Barangay, Monte Vista, Pansol, Los Baños, Laguna
19 | Livelihoods oppoortunities & references on SWM
20 | Mall owner reps., & head of janitorial services
21 | National College of Public Administration & governance (NCPAG)
22 | Navotas, M.M. (fishermen & NGOs)
23 | Office of the Ombudsman
24 | Orientation workshop on ESWM for Valenzuela brgy. Officials, PAWB Visitor's Center
25 | PCAPI - National Chapter
26 | PCAPI - National Power Corporation at Napocor
27 | Philippiine Society of Mechanical Engineers
28 | Provincial Board Members League of the Phils, Calapan City
29 | Q.C. Brgy. Leaders sponsored by SIDA & DILG NCR
30 | Regional Inter-agency Committee on Environmental Health Region IV
31 | RTI, College of Public Administration, Mandaluyong City
32 | Sandigan Bayan
33 | SIBAT sponsored forum for payatas victims
34 | Sta. Catalina convent, Baguio City for SK offiers of Itogon, Benguet
35 | UP Diliman Faculty
36 | World City Colleges, Aurora Blvd., Q.C.
4th quarter
Training/ Workshop on the Global Positioning System and other solid waste disposal issues
ESWM seminar at the Bureau of Domestic Trade, DTI
Worskshop on the Implementation of LGU-wide ESWM at the Century Imperial Suites

## LGU Wide
Region |  | Site
CAR | 1 | Tuba, Benguet
Region 1 | 2 | Candon City
| 3 | Laoag City
| 4 | San Fernando City
| 5 | Calasiao, Pangasinan
Region 2 | 6 | Tuguegarao City
Region 3 | 7 | Marilao, Bulacan
| 8 | San Jose Del Monte, Bulacan
| 9 | San Fernando, Pampanga
| 10 | Guagua, Pampanga
| 11 | Moncada, Tarlac
Region 4-a | 12 | Batangas City
| 13 | Bauan Batangas
Region 4-b | 14 | Puerto Princesa, Palawan
| 15 | San Isidro, Calapan
Region V | 16 | Naga City
| 17 | Sorsogon City
| 18 | Pilar, Sorsogon
| 19 | Legaspi City
Region VI | 20 | San Enrique
| 21 | La Castellana
| 22 | Iloilo City
| 23 | Sigma, Capiz
| 24 | Sagay City
| 25 | Boracay Island
| 26 | Guimaras Province
Region VII | 27 | Mandaue City
| 28 | Cordova
| 29 | Dumaguete City
Region VIII | 30 | Calbayog City
| 31 | Tacloban City
| 32 | Maasin City
Region IX | 33 | Ipil, Zamboanga
| 34 | Isablela, Basilan
Region X | 35 | Iligan City
| 36 | Province of Camiguin
Region XI | 37 | Davao City
| 38 | Panabo
| 39 | Malalag
| 40 | Tagum City
Region XII | 41 | Takurong, Sultan Kudarat
| 42 | Maitum, Sarangani
CARAGA | 43 | Butuan City
NCR | 44 | Makati City
| 45 | Valenzuela City
| 46 | Quezon City (district II)
| 47 | Muntinlupa City
| 48 | Marikina City
| 49 | Manila (district V)

## projects
FOREIGN ASSISTED PROJECTS
Metro Manila Solid Waste Management Project(MMSWMP)
§ Inception Report of the Metro Manila Solid Waste Management Project
§ Facilitate in the MMSWMP (TA3848)Workshop 1:Issues & Problems
§ Facilitate in Workshop 2: Medical Waste Issues and Problems
§ Facilitate on Workshop 3: Development of LGU SWM Plans
Pilot Study for the Formulation of SWM plan for selected LGUs (PLFSWMP)
§ Conducted Field Studies in the project areas (Muñoz City, Legaspi City and Butuan City) to gather relevant information on existing efforts in SWM
§ Assisted in the establishment of the cities respective Solid Waste Management Boards
§ JBIC Study Team submitted the final copy of the cities respective Solid Waste Management Plan
Public-Private Partnership in Urban Environment for SWM (PPPUE)
§ Facilitate MOA signing of Barangays in Laguna, DENR and UNDP at the OSEC
§ Inception Workshop of PPPUE at Calamba, Laguna
§ Orientation Wokshops on RA 9003 in the three partner-barangays
§ Creation of the SWM Committees in Brgys. Palingon, Lingga and
Sampiruhan in Calamba City
§ Conducted workshop for barangay and city government for the formulation of the City SWM Plan and the Barangays’ SWM program
Ecological Governance Project (ECOGOV)
§ Participated in the Interactive Assembly for local providers in Central Visayas
§ MOA with 4 LGUs (libak and Kalamansig, Sultan Kudarat, Jagna and Duero, Bohol)
§ 3 MOAs signed in Region 7 (Municipality of Talibon, Jagna and Duero)
§ 7 MOAs signed in Mindanao (Lamitan, Isabela, Sultan Kudarat, Kidapawan, Isulan, Tacurong and Libak)
§ Launch the Northern Luzon Ecological Site in Region 2
§ Formulated SWM Modules for LGUs
§ Prepared primer on ESWM Act and the IRR
ESTABLISHMENT OF DROP-OFF CENTERS
Preliminary meetings were held with the following industries:
Tires | Plastics/ Packaging
Batteries | Laminates
Food chains | Flexibles
Mall Owners | Tin/ Aluminum
NATIONAL ECOLOGY CENTER
Preparation of the Development Plan for the National Ecology Center Pavillion in coordination with DENR-NCR
NOTICE TO PROCEED
Issuance of NTPs for the ff. disposal facilities:
Calapan, Oriental Mindoro
San Cristobal, Victoria, Oriental Mindoro
Prepared by: | Noted by:
Raymond P. Blaquera | ALBERT A. MAGALANG
Planning Officer II | Executive Director

## others
Preparation of tne SWM Handbook
Participated in the World Clean-up day Sept. 20, 2003
Prepared poster for model barangays ESWM system
SWM Orientation Workshop of Mall Owners
Sta. Maria, Bulacan conversion of open to controlled dump with MRF
Condemnation of fruits, vegetables, & meats in Angat, Bulacan
Conversion of the Payatas from open to controlled dump
Conversion of the Marikina City open dump to controlled dump
Tech. Conference in Brgy. Langgam, San Pedro, Laguna
Tech. Conference in Pamalakaya, Obando, Bulacan
Tech. Converence with BFAR re: watersampling of Navotas, Malabon, Valenzuela, & Meycauayan
Meeting with Flexibles/ Laminates
Meeting with Starbucks
Eco-labeling meeting with La Salle
Attended clean-up at Brgy. Batis, San Juan
Attended the 18th Coastal clean-up
Sent letters to all Mayors & Governors in the country reminding them of the Implementation of RA 9003