## Sheet1
GOALS - OBJECTIVES - TASKS | Priority | Est. Start | Est. Finish | Responsible for Action | Status | Driver
1. GOAL: Develop joint policy and guidance environmental and occupational health in the deployment setting
Note!. All tasks from goal 1, objectives 1-4 must be completed to allow the JESWG to pursue the remaining objectives in this Action Plan
1.1. Objective 1. Develop organizational infrastructure for development of OEHS | [5 empty] | MRSP C1.6.2.2.2.
OEHS White Paper 4-2a,
1.1.1 Task 1. Amend JESWG Charter to change environmental health surveillance (EHS) to occupational and environmental health surveillance (OEHS). |  | 2002-06-01 | 2001-08-24 | JESWG chair,LMI | Completed | JESWG issue
1.1.2 Task 2. Determine JESWG role for inclusion or exclusion for surveillance subject areas of: physical hazards (ergonomics, safety) and psychological hazards. |  |  |  | JESWG chair | Reassess requirements | MRSP AP1.12.1.4.4
1.2 Objective 2. Develop an approved DoD white paper on vision for deployment environmental & occupational health surveillance (OEHS). | [5 empty] | MRSP AP1.1.1.3,
PRD-5 DH 1.1
1.2.1 Task 1. Develop draft OEHS white paper. | 1 | 1999-02-01 | 2001-09-21 | JESWG Chair / LMI | Completed March 2002 | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.2 Task 2. Review and approve White Paper. | 1 | Sep 01 | Sep 01 | JESWG members | Approved March 2002 | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.3 Task 3. Submit OEHS White Paper for JPMPG approval. | 1 | 2002-10-01 | TBD | JESWG Chair | Memo & paper to JPMPG June 2002 | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.4 Task 4. JPMPG coordinates the review of the OEHS White Paper and determines who will be the signatory. | 1 | 2002-10-01 | Dec 01 | JPMPG | JPMPG Reviews May 2002 | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.5 Task 5. Approve & sign OEHS Wwhite Paper. | 1 | Dec 01 | Dec 01 | JPMPG / Health Affairs | JPMPG endorses to DASD (FHP &R), June 2002 | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.6 Task 6. Distribute the OEHS White Paper within the services (including doctrinal offices) and the J-staff. | 1 | Dec 01 | Dec 01 | Service Representatives/J-4 MRD | Outside JESWG | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.2.7 Task 7. Distribute the OEHS White Paper and brief external agencies that may have impact on further OEHS activities. | 1 | Dec 01 | Mar 02 | JESWG Chair / JPMPG | Reassess requirement | MRSP AP1.1.1.4.1
PRD-5 DH 1.1.1
1.3 Objective 3. Perform gap analysis between existing policies, guidance, health standards, and ORM framework, and those documents needed to achieve the OEHS Vision | [5 empty] | MRSP C1.6.1.1.. C1.6.9.2., C1.6.10.2.5., C1.6.12.1., C4.1.2.1., C11.4.5., C13.3.6., C13.3.7., AP1.10.5.1.1., AP1.10.5.2.2., AP1.10.5.2.3., AP1.10.5.2.4., AP1.10.5.4.2., AP1.10.5.4.4., AP1.10.5.4.10., AP1.11.2.2.3., AP1.12.3.4.1.
1.3.1 Task 1. Inventory existing DoD, JCS, Service, and Defense Agency policies addressing OEHS. | 2 | 2000-03-01 | 2000-10-11 | LMI, JESWG,Service Reps | Completed, Reassess as required
1.3.2 Task 2. Identify policy subject area and type of document needed to fill the policy gap by comparing existing policies to OEHS White Paper. | 2 | 2000-10-11 | Feb 02 | LMI, JESWG,Service Reps | Policy requirements developed. Dr. Bratt presented policy gap analysis approach 17 May 2001
1.3.3 Task 3. Work with Military Dept Surgeon general staff members during staff coordination of the draft joint policy on overseas garrison environmental exposures. |  | TBD | TBD | JESWG Senior Navy rep | On hold | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.4 Objective 4. Draft a joint Service instruction to guide OEHS field surveillance activities, to include a minimum list of analytes. | [5 empty] | MRSP C1.6.10.2.5., AP1.2.1.3, AP1.10.3.3, AP1.12.1.3
AP1.12.3.3
PRD-5 R&D 4.1
1.4.1 Task 1. Provide comments for the draft instruction to the JESWG chair. | 1 | 2000-02-01 | 15 Jul 01 | JESWG members | On Hold. Need to define requirements. Reassess Status | MRSP AP1.12.1.4.4
PRD-5 R&D 4.1.4
1.4.2 Task 2. Consolidate comments as a JESWG position. Coordinate with the JPMPG, BUMED; and JESWG members. | 1 | 2002-08-01 | Sep 01 | JESWG Chair | Comments on initial JSI document were provided. | MRSP AP1.12.1.4.4
PRD-5, R&D 4.1.4
1.4.3 Task 3. Assist JPMPG in completing redraft of the joint instruction. | 1 | 2000-04-01 | TBD | JESWG Chair | On hold awaiting JPMPG response to offer of assistance. CAPT Yund, BUMED presented update 16 May 2001. March 01 Version w/Encl E to be sent to JESWG members for comments. | MRSP AP1.12.1.4.4
PRD-5 R&D 4.1.4
1.4.4 Task 4. Update guidance in Sanitary Control and Surveillance of Field Water Supplies (TB MED 577 / AFOSH 48-7). | 1 | TBD | TBD | LtCol Dave Gibson, AFIERA, Field Water Standards sub-work group | MAJ Stinson, AFIERA presented Joint Field Water Subgroup action update, 16 May 2001 | MRSP AP1.12.1.4.4
PRD-5 R&D 4.1.4
1.5 Objective 5. Develop an RDT&E and Materiel Acquisition Guidance Document which includes information on: | [5 empty] | MRSP AP1.11.1.3,
- how to identify and complete materiel requirements | [5 empty] | AP1.11.2.3
- how to prioritize & submit materiel research requirements | [5 empty] | PRD-5 DH 1.1
- ensure OEHS requirements of PRD-5 are met
- coordination of OEHS requirements with the NBC community (DOD Low-Level Strategy for Chemical Agent Exposures During Deployment)
1.5.1 Task 1. Develop a draft information paper describing individual Service RDT&E / Acquisition procedures and points of contact. |  | TBD | TBD | Dr. Paul Knechtges, CEHR | On Hold. Possible Agenda Item for 4Q01 meeting JESWG discuss with CEHR | MRSP AP1.11.2.4.2
1.5.2 Task 2. Produce the draft information paper as a JESWG document and distribute to the JPMPG. |  | TBD | TBD | JESWG members | On Hold. Need to define format. | MRSP AP1.11.2.4.2
1.5.3 Task 3. Coordinate with ASBREM concerning RDT&E for materiel. |  | TBD | TBD | Dr. Paul Knechtges, CEHR | On Hold. Need to define requirements
1.5.4 Task 4. Establish feedback loop for fielded materiel evaluation. |  | TBD | TBD |  | On Hold Need to define criteria
1.5.5 Task 5. Coordinate NBC & non-NBC RDT&E requirements for OEHS with NBC R&D group, or add representative of NBC R&D group on the JESWG. |  | TBD | TBD |  | Need to define requirements
1.6 Objective 6. Develop a military operations Planner’s Guide to Occupational and Environmental Health Surveillance | [5 empty] | MRSP C1.6.1.1., AP1.1.1.3,
AP1.12.1.3, AP1.12.3.3
PRD-5 DH 1.1
1.6.1 Task 1. Identify requirements for intelligence products. |  | TBD | TBD | Users/AFMIC | Need to define one time or recurring requirements. | OEHS White Paper 3-3d
1.6.2 Task 2. Perform gap analysis between intelligence product requirements and current capability. |  | TBD | TBD | JESWG/LMI | On Hold | OEHS White Paper 3-3d
1.6.3 Task 3. Submit need for intelligence products through JPMPG to the Services and DIA. |  | TBD | TBD | Users/JESWG/LMI | Need to define requirements. Additionally, channels currently exist for intelligence production requirement submission. | OEHS White Paper 3-3d
1.6.4 Task 4. Develop basic references list for field deployment and provide to medical intelligence for distribution to personnel performing OEHS. |  | 2000-10-01 | TBD |  |  | MRSP AP1.1.1.4.3, AP1.12.3.4.1
[5 empty] | Reassess requirement & define Service needs & what exists. | PRD-5 DH 1.1.2;
OEHS White Paper 3-3d
1.6.5 Task 5. Develop an information paper identifying procedures for requesting and accessing hazard identification guidance from the intelligence community to include: |  | 1999-12-01 | TBD | AFMIC | Reassess need & what is currently available. | MRSP AP1.1.1.4.3, AP1.12.3.4.1
- currently available intelligence products | [5 empty] | PRD-5 DH 1.1.2
- procedures for requesting new intelligence products
- procedures & restrictions in accessing intelligence products
1.6.6 Task 6. Develop input for Joint & Service doctrine for requesting & evaluating medical intelligence. |  | TBD | TBD | JESWG/LMI | On Hold. Policy and Doctrine Gap Analysis should identify any shortcomings
1.7 Objective 7. Develop a “global” joint Operational Risk Assessment/Risk Management Guidance document for OEHS in terms of ORM to include: (a) chemical exposures, (b) ionizing radiation hazards, (c) physical agents (heat, noise, non-ionizing radiation), and (d) biological hazards. | [5 empty] | MRSP AP1.2.1.3,
AP1.10.3.3,
AP1.10.5.3,
AP1.12.1.3
AP1.12.3.3
PRD-5 DH 1.1, R&D 2.9, 4.4
1.7.1 Task 1. Inventory current ORM guidance and distribute to JESWG members to confirm completeness. |  | 2000-03-01 | 2000-10-11 | LMI | As part of inventory and gap analysis | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1
1.7.2 Task 2. Review existing ORM guidance and provide comments for an approach. |  | TBD | TBD | JESWG members | CAPT Gillooly, NEHC presented Navy’s efforts to incorporate risk assessment with ORM, 17 May 2001. | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1
1.7.3 Task 3. Consolidate JESWG member comments and propose an ORM approach and guidance document outline. |  | TBD | TBD | LMI | Completed TG 248 published August 2001 | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1
1.7.4 Task 4. Provide draft TG 230B for JESWG review. |  | 1999-12-01 | Dec 02 | USACHPPM | Completed TG 230 published January 2002 | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.7.5 Task 5. Review & provide comments to draft TG 230B |  | TBD | TBD | JESWG members | Completed TG 230 published January 2002 | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.7.6 Task 6. Consolidate comments and publish TG 230B. Distribute to Service doctrinal offices. |  | TBD | TBD | CHPPM | Completed TG 230 published January 2002 | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.7.7 Task 7. Review & recommend policies & guidance for application of ORM to chemical exposures. |  | 2000-07-26 | 2002-01-01 | Tony Pitrat, USACHPPM | Completed TG 248 published August 2001 | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.7.8 Task 8. Submit draft joint policy (covering technical guides & ORM) to JPMPG for approval. |  | 2001-01-01 | TBD | Tony Pitrat, USACHPPM | Need to define requirements-Reassess Status | MRSP AP1.12.1.4.4
PRD-5 DH 1.1.1, R&D 4.4.1
1.8 Objective 8. Develop draft policy & guidance for risk communication of the results of OEHS & ORM activities. | [5 empty] | MRSP C1.6.12.2.3., AP1.2.1.3, AP1.10.3.3,
AP1.12.1.3,
AP1.12.3.3,
PRD-5 DH 1.1
1.8.1 Task 1. Develop risk communication handbook for OEHS activities. Distribute to Service doctrinal offices. |  | TBD | TBD | USACHPPM Risk Comm. Office | Need to define requirements-Reassess Status
1.8.2 Task 2. Develop documentation procedures for tracking risk communications involving OEHS activities. Distribute to Service doctrinal offices. |  | TBD | TBD | USACHPPM Risk Comm. Office | Need to define requirements-Reassess Status
1.8.3 Task 3. Train OEHS personnel in risk communication techniques. |  | TBD | TBD | USACHPPM Risk Comm. Office | Need to define tasks-Reassess Status
1.9 Objective 9. Develop sampling data quality objectives (how many, locations) for collection of environmental/occupational hazards | [5 empty] | MRSP AP1.10.3.3,
AP1.12.1.3,
AP1.12.3.3
PRD-5 R&D 4.4
1.9.1 Task 1. Develop sampling data quality objectives for chemical exposures (TG 251). Distribute to Service doctrinal offices. |  | 2000-10-01 | TBD | USACHPPM DESP | TG251-Reassess Status | MRSP AP1.12.1.4.4
PRD-5 R&D 4.4.2
1.9.2 Task 2. Develop sampling data quality objectives for ionizing radiation exposures (TG 236A & B). Distribute to Service doctrinal offices. |  | 2000-10-01 | TBD | USACHPPM Health Physics Program | Reassess Status | MRSP AP1.12.1.4.4
PRD-5 R&D 4.4.2
1.9.3 Task 3. Develop sampling data quality objectives for exposures to physical agents (including non-ionizing radiation). Distribute to Service doctrinal offices. |  | TBD | TBD | USACHPPM | "physical agents" needs better definition-Reassess Status | MRSP AP1.12.1.4.4
|  |  |  | NonIonizing, IH, Etc ??? |  | PRD-5 R&D 4.4.2
1.9.4 Task 4. Develop sampling data quality objectives for exposures to biological agents, including entomological. Distribute to Service doctrinal offices. |  | 2000-10-01 | 2001-03-01 | USACHPPM Entomological Sciences Program | Reassess Status | MRSP AP1.12.1.4.4
PRD-5 R&D 4.4.2
1.10 Objective 10. Establish procedures to access and combine all available exposure data, regardless of data source or job specialty performing the data collection. | [5 empty] | MRSP AP1.10.3.3,
AP1.12.1.3,
AP1.12.3.3
PRD-5 R&D 1.2
1.10.1 Task 1. Inventory occupational and environmental data sources (e.g. Veterinary inspections, Environmental Security, other federal agencies, allies, civilian sources, etc.) and determine what data is pertinent to OEHS and should be accessible by a central OEHS database |  | 2000-11-01 | TBD | USACHPPM DESP, LMI | On Hold-Reassess Status | MRSP AP1.12.1.4.8
PRD-5 R&D 1.2.1
1.10.2 Task 2. Establish procedures to consolidate OEHS data. Distribute to Service doctrinal offices. |  | 2001-01-01 | TBD | USACHPPM DESP, LMI | On Hold-Reassess Status | OEHS White Paper 3-2c
2. GOAL: Identify resource requirements to implement OEHS
2.1 Objective 1. Provide personnel to perform OEHS. | [5 empty] | MRSP
C1.6.6.2.1.,
C1.6.12.2.1.,
AP1.1.1.3,
AP1.1.2.3,
AP1.2.1
AP1.12.1.3
PRD-5 DH 1.1, R&D 5.2
2.1.1 Task 1. Perform a gap analysis between the force structure required by the White Paper and the existing force structure (including non-DoD capability). |  | TBD | TBD | TBD | MAJ Stokes, AMEDD C&S presented update on Army MFP-ICT, 17 May 2001. | MRSP AP1.6.1.3;
• organizations & teams | [5 empty] | PRD-5 R&D 5.2.2; OEHS White Paper 4-4
• Active & Reserve
• each echelon of support
• capability of each organization (including capability in other business areas, such as Environmental Security)
• number and skill sets of individuals assigned to organizations
• career path for OEHS support personnel & PM leaders
2.1.2 Task 2. Develop Defense Planning Guidance (DPG) & Medical Planning Guidance (MPG) for OEHS staffing. |  | TBD | TBD | JESWG | Need to review current DPG & DMPG | MRSP
AP1.12.2.4.4
PRD-5 R&D 5.2.2
2.1.3 Task 3. Program billets & funding for required staffing level. |  | TBD | TBD | Military Services | Outside JESWG | MRSP
AP1.12.2.4.4
PRD-5 R&D 5.2.2
2.1.4 Task 4. Provide tri-service data analysis and reporting center |  | TBD | TBD | CHPPM | Need to define what currently exists within Services | FY 99 Defense Authorization Act, Sctn 743;
ASD(HA) memo, 30 Sep 99;
FY 02-07 Medical Planning Guidance;
OEHS White Paper 3-3a;
2.2 Objective 2. Train personnel to perform OEHS. | [5 empty] | MRSP AP1.7.1.3,
AP1.12.1.3
PRD-5 Research Priority Area 1;
PRD-5 DH 2.1, 2.2; R&D 4.1, 4.2.2
2.2.1 Task 1. Identify OEHS training requirements for all DoD and non-DoD positions, content of training, and frequency of training. |  | TTBD | TBD | JESWG | COL Lynch, AMEDD Ctr & School presented Army Training Initiatives, 16 May 2001. | MRSP C1.6.1.1.,AP1.7.1.3 (Joint Medical Readiness Training Needs Analysis Work Group);
• Preventive medicine community (officer, enlisted, civilian, contractor) | [5 empty] | PRD-5 DH 2.1.5;
- leadership (knowledge of OEHS) |  |  |  |  | MAJ Stokes, AMEDD C&S presented update on Army MFP-ICT, 17 May 2001. | OEHS White Paper 4-2, 4-3
- organizational awareness
- operational training |  |  |  |  | Need to establish training requirements
- medical readiness planning
- medical intelligence |  |  |  |  | Reassess Status
- foreign area specialty
- risk assessment
- exposure assessment
- environmental Modeling
- health effects of low-level exposures (environmental/chemical/NBC)
- sampling strategy/protocol/procedures
- risk communication
- equipment proficiency training
- drivers license
- software operating procedures
- contracting
• non-OEHS military courses (basic & advanced courses for enlisted, NCOs, WOs, and Officers; and for Command, Staff, and Senior Service programs)
• Joint & multi-national OEHS training
2.2.2 Task 2. Identify gaps between training requirements and training currently provided in each Service’s AC and RC (including training from other business areas, such as Environmental Security). |  |  | TBD | Navy School of Health Sciences; AMEDD C&S/Combat Develop., AF Aerospace Med/ Sheppard AFB | COL Lynch to coordinate training initiatives between AC&S & AF counterparts in San Antonio. | MRSP AP1.7.1.3 (Joint Medical Readiness Training Needs Analysis Work Group)
|  | TBD |  |  | Brief to 1Q FY 02 JESWG meeting | PRD-5 DH 2.1.5
OEHS White Paper 4-2a.
2.2.3 Task 3. Fund & provide training to fill gaps between existing & required training in Service ACs and RCs, and the Joint Staff. |  |  |  | Schools, Surgeons General | Outside JESWG | MRSP AP1.7.1.3,
|  | TBD | TBD |  |  | AP1.7.2.3,
AP1.7.3.3,
AP1.7.4.3
(Joint Medical Readiness Training Needs Analysis Work Group)
PRD-5 DH 2.2.1 OEHS White Paper 4-2a, 4-2b, 4-2d
2.2.4 Task 4. Develop OEHS scenarios for inclusion in training exercise plans. |  | TBD | TBD | TBD | Need to define scenarios and criteria for evaluation | OEHS White Paper 4.2a.
• Active & Reserve Components
• Joint, multinational and Service training exercises
2.3 Objective 3. Provide materiel to perform OEHS. | [5 empty] | MRSP C1.6.4.2.2., AP1.12.1.3
PDR-5 DH 2.1, R&D 4.4, 4.1.5, 5.2, OEHS White Paper 4-5.
2.3.1 Task 1. Identify materiel requirements from the OEHS White Paper to perform OEHS at each echelon (field medic, field PM teams, theater labs & other intermediate support, Service labs, DoD support center). |  |  | TBD | JESWG | MAJ Malone & Mr. Becker presented update on JFCOM FMP ACTD 16 may 2001. | MRSP AP1.3.3.3,
- Sampling equipment (e.g. LEL/O2 meters, air pumps, hazmat kit, passive dosimeters, active dosimeters, soil kits, water kits, direct reading, ambient air samplers [real time], vector collection equipment, microbiological incubator, water testing equipment, toxic chemical & biological warfare detection & warning, lightweight portable CB agent & TIM detector, individual exposure detector, heat stress monitors |  | TBD |  |  |  | AP1.4.2.3
- C4I (computers, software/database/modeling, communications equipment, internet access, CD-ROM, resources on CD-ROM, printers). |  |  |  |  | MAJ Stokes, AMEDD C&S presented update on Army MFP-ICT, 17 May 2001. | PRD-5 DH 2.1.5
- Protective equipment (sprayers, pesticides, PPE, mosquito netting, sunscreen, repellant) | [5 empty] | OEHS White Paper 3-3b, 3-3c, 4-5.
- Vehicles (dedicated) |  |  |  |  | Reassess Status
- Contract capability
- Maps
2.3.2 Task 2. Inventory existing materiel and identify gaps between required & existing materiel (including materiel used in other programs, such as NBC, safety, pollution prevention, environmental compliance and environmental cleanup). |  |  | TBD | Medical Logistics | What have Services done? Reassess need | MRSP AP1.4.2.3,
|  | TBD |  |  |  | AP1.11.1.3
PRD-5 DH 2.1.5
2.3.3 Task 3. Identify statement of need to fill materiel gaps through JPMPG to the military medical combat developers (acquisition community). |  |  |  | Combat Development; HSW Brooks; ONR/MRMC, CBW community; AFRL; SG staff | What have Services done? Reassess need | MRSP C1.6.11.2.1., AP1.4.2.3,
|  | TBD | TBD |  |  | AP1.11.1.3 (ASBREM)
AP1.12.1.3, AP1.12.1.4.2
PRD-5 DH 2.1.5, R&D 5.2.1
OEHS White Paper 3-3d
2.4 Objective 4. Provide information management system(s) with OEHS capability to enhance risk assessment data collection & analysis, and ORM risk communication to commanders | [5 empty] | MRSP C1.6.3.2.2., C1.6.10.2.3.
OEHS White Paper 3-3a
2.4.1 Task 1. Identify OEHS information management (IM) requirements |  | 1998-06-01 | 1998-11-01 | JESWG/LMI | Completed | OEHS White Paper 3-3a
2.4.2 Task 2. Perform gap analysis between IM requirements and current capability |  | TBD | TBD | JESWG/LMI | On Hold. Reassess need | OEHS White Paper 3-3a
2.4.3 Task 3. Submit need for IM requirements for acquisition of IM capability. |  | 1998-12-01 | TBD | JESWG/LMI | On Hold. Reassess need | OEHS White Paper 3-3a
3. GOAL: Monitor OEHS implementation to ensure effective operational support.
3.1 Objective 1. Develop MOEs and MOPs to implement the JSI. | [5 empty] | MRSP AP1.12.2.3
PRD-5 DH 2.1, 2.3
3.1.1 Task 1. Develop MOEs and MOPs for : |  | TBD | TBD | Recommend: | On Hold. What have Services done? Reassess need | MRSP C1.6.12.2.2., AP1.12.2.4.1,
-Organization |  |  |  | -ID current subgroups or create JESWG subgroup to develop MOEs/MOPs |  | AP1.12.2.4.2
-Policy | [5 empty] | JPMPG Charter 1,2
-Materiel and Equipment | 1 |  |  |  |  | PRD-5 DH 2.3.x
-Training
-IM/IT
-Manpower
-RDT&E
-Evaluation Matrix
3.1.2 Task 2. Develop standard protocol for after-action reports (AARs) and review |  | TBD | TBD | Subgroup with AFMIC support | Reassess need. Believe procedures already exist. | MRSP AP1.12.2.4.1,
-JULLS | 3
-Recommend improvements to existing AAR process | [5 empty] | JPMPG Charter 1,2
PRD-5 DH 2.3.x
3.1.3 Task 3. Recommend MOEs, MOPs and AAR protocols to JPMPG for policy/guidance |  | TBD | TBD |  | On Hold. Reassess need. | MRSP
| 1 |  |  | JESWG to JPMPG |  | AP1.12.2.3
JPMPG Charter 1,2
PRD-5 DH 2.3.x
3.2. Objective 2. Implement the evaluation criteria.
3.2.1 Task 1. Collect performance/effectiveness data. | 1 | TBD | TBD | Service Reps | Reassess need. What have Services done? | MRSP
|  |  |  | (NEHC, USACHPPM, AFIERA) |  | AP1.12.2.4.3
3.2.2 Task 2. Compare MOEs and MOPs to data and to JSI intent. |  | TBD | TBD | JESWG | Reassess need. What have Services done? | MRSP
| 1 |  |  |  |  | AP1.12.2.4.3
3.3. Objective 3. Establish a feedback loop and reassessment process of the vital areas: Organization, Policy, Material, equipment, manpower, R&D, Training and IM/IT | [5 empty] | MRSP
AP1.12.2.4.3
3.3.1 Task 1. Evaluate OEHS activities and capability (OEHS and non-OEHS organizations & personnel). | 2 | TBD | TBD | Service Reps | Capabilities document of Service PM units being prepared Dec 2002. Reassess need. What have Services done? | MRSP
|  |  |  | (NEHC, USACHPPM, AFIERA) |  | AP1.12.2.4.3
3.3.2 Task 2. Perform gap analysis between current and required OEHS capability from the OEHS White Paper. | 1 | TBD | TBD | Service Reps | Reassess need. What have Services done? | MRSP
|  |  |  | (NEHC, USACHPPM, AFIERA) |  | AP1.12.2.4.3
3.3.3 Task 3. Provide status through JPMPG to Services and Joint Staff of required changes to OEHS capability. | 2 | TBD | TBD | JESWG | Reassess need. What have Services done? | MRSP API.12.2.4.3