## Action Items
Identifier | Action Item Description | Owner | Participants | Origin | DateOpen | Category | Status | DateTarget | DateClosed | Next Steps
Reference number (decimal) | Describes what the action item is - might include rationale, constaints and expected outcomes | The name of the individual accountable for the completion of the action item | Individuals or groups working with the owner on the action item | WGM- Working Group Meeting CC- Conf.Call INT - Interim OTH- Other | YYYYMMDD | RIM/HDF/MIF/Vocab/Admin/Guide/Action/ etc. | Active-blank Complete Held Nullify Suspend | Target completion date YYYMMDD | YYYYMMDD | Next steps to include: who will do what and by when
1 | Publish RIM to wider audience | Woody |  | CC | 20030822 |  |  |  |  | Formal publication of RIM to be submited to ISO
2 | Update MnM info on HL7 web site | AMS |  | CC | 20030822
3 | HL7 V3 Developer's Guide | Woody |  | CC | 20030822
4 | Ballot 4 followup - clear negative ballots | Woody |  | CC | 20030822 |  |  |  | 20031219
5 | HL7 V3 inventory of pilot projects | Jane |  | CC | 20030822 |  |  |  |  | Follow up patient care with Charlie
6 | Prepare MnM facilitator's toolkit | Jane |  | OTH | 20030822
7.1 | HDF transition plan | Mead |  | CC | 20030822
8 | Memphis - review Action Item granularity | Ben |  | CC | 20030822 |  |  |  | 20031219
9 | Create harmonization document template in order to adequately capture resolutions, outcomes, actions, comments, votes, etc | Ann |  | CC | 20030711
10 | Create definition of V3 interoperability | Jane |  | CC | 20030815 |  |  |  |  | Complete partial draft
11 | Memphis - Research a user-friendly communication style; one page description of functional requirements | Kathleen |  | CC | 20030815 |  |  |  |  | Kathleen to forward documentation to MnM Co-chairs
12 | Memphis - Discuss impact of MIF; focus on interoperability on the dynamic side, which is still in change | Lloyd |  | CC | 20030815 |  |  |  | 20031219
13 | Memphis - Develop a style guide to help committees with consistency in use of Trigger Events | Jane | Lloyd | CC | 20030815
14 | Create a communication document to take to the sponsors of major efforts like EHR and the Registry project; start with one page | Jane | Linda | CC | 20030815 |  |  |  |  | Review minutes
15 | Memphis - Review draft of updated HL7 mission statement, with the objective to present present to the TSC in January 2004 | Jane | Lloyd / Ben | CC | 20030815 |  |  |  |  | Jane to add to agenda ofr next ARB meeting
16 | Reolve CMET SIF isue with closing ballot items | AMS |  | CC | 20030822
17 | Review Action item tracking Project Charter | MnM Co-Chairs |  | WGM | 20030912 |  |  |  |  | Add to MnM Conference call meeting of January 9, 2004
18 | Open issue - deprecate SUBS code | Harold | Woody | CC | 20030711
19 | Open issue - rename ActAlertCode | Harold | Woody | CC | 20030711
20 | Question - vocabulary entries | AMS |  | CC | 20030711 |  |  |  | 20031219
21 | White paper to talk about interactions - Lloyd, AMS, Kathleen, Jane, Laura, Ben (Mead after first draft) | Lloyd |  | WGM | 20030912 |  |  |  | 20031219
22 | Revisit structured sort names | Lloyd |  | WGM | 20030912
23 | Further discussion item: CMETs their interrelationship and implications for ballot reconciliation | AMS |  | WGM | 20030912
24 | Style guide for naming structured attribute and corresponding vocabulary | Harold | Woody | WGM | 20030912
25 | Conference call ED / ST - notify list server and HQ | AMS |  | WGM | 20030912 |  |  |  | 20031219
26 | Develop actions items for MIF and Tooling | Woody |  | WGM | 20030912
27 | Discuss OCL and Templates | AMS |  | WGM | 20030912
28 | Add decimal fro ID - Action Tracking | Ben | done | WGM | 20030912 |  |  |  | 20031219
7.2 | HDF implementation guide | Jane | Ben | WGM | 20030912
29 | MnM needs to figure out how the vocabulary for non structural items is related to balloted specifications. | AMS | Ted | CC | 20030926
30 | Adrian Elakey will work as liaison with Johannes Ernest to see if he will be able to attend the November Interim meeting | AMS |  | CC | 20031010 |  |  |  | 20031219
31 | Naming style guide | AMS |  | CC | 20031003
32 | Process for open issues to be determined | Jane |  | INT | 20031117
33 | CA/CSA item needs to be verified (III FICR) | Ann |  | INT | 20031117
34 | BllodProductTypeCode - 2 SIGs to review | Ann |  | INT | 20031117
35 | Version and release values (V CQ) | Woody |  | INT | 20031117 |  |  |  | 20031219
36 | Generating standard version codes CQ/MnM | Woody |  | INT | 20031117
37 | Definition portions of the RIM (V! PM) - align rim and vocab defintions for classes - renamce | Woody |  | INT | 20031117
38 | Modeling Junrisdcition (VII) = Document resolution of | Linda |  | INT | 20031117
39 | Blocking access to download (VII) Break public accessto commpostie rim file - rename | Woody |  | INT | 20031118
40 | Dynamic Model proposal (IX) - dc0ument | Woody |  | INT | 20031118
41 | VA deliverables documentation | Woody |  | INT | 20031118
42 | Europe meeting - feedback to HQ | Jane |  | CC | 20031107 |  |  |  | 20031219
43 | Europe meeting - agenda | Jane |  | CC | 20031107 |  |  |  | 20031219
44 | Harmonization arragements (section 6) | Jane/Greg |  | CC | 20031107 |  |  |  | 20031219
45 | Resolve business process for action item | MnM Co-Chairs |  | CC | 20031107 |  |  |  |  | Resolve then document
46 | Update action list after co-chair feedback | Ben |  | CC | 20031107 |  |  |  | 20031219
47 | Entity.id - develop statement of principles | Jane |  | CC | 20031205
48 | No way to tell fixed value in schemas | AMS |  | CC | 20031219 |  |  |  |  | What is the rule within the XML ITS? / Hot topic San Diego
49 | Negation indicators - define process(update) | AMS | Greg | CC | 20031219
50 | Schedule early adopter breakfast SD WGM | Woody |  | CC | 20031219
51 | Early adopter web site page | Woody |  | CC | 20031219 |  |  |  |  | Woody to discuss with NIST
52 | Cross-committee issue/resolution tracking | AMS |  | CC | 20031212 |  |  |  |  | Fro both email conversations and meeting discussions
53 | Mechanism to alert MnM - RIM discrepancy | AMS |  | CC | 20031212
54 | Relationships with interactions (HL7 v3 com) | AMS |  | CC | 20031212 |  |  |  |  | Email thread - clarification and write up after conclusion
7.3 | HDF peer review | AMS |  | CC | 20031212 |  |  |  |  | Scheduled for January 9, 2003
55 | Changes - Action item tracking speadsheet | Ben |  | Other | 20031222 |  |  |  |  | Add Next steps column and archive closed items