## Sheet4
Master Close-out list for Capital Projects
to be completed by Project Manager |  | PLATE
During Course of Project
To Improve Close-out Culture |  | Sample, see attached Cauthen House actual Close-out data
| Description of Data Required |  | Listing of Required Data
Project Title
Project Number, ( State No.)
Building Number, ( FAACS )
Architect / Engineer, ( Firm Name )
Contractor, ( Firm Name )
Gross Square Feet ( GSF ) new + renovated space
Bid Opening Date
Note ---> | A good close-out starts at the | Copy Attached | x | Copy Scanned | x
beginning of the Project
|  | Date |  | Comments
Form CO-8b ( Opinion of A/E Performance ) follows CO-6
Operation and Maintenance Manuals Delivered *
Equipment Warranties and Guarantees Delivered *
Preventive Maintenance Inventory Data Delivered *
Compliance with State Roofing Requirements per CPSM *
Fire Marshal's Final Inspection Letter
Form CO-13.3b ( Checklist for Beneficial Occupancy )
Record Drawings Delivered to Resource Center *
Elevator Inspection Certificate
| Form CO-12 ( Certificate of Payment-Final ) |  |  | Electronic copy required for BCOM
Form CO-13 ( Affidavit of Payment of Claims )
Form CO-13.2 ( Certificate of Completion by Contractor )
Form CO-13.1 ( Certificate of Completion by Arch./Engr.)
Form CO-13.1b ( Report of Structural and Special Insp.)
Form CO-13.3 ( Certificate of Use and Occupancy )
| Form CO-17 ( Building Permit ) accompanies HECO-6 |  |  | Hard copy to RESM, signed by Project Manager
Form CO-14a ( Opinion of A/E Performance )
Form CO-14b ( Opinion of Contractor Performance )
| Form CO-14 ( Project Completion Report ) |  |  | Electronic copy required for BCOM
Total Project Cost
Cost Per Bed / Unit
| Cost Per Square Foot | #DIV/0!
* Process Transmittal Document
| The disposition of these Transmittals will be determined by | Project Manager -->
| See separate instructions on performance requirements. | Signature ------>
Performance requirements of Project Managers
| regarding proper instructions to Contractors / Operations |  |  | Draft
to accomplish desired goals of FP&C in the following
| four areas of importance : |  |  | Incomplete
| 1. Operation and Maintenance manuals, including |  |  | Preliminary
all information detailed in contract specifications.
The Contract Documents should clearly explain the process
of this requirement.
A. How many copies should be delivered ---- Two (2)
B. To Whom should they be delivered ----- A/E Firm
C. Accompanying these Manuals should be a data sheet inventory
of all installed equipment and components, listed by Specification Division
Categories, such as Architectural, Elevators, HVAC, Electrical, BAS etc.
D. This list should be accompanied by the corresponding submittal
for all installed equipment and components, for comparison by
Operations personnel, when preparing the preventive maintenance document
E. Warranties and Guarantees should be included with Manuals.
2. Preventative Maintenance Inventory Data,
to be prepared by Operations in-house trade specialists with time charged to project, against a fixed fee.
A. Each Operations cost center will be responsible for reviewing the Preliminary and 95% documents,
and visiting the job site to become familiar with the Project, for the purpose of preparing accurate
preventive maintenance records, to be delivered to Work Management shortly after final
demonstration of equipment. ( 1 week )
B. These maintenance records should be compared with the data sheet inventory and submittals,
presented by the Contractor, for completeness and accuracy.
C. The purpose of these records is to identify all equipment that requires periodic maintenance and
establishes the frequency of this maintenance. The format of this information may be altered by
each cost center for their convenience, as long as it accomplishes the goal of the process.
3. Record Drawings,
A. Contractor will maintain Marked-up Drawings and Submittals for presentation
to the A/E firm immediately prior to the substantial completion date.
B. Project Manager will arrange for electronic copies of record drawings ( as-builts )
to be prepared by the A/E firm and delivered to the FP&C Resource Center.
For most projects, Mylar copies will also be requested for the Resource Center.
On other ocassions the Resource Center may see that data is entered into GIS.
4. State Roofing Requirements, ( CPSM - Section 707.B )
particular attention should be given to the following requirements because the CPSM form CO-14
requires that documented proof be submitted with close-out documents.
A. Contractor's 2 year guarantee ( 707.B.7 )
B. Manufacture's standard warranty / guarantee ( 707.B.7 ) - 15 years min.
C. Certification that materials comply with ASTM standards ( 707.B.10 )
D. Survey report ( 707.B.14.7 )
E. Historical record ( 707.B.15.1.4 ) - appendix G, form A
This information is not intended to replace Contract Document language but hopefully assist
the Project Manager in clarifying the intent of that language in those documents.