## Summary & Timeline
Core Activity
Preparation/Follow-up
Task | Task Description | Organization(s) | 2003 | [11 empty] | 2004 |  |  |  | 2005 |  | 2006 |  | 2007 |  | 2008
|  |  | J | F | M | A | M | J | J | A | S | O | N | D | J-F-M | A-M-J | J-A-S | O-N-D | J-J | J-D | J-J | J-D | J-J | J-D | J-J | J-D
1.0 | PM-2.5 Designations | States & EPA
2.0 | Natural & Baseline Conditions
2.1 | Technical Memorandum for Natural and Baseline estimates (review by air directors) | ME, NH, VT, NJ w NESCAUM & TSC | bar: 2003 M to 2003 O
2.2 | Stakeholder Review of Baseline and Natural Conditions Estimates | ME, NH, VT, NJ w NESCAUM, MARAMA, OTC & TSC | bar: 2003 N to 2003 D
2.3 | MANE-VU Adoption of Methodology for Baseline and Natural Conditions Estimates | OTC & MANE-VU Directors & Board
2.4 | Inter-RPO and Intra-RPO Discussions | ME, NH, VT, NJ w NESCAUM & TSC
3.0 | SIP Template Development
3.1 | Develop SIP Template (review by Air Directors) | TSC w MARAMA | bar: 2003 M to 2003 S; 2003 N to 2003 D
3.2 | External Review of SIP Template | TSC w MARAMA | bar: 2003 O
3.3 | MANE-VU Directors Approval of SIP Template | OTC w MANE-VU Directors
4.0 | Technical Support Activities
4.1 | 2002 Inventory (from technical work plan A2) | States and MARAMA
4.2 | Future Inventory (2013 and 2018) (from technical work plan A11) | States and MARAMA
| Stakeholder review of Inventory | MARAMA and states
| Emissions Modeling | NESCAUM, NY, Others?
| Identify Potential BART Sources | NESCAUM and States | bar: 2003 J to 2003 J
4.3 | Modeling (from technical work plan C5) | NESCAUM & Modeling Work Group | bar: 2003 J to 2003 D
4.4 | Source Apportionment Analysis (from technical work plan D3) | MARAMA & Data Analysis Work Group
4.5 | Contribution Assessment (from technical work plan D5) | NESCAUM & TSC
5.0 | Final technical support documents and weight of evidence
5.1 | Consolidate technical documentation (annually) | NESCAUM & MARAMA
5.2 | Internal review process | NESCAUM & MARAMA
5.3 | Final technical support documents and weight of evidence | NESCAUM & MARAMA
6.0 | Identify and analyze alternatives for goals and strategies
6.1 | Define equitable and effective multi-p strategy for eastern US | TSC w NESCAUM, OTC & MARAMA
6.2 | Identifying current rules; Federal and State Rules | TSC w NESCAUM & MARAMA
6.3 | Identify Additional Rules, as necessary (Oil Combustion, Burning, etc.) | TSC w NESCAUM & MARAMA
6.4 | Ancillary Benefits Report (economic analysis, health effects and benefits analysis) | TSC with NESCAUM and MARAMA | bar: 2003 J to 2003 D
7.0 | Model Rules for Selected Sources
7.1 | MANE-VU MOA on model rules? | OTC & MANE-VU Directors & Board
7.2 | Develop Model Rules for selected sources, if applicable | TSC w NESCAUM (w other RPOs?)
7.3 | Stakeholder Review of Model Rules for selected sources | TSC w NESCAUM
7.4 | Adoption of rules | States
8.0 | Reasonable Progress Goals
8.1 | Develop reasonable progress goals for MANE-VU Class I Areas (from technical work plan D8) | TSC w NESCAUM & MARAMA
8.2 | Consultation with other RPOs on their Reasonable Progress Goals and vice versa | TSC and Workgroups
8.3 | Analyze feasibility of reasonable progress targets | TSC w NESCAUM & MARAMA
8.4 | Internal review of alternatives for goals and strategies | MANE-VU Directors and OTC
8.5 | Consultation with EPA and FLMs on alternative goals and strategies | TSC w NESCAUM & MARAMA
8.6 | Consultation with other RPOs and stakeholders on alternative goals and strategies | OTC
9.0 | Develop long-term strategy agreement and SIP
9.1 | Develop long-term strategy agreement | TSC w OTC | bar: 2003 D
9.2 | Consultation process | TSC w OTC
9.3 | MANE-VU Director Approval | TSC w OTC
9.4 | MANE-VU Board Approval | TSC w OTC
9.5 | SIP development and hearing | TSC w NESCAUM & MARAMA
10.0 | Submit SIP | States