## Sheet1
Stage-Gate ™ |  |  | EXHIBIT A - Flexi-Trac Client Mapping ™
|  |  | Define Value Proposition | Management Analysis | Market Analysis |  | Financial Analysis | Product Analysis
|  | LEVEL | [7 empty] | PDC Involvement
| Preliminary Investigation | A (Approx. 10 pg Bus Plan) | See Sheet A1 - Statement of how customer value will be created - translate idea into opportunity | See Sheet A2 - Identification of strengths and weaknesses of management team to carry out the value proposition; legal concerns | See Sheet A3 - Layout of market existence, size and acceptance (floating of idea to potential customers), distribution channels |  | See Sheet A4 - financial assessment of rough sales, costs, personal and other investment, ratios | See Sheet A5 - preliminary technical investigation, begin to drive engineering requirements based on market, financial boundaries, identify infringements | Instructions Level A | Available to business consultants ONLY as an advisor
| Bus. Case Investigation | B (Approx. 20 pg Bus Plan) | See Sheet B1 - Redefine value proposition as needed based upon Level A information | See Sheet B2 - Formulate plan for augmentation of weaknesses (partners) to deliver the value proposition for attraction of capital | See Sheet B3 - studies for needs and wants, value in use, in-depth competitive analysis, sales adjustment and price sensitivity, channel requirements |  | See Sheet B4 - translate gathered market information from Levels A & B to financial framework created in Level A | See Sheet B5 - create prints/ mockup (functional or not) to validate/ extend market information/ firmly define engineering requirements, infringement opinion | Instructions Level B | Available to business consultants as advisor; available to clients AFTER other Level activities complete
| Development | C (Approx. 40 pg Bus Plan) | See Sheet C1 - Redefine value proposition as needed based upon Level B information | See Sheet C2 - gannt charting of project; value chain partners to be secured via negotiation of agreements; create plan for operations processing | See Sheet C3 - customer feedback as in Level B continues, secure market channels via negotiation of agreements |  | See Sheet C4 - finalize the analysis and begin to attract needed capital | See Sheet C5 - detail prints and prototyping - eng. req. to be firmly defined, not iterative event due to cost/ time considerations | Instructions Level C | Available to business consultants AND clients during all level activities
| Testing & Validation | D (Bus. P. complete) | See Sheet D1 - Redefine value proposition as needed based upon Level C information | N/A unless management situation has changed from level C; finalize operations processing | See Sheet D3 - user tests (focus groups) and field trials under actual conditions |  | See Sheet D4 - All capital requirements to be met | See Sheet D5 - packaging engineering, lab tests, field trials, pilot production | Instructions Level D | Available to business consultants AND clients during all level activities
| Full Production/Market Launch | E (Bus. P. complete) | See Sheet E1 - Redefine value proposition as needed based upon Level D information | N/A unless management situation has changed from level C | See Sheet E3 - Market studies to drive engineering requirements for next version of product |  | See Sheet E4 - Adjust financial analysis based on reality of launch | N/A unless market launch indicates need for immediate revision | Instructions Level E | Available to business consultants AND clients during all level activities
All activities listed above are pending university review and approval.
All services provided by this office are for information purposes only.
This service is not intended, and shall not be construed as professional consulting service or legal advice.
Questions concerning the propriety or legality of any activities herein should be directed to the appropriate regulatory agencies.