## Timeline Information
Task # | Task Name | Devices | Duration | Hours | Start Date | End Date | Dependency | Staff | All Staff | Hrs/ws
| Network Migrations |  | Days | Labor |  |  |  | 1 week
| Kenai - PD (Pending move) | 10 | 9 | 51.75 | 1999-06-29 | 1999-07-07 | Planning/Wiring/Servers | 1.2937 | 9.7063
| Bethel - PD | 10 | 4 | 51.75 | 1999-07-06 | 1999-07-09 | Planning/Wiring/Servers | 1.2937 | 9.7063
| Soldotna - DMV | 10 | 4 | 51.75 | 1999-07-09 | 1999-07-12 | Planning/Wiring/Servers | 1.2937 | 9.7063
| Juneau - R&B (Pending move will require 2nd install) | 80 | 4 | 414 | 1999-08-15 | 1999-08-18 | RFP on Street to Move | 10.35 | 0.65
| Anchorage - ALP | 36 | 4 | 186.3 | 1999-08-27 | 1999-08-30 | Planning/Wiring/Servers | 4.6575 | 6.3425
| Anchorage - R&B (Pending move) | 15 | 4 | 77.625 | 1999-09-03 | 1998-09-06 | Pending Move | 1.9406 | 9.0594
| Juneau - DMV - Field office | 10 | 4 | 5.75 | 1999-09-10 | 1999-09-13 | Pending Netopia Hub & wiring | 0.14375 | 10.8562
| Juneau - ITG | 75 | 1 | 388.125 |  |  | Pending Network Changes | 9.7031 | 1.2969
| Anchorage - AOGCC (pending move) | 22 | 1 | 113.85 |  |  | Pending Move | 2.8462 | 8.1538
Software Installs
| Fat Client software (10) | 320 | 1 | 552 |  |  | OMB, Finance & others | 13.8 | -2.8 | 1.5 | Ave. Hours per ws install
Database, emulation & connectivity tools
| Hardware Installs | [6 empty] | 2 weeks ea
| New Workstations | 116 | 52 | 600.3 | 1999-06-20 | 1999-08-10 | Orders & software | 7.5037 | 3.4963 | 4.5 | Ave. Hours per ws install
| New Workstations | 116 | 18 | 600.3 | 1999-09-13 | 1999-09-30 | Orders & software | 7.5037 | 3.4963
| New Workstations | 50 | 1 | 258.75 |  |  | Thru 9/30/99 | 3.2344 | 7.7656
Projects
| Calander Upgrades - concurrent with migrations | 853 | 288 | 1471.425 | 1999-01-01 | 1999-10-15 | 4 weeks | 9.1964 | 1.8036
| NetG Netscape plugin - x days after available | 853 | 32 | 490.475 | 1999-05-15 | 1999-06-15 | 4 weeks | 3.0655 | 7.9345
| Y2K Windows O/S patch | 853 | 114 | 490.475 | 1999-03-09 | 1999-06-30 | 4 weeks | 3.0655 | 7.9345 | 0.5 | Ave Hours per ws
| Y2K MS Office patch | 853 | 114 | 490.475 | 1999-03-09 | 1999-06-30 | 4 weeks | 3.0655 | 7.9345
| Y2K desktop test | 853 | 114 | 490.475 | 1999-03-09 | 1999-06-30 | 4 weeks | 3.0655 | 7.9345
| Upgrade Servers to Innoculan 4.0 | 30 | 83 | 17.25 | 1999-03-09 | 1999-05-30
| Upgrade Servers to Managewise 2.6 | 30 | 83 | 17.25 | 1999-03-09 | 1999-05-30 | 1 week | 0.43125 | 10.5687
Maintenance
| Devices@ 1/2 hr. /node/week | 1044 |  | 522 |  |  |  | 13.05 | -2.05

## Migrations Finished
Task # | Task Name | Devices | Duration | Hours | Start Date | End Date | Actual Staff | Projected Staff | Available Staff | Hrs/ws | Why
| Network Migrations |  | Days | Labor |  |  | Project Staff based on 1 week
June '97 - Pre DOAIT - Must be redone
| APOC - Anch | 12 |  | 62.1 |  |  | 3 |  |  | 4.5 | Ave. Hours per ws install - Hardware
| PD - Anch | 45 |  | 232.875 |  |  | 4 |  |  | 1.5 | Ave. Hours per ws install - Software
| OPA - Anchorage | 45 |  | 232.875 | 342 | Start | 4 |  |  | 0.5 | Ave. Hours per ws install - Fat Client Software
| DMV - Juno | 30 |  | 155.25 | 165 | Stay on net | 4
| DMV - Anch HQ | 30 |  | 155.25 |  |  | 4
| DMV - Anch AFO | 30 |  | 155.25 | 988 | Current | 4
| ITG - Anch | 50 |  | 258.75 |  |  | 3
| ITG - Juno | 75 |  | 388.125 |  |  | 3
| ITG - Fbx | 25 |  | 129.375 |  |  | 3
DOAIT Admin Network
| Risk Management | 10 | 13 | 51.75 | 1998-02-17 | 1998-03-01 | 3 | 1.2937 | 1.7063
| Tax Appeals | 5 | 5 | 25.875 | 1998-02-25 | 1998-03-01 | 1 | 0.64687 | 2.3531
| APDI Lab - Juneau | 15 | 7 | 77.625 | 1998-02-23 | 1998-03-01 | 5 | 1.9406 | 1.0594
| Labor Relations | 10 | 4 | 51.75 | 1998-03-26 | 1998-03-29 | 5 | 1.2937 | 1.7063
| DAS | 41 | 46 | 212.175 | 1998-04-01 | 1998-05-16 | 5 | 5.3044 | -2.3044
| General Services - Juneau | 21 | 16 | 108.675 | 1998-05-16 | 1998-05-31 | 5 | 2.7169 | 0.28313
| General Services - Anchorage | 16 | 4 | 82.8 | 1998-05-28 | 1998-05-31 | 2 | 2.07 | 0.93
| ITG - Anchorage | 50 | 10 | 258.75 | 1998-08-12 | 1998-08-21 | 4 | 6.4688 | 5.5312
| DMV - Anchorage HQ | 42 | 10 | 217.35 | 1998-08-12 | 1998-08-21 | 4 | 5.4337 | 6.5663
| Personnel - Juneau | 60 | 15 | 310.5 | 1998-09-01 | 1998-09-15 | 5 | 7.7625 | 4.2375
| Finance - Juneau | 70 | 40 | 362.25 | 1998-10-12 | 1998-11-20 | 5 | 9.0563 | 2.9437
| PD - Fairbanks | 21 | 35 | 108.675 | 1998-12-11 | 1999-01-14 | 2 | 2.7169 | 9.2831
| DMV - Fairbanks | 15 | 35 | 77.625 | 1998-12-11 | 1999-01-14 | 4 | 1.9406 | 9.0594
| OPA - Fairbanks | 14 | 35 | 72.45 | 1998-12-11 | 1999-01-14 | 4 | 1.8112 | 9.1888
| R&B - Anchorage | 15 | 7 | 77.625 | 1998-12-18 | 1998-12-24 | 1 | 1.9406 | 9.0594
| OPA - Anchorage | 45 | 56 | 232.875 | 1999-01-08 | 1999-03-04 | 4 | 5.8219 | 7
| Senior Services - Juneau | 13 | 8 | 67.275 | 1999-01-08 | 1999-01-15 | 3 | 1.6819 | 8
| Pioneers homes - Juneau | 17 | 8 | 87.975 | 1999-01-08 | 1999-01-15 | 2 | 2.1994 | 9
| Y2K Office - Juneau | 5 | 6 | 25.875 | 1999-01-10 | 1999-01-15 | 1 | 0.64687 | 10
| PD - Juneau | 9 | 7 | 46.575 | 1999-02-04 | 1999-02-10 | 1 | 1.1644 | 10
| OPA - Juneau | 5 | 7 | 25.875 | 1999-02-04 | 1999-02-10 | 2 | 0.64687 | 9
| DMV - Palmer | 9 | 72 | 46.575 | 1998-12-15 | 1999-02-24 | 4 | 1.1644 | 7
| PD - Palmer | 10 | 100 | 51.75 | 1998-12-15 | 1999-03-24 | 4 | 1.2937 | 7
| Anchorage - Personnel Move | 23 | 5 | 119.025 | 1999-02-23 | 1999-02-27 | 1 | 2.9756 | 10
| Juneau - ALP HQ | 24 | 5 | 124.2 | 1999-03-08 | 1999-03-12 | 3 | 3.105 | 8
| Ketchikan - DMV, PD & ALP | 30 | 6 | 155.25 | 1999-03-19 | 1999-03-24 | 2 | 3.8813 | 9
| Anchorage - Senior Svcs. | 57 | 8 | 294.975 | 1999-04-05 | 1999-04-12 | 7 | 7.3744 | 3.6256
| Anchorage - DMV - AFO | 55 | 3 | 284.625 | 1999-04-23 | 1999-04-25 | 6 | 7.1156 | 3.8844
| Sitka - ALP, DMV & PD | 30 | 6 | 155.25 | 1999-04-30 | 1999-05-05 | 3 | 3.8813 | 7.1188
| Anchorage - DMV - 5th Ave Downtown | 10 | 3 | 51.75 | 1999-05-19 | 1999-05-21 | 2 | 1.2937 | 9.7063
| Fairbanks - ALP | 30 | 4 | 155.25 | 1999-05-21 | 1999-05-24 | 4 | 3.8813 | 7.1188
| Palmer - ALP | 22 | 4 | 113.85 | 1999-05-28 | 1999-05-31 | 2 | 2.8462 | 8.1538
| Anchorage - R&B | 14 | 4 | 72.45 | 1999-06-25 | 1999-06-28 | 2 | 1.8112 | 9.1888
| Anchorage - DMV - Eagle River | 10 | 3 | 51.75 | 1999-06-13 | 1999-06-15 | 2 | 1.2937 | 9.7063
| Hardware Installs | [6 empty] | 2 weeks ea
| New Workstations | 300 | 216 | 1552.5 | 1998-07-15 | 1999-02-15
Software Installs
| Fat Client Installs (18x70) | 1260 | 199 | 724.5 | 1998-08-01 | 1999-02-15
Projects
| Netscape Email | 850 | 76 | 1466.25 | 1998-05-01 | 1998-07-15
| Commerce Server Build | 2 | 32 | 80 | 1999-01-15 | 1999-02-15
| Y2K server patches & testing | 46 | 32 | 79.35 | 1998-12-15 | 1999-01-15
| Comtec | 8 | 3 | 41.4 | 1999-02-03 | 1999-02-05
| ITG TNG Project | 200 | 193 | 1035 | 1999-01-04 | 1999-07-15
| Anchorage - Nal/Zen Knoledge transfer | 15 | 5 | 240 | 1999-04-05 | 1999-04-09 | 1 week | 6 | 5
| NT desktops, consoles & servers | 35
| Upgrade Servers to DS 6 | 47 | 84 | 81.075 | 1999-03-09 | 1999-05-31 | 1 week | 2.0269 | 8.9731
Network Failures
| DMV Anch AFO | 25 |  | 80 | 1998-09-01 | 1998-09-05 | 2 |  |  |  | Token Beaconing
| ALP - Sitka | 17 |  | 8 | 1998-11-19 | 1998-11-19 | 1 |  |  |  | Power failure
| DMV Anch AFO | 25 |  | 64 | 1999-01-05 | 1999-01-08 | 2 |  |  |  | Routing
| OPA/PD Building Power failure | 120 |  | 8 | 1999-02-09 | 1999-02-09 | 1 |  |  |  | Power failure
| OPA/PD Building Power failure | 120 |  | 8 | 1999-02-12 | 1999-02-12 | 1 |  |  |  | Power failure
| ALP - HQ (juno) | 24 |  | 32 | 1999-03-06 | 1999-03-07 | 2 |  |  |  | Routing
| Juneau Site Server | 280 |  | 24 | 1999-03-22 | 1999-03-22 | 3 |  |  |  | NIC buffers
| DIS-Juneau | 75 | [8 empty] | Disk Space

## TimelineWizardData (hidden)
H:\VISIO\SOLUTIONS\BUSINESS DIAGRAM\Project Timeline Wizard.exe