## Sheet1
Advanced LIGO UK financial report
Work Package 3
Number | Item | k GBP |  |  | k GBP
|  | Original estimate less WA, no VAT | Spend to date less VAT | approx % complete | Current est cost to completion, no VAT
1 | Noise prototypes
1.1 | Models | 10 | 4 | 100 | 4
1.2 | frames | 5 | 6 | 100 | 6
1.3 | masses | 5 | 4 | 30 | 15
1.4 | other components | 5 | 0 | 0 | 7
2 | main quads
2.1 | structures | 1000 | 650 | 60 | 1100
2.2 | masses | 1000 | 0 | 0 | 950
2.3 | blades | 20 | 10 | 40 | 25
2.4 | wires | 20 | 0 | 0 | 22
2.5 | other parts | 20 | 0 | 0 | 20
3 | OSEMs
3.1 | parts | 500 | 0 | 0 | 500
3.2 | assembly | 500 | 0 | 0 | 500
| consumables | 16.565 | 5 | 30 | 16.5
| travel | 161.116 | 23.6 | 20 | 161.1
| exceptional | 0.914 | 0.2 | 20 | 0.914
Totals |  | 3263.595 |  |  | 3327.514
Current anticipated reserve (+ve) or overspend (-ve) |  | -63.919
Total approved WA drawdown |  | 60
Nett balance (+ve good, -ve bad) |  | -3.919
|  | est | so far |  | est to completion
| Unrefundable VAT | 0 | 0.3 |  | 2
ALUK FINANCIAL REPORT |  |  |  |  | IGRQA0002