## Financial
NAPMW BALANCED SCORECARD
Strategic Plan and Implementation Schedule
Updated November 25, 2002
FINANCIAL
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When: | Champton & contributors
|  | 1. Increase Membership | 1. Develop member profile model | 1. Market vigorously and continuously to make and keep NAPMW a household name | now and ongoing | C = Alana/Jenifer
|  | 2. Increase Corporate Sponsorships | 1. 4200 members by 2003 | 1. Develop and expand benefits so we are perceived as having top value in mind | now and ongoing | John S., Mellissa F., Tracy L.
|  | 3. Operational Revenue Increase (N&L) | 1. 5000 members by 2004/05 | 1. Best education provider in mortgage industry. | now and ongoing
| Increase Stability |  |  | 1. Use Ntl. Quarterly programs in all states to gain presence | 2004-06-01
|  |  | 2. 25 sponsors by 2003 | 1. Press releases go out recognizing achievements of members on all levles | now and ongoing
|  |  | 2. Increased linkages with non-industry manuf. | 1. Develop, implement, and refine recruting program | 2003-05-01
|  |  | 2. Create sponsor program w/ listing of opps. | 1. Develop, implement, and refine retention and recognition program. | 2003-06-01
2. Create sponsor management, communication and recognition program by 3/02.
|  |  | 2. Sponsored newsletter and mag by 2003 | 2. Convention sponsors secured by Jan 1st fo that year's convention | ongoing | C = Alana
|  |  | 2. $30k title level conference sponsor by 2005 | 2. Develop Notes and Deeds sponsor program -- establish separate committee | 2002-05-01 | HQ, sponsor committee, Notes & Deeds chair
|  |  | 2. Manufacturer sponsors by 2003 convention | 2. Meet with MBA to discuss sponsorships | 2002-10-01
|  |  |  | 2. Formal sponsor schmoozing program developed (e.g. reception at convention) | 2003-05-01
|  |  | 3. $100k a year increase starting in 2003 | 2. Script for plugging sponsors to local Assns dvlpd. | now and ongoing
|  |  | 3. Cash flow not from investment account | 2. Evaluate current sposnsor database. | 2002-06-01
|  |  |  | 2. Target group of sponsor to make personal visit to get them on board. (e.g MI Tour). | 2002-08-01
|  |  |  | 2. Send sponsor evaluation asking "How'd we do?" with thank you and asking what else we could do. | 2002-06-01
|  |  |  | 2. Reevaluate sponsor materials and benefits to sponsor dollar levels. | 2002-06-01
|  |  |  | 3. Educational programs generating revenue for National Assn. | ongoing | C = Patty
|  |  |  | 3. Updated branding and look for Assn. to increase membership. | ongoing | Task force members as contributors
|  |  |  | 3. Updated branding and look for Assn. to increase sponsorship | ongoing
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champton & contributors
|  | 1. Develop/expand member benefits | 1. Member benefit opportunity matrix developed by 2003 | 1. Review past surveys of benefits. | 2002-08-01 | C = Jenifer/Patty
| Increase Value | 2. Develop additional professional designations | 1. 90% retention of members by 2003/04 | 1. Create system to track, measure and evaluate benefit usage and requests. | 2004-06-01 | Hulene, HQ, members
| to Members |  | 1. Member benefit demands assessment completed by 2003 | 1. Announcments of members accomplishments to foster netoworking and member exposure. | 2002-06-01 | C = Sara
|  |  | 1. 75% increase in regular membership participation by 2003 | 1. Expand MOM to other publications | 2002-06-01 | members, HQ
|  |  | 2. Two new designations developed by 2004 | 2. Research other designations by state (link to PNPAC's other research) and report to Ntl. Board. | 2004-06-01 | C = Stevie
|  |  | 2. Designation cooperation plan explored by 2003 |  |  | Karen S.
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Increase non dues revenue sources | 1. Identify and rank all sources of non-dues inc. | 1. Web-based national education programs offered. | 2003-06-01 | C = Paula
| Improve the Cost | 2. Create objective-task budget based on strat. Plan |  | 1. Facilitated national education programs offered. | 2003-06-01 | HQ, Patty
| Structure |  | 2. Budget developed and based on plan by 2/02 | 1. Increased sponsorships and advertising from vendors (e.g. Office Max, UPS, MBNA, Kinkos, All-Regs, AirBourne, etc.) and their participation as exhibitors in trade shows. | 2003-06-01
|  |  |  | 1. Increased convention attendance. | 2003-06-01
|  |  |  | 1. Develop turnkey networking/fun events (e.g. bottle auctions). | 2003-06-01
|  |  |  | 2. Budget developed and presented | 2003-02-01 | C = Jenifer
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Increase investment account | 1. Account up to $400k by 2003 |  | 2003-06-01 | C = President-Elect
| Improve Use of | 2. Implement performance-based contracts |  |  |  | HQ
| Assets |  | 2. Implement performance based contracts with all outside vendors and agencies by June 2002. | 2. Review all current contracts and see where we can make changes. | 2003-05-01
2. NAPMW vendors exhibit at convention and participate in advertising via Notes & Deeds, Web Site.

## Member
NAPMW BALANCED SCORECARD
Strategic Plan and Implementation Schedule
Updated November 25, 2002
MEMBER
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Cooperative dues agreement/structure between NAPMW and other industry organizations & associations | 1. Model completed and proposed by 6/02 | 1. Contact MBA to discuss arrangement | 2002-05-01 | C = Patty
| Price |  | 1. Model implemented | 1. Continue proposals to other associations (brokers, realtors, women's organizations, etc.) | 2002-12-01 | Parker D.
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Create Association Management Guide for locals | 1. Guide completed and proposed by 4/1/03 | 1. Appoint task force to review existing materials. | 2003-01-05 | C = Gina
|  | 2. National secures speakers for quarterly programs | 1. Template in place and being used with measurements | 1. Get input form local presidents | 2003-01-05 | Sara, Barbara C., Artie B., Laurel M. R. VPs
| Time |  | 1. Increase in local communication response times | 1. Task force assessment and development of new guide. | 2003-04-01
|  |  | 1. Develop turnkey model and checklist for tradeshows | 1. Implemented on the web | 2003-04-01
|  |  |  | 1. TTT on using LG online (ease of use, shortcuts) | 2002-05-01
|  |  | 2. Model completed and proposed by 6/02 | 1. TTT for local presidents | 2002 Convention
|  |  |  | 1. Evaluate and reinforce | ongoing
|  |  |  | 2. Provide program planning template | 2002-05-01 | C = Stevie
|  |  |  | 2. Provide four topics yearly (seminars for profit) | ongoing | Sara, Verley M., Karen S., U.G. Wolford
|  |  |  | 2. Task force to determine viability (5 members, 1 per region) | 2002-04-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Viable leadership symposium | 1. Model completed and proposed by 6/02 | 1. Announce and schedule symposium for May 2002 | 2002-05-01 | C = Alana
| Quality |  | 1. All incoming association officers attend (local, regional and national) | 1. Define curriculum based on Strategic Plan's goals | 2002-06-01 | Stevie, David K.
|  |  |  | 1. Obtain funding for speaker fees | 2002-08-01
|  |  |  | 1. Prepare planning meeting "cliff notes" | 2002-04-01
|  |  |  | 1. Instruct incoming and outgoing VPs on implementation | 2002-05-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Information and services in multiple languages | 1. Proposal developed and submitted to board. | 1. Survey need for this in Hispanic community | 2003-02-01 | C = Jenifer
| Service |  |  | 1. Prepare recommendations to board based on findings. | 2003-02-01 | Liz V., Eva F.M.
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. NAPMW becomes an educational avenue | 1. Regulatory agencies promote NAPMW | 1. Task force developed to identify what we can offer and what agencies need. | 2003-05-01 | C = Jenifer
| Relations |  | 1. Strategic alliances in place | 1. Agency reps to meet and develop model to take to agencies | 2003-05-01 | Patty A., Ron Ross, Laurie D., Anne S., Beverly
|  |  |  | 1. System for referrals from agencies to locals set up. | 2003-05-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Market to all mortgage professionals | 1. Balanced membership mix of males/females | 1. Research to identify state entities. | 2004-05-01 | C = Hulene
| Image | 2. Update Association visual brand | 1. Innovative and creative marketing and recruitment program in place | 1. NAPMW information distributed to all new licensees in every state. | 2004-05-01 | Region VPs, Local VPs and Presidents
|  | 3. Update Association brand positioning in marketplace | 1. Multiple candidates running each year at National level | 1. Linka NAPMW website to any and all mortgage related sites. | 2003-02-01
|  |  | 1. Develop linkages to state licensing to promote NAPMW membership | 1. Press release to be sent by HQ routinely to all national newspapers and industry publications. | 2002-06-01
|  |  |  | 1. A presence at all mortgage-related conferences | 2004-06-01
2. Re-image association logo and communications to reflect all mortgage professionals (men and women)
|  |  | 2. New materials and visual identity in place | 2. Montly mailers and Notes & Deeds messages to indicate upcoming brand change | Feb. through May 2002 | C = Hulene
|  |  | 2. Logo and image consistently used throughout Association | 2. Task force to review logo ideas, and present to board. | Feb through March 2002 | Mary Ellen, David K., Jessica/Patty, membership
|  |  |  | 2. Reprint all supplies, publicaitons, etc. for unveiling at convention | April & May 2002
|  |  | 3. Consistent messaging created re: value, benefits, purpose, etc. | 2. Packets with templates, masthead, etc to all presidents. | May 2002 Convention
3. Identify positioning points relative to competition
|  |  | 3. Branding campaign implemented | 3. Unveil new brand at May Convention | May 2002 Convention | C = Hulene
|  |  |  | 3. Market new NAPMW brand through media | 2002-06-01 | Mary Ellen, David K., Jessica/Patty, membership
|  |  |  | 3. Market new NAPMW brand through person-to-person | May 2002, ongoing

## Internal Process
NAPMW BALANCED SCORECARD
Strategic Plan and Implementation Schedule
Updated November 25, 2002
INTERNAL PROCESS
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Management training center | 1. In-person training courses nationwide | 1. Contact quick hits for web links (MI companies, VA, FHA, FNMA, FHLMC) | 2003-06-01 | C = Paula
|  | 2. MBA collaboration | 1. Training courses (NAPMW and other) on web site | 1. Build links on NAPMW web site | 2003-06-01 | Jillayne S., David W., Sara V., Annette S., Beverly, Hulene
|  | 3. Formal university collaboration regarding lending curriculum | 1. MML courses on web by 2/02 | 1. Announce resource information to membership | 2003-06-01
| Innovation |  | 1. Collaborative agreement with FHA, VA, FNMA, FHLC etc
|  |  |  | 2. Expand service to NAMB, MBA and other industry related groups (DRE, DOC, Appriaisal Inst.) | 2004-06-01 | C = Paula
2. MBA companies support employees involvement with NAPMW
|  |  |  | 3. Research links to university mortgage courses | 2004-06-01 | C = Paula
|  |  | 3. Five universities across the nation using the IML texts as curriculum in credit courses. | 3. Full implementation of web portal and announcement to members, press, external markets. | 2005-06-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
| Management | 1. Assess value of Association to membership | 1. Competitive analysis of benefits, price, services and delivered value | 1. Develop survey based on member assessment needs. | 2002-05-01 | C = Jenifer
| of Value |  | 1. Membership survey completed with 100% participation | 1. Distribute survey to local presidents and regional VPs at planning sessions with instructions on how to implement to get feedback | 2002-05-01 | Jessica, David K., Board, Locals, members
|  |  |  | 1. Results submitted to Ntl. Board for review | 2002-08-01
|  |  |  | 1. Action plan developed by Ntl. Board based on results | 2002-09-01
|  |  |  | 1. Applicable information entered into database | 2002-10-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
| Operation and | 1. Review the national and region board and committee structures for efficiencies | 1. Review completed and recommendations submitted | 1. Define and inform future leaders of what is expected of them. | 2002 Convention | C = Alana, Jenifer, Paula
| Logistics |  |  | 1. Define what future leaders can expect from the experience of service. | 2002 Convention | Region VPs, Jillayne S., presidents
|  | 2. More effective use of Association database | 2. Integrated communication program in place | 1. Cliff Notes distributed to presidents | 2002 Convention
|  |  | 2. New prospect names (non purchased) added to database | 1. Region meetings at National convention to become planning retreats | 2002 Convention
|  |  |  | 1. National to fund one delegate from each local association if local funds two or more (registration fee only). | 2004 Convention
|  |  |  | 1. Every local association to have a president elect. | 2004 Convention
|  |  |  | 1. By-law change at Convention re: mandatory president elect position | 2003 Convention
|  |  |  | 1. National, regional and local committees to be active and essential, removing any non-essential committees | 2003 Convention
|  |  |  | 1. Board to have and project the same platform | 2003 Convention
|  |  |  | 2. Gather information about Customer Management Software that meets Association's needs | 2002-03-01 | C = Jenifer and Jessica
|  |  |  | 2. Create tier-level proposal for National Board | 2002-04-01 | David K., local presidents,
|  |  |  | 2. Discuss at board meeting | 2002-05-01
|  |  |  | 2. Find financial resources for purchase of database. | 2002-05-01
|  |  |  | 2. Gather information from locals to append to database | 2002-09-01
|  |  |  | 2. Input data into new system. | 2002-12-01

## Learning & Growth
NAPMW BALANCED SCORECARD
Strategic Plan and Implementation Schedule
Updated November 25, 2002
LEARNING & GROWTH
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Define required competencies for levels of leadership service | 1. Articulated by 6/02 | 1. Create a task force to recommend competencies for all levels of leadership service. | 2002-01-01 | C = Alana
|  | 2. Establish professional and leadership development program |  | 1. Report findings to National Board. | 2002-02-01 | John Shore, past presidents
| Competencies |  | 2. Model completed and proposed by 12/02 | 1. Create action plan to address recommendations if needed. | 2002-02-01
|  |  |  | 2. Articulate vision to members for program. | 2003-04-01 | C = Stevie
|  |  |  | 2. Appoint task force to oversee and/or conduct member assessment, develop curriculum, determine/research methods of delivery, create a budget and report findins to the National Board. | 2003-09-01 | members, task force group
|  |  |  | 2. Implement program. | 2003-11-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. Change culture of leadership to a more professional business model | 1. Establish, communicate, implement and measure/reinforce group tenets and behavioral expectations | 1. Board to have open and frank discussion about gossip and negativism. | 2002-02-01 | C = Alana
| Group Culture |  |  | 1. Educational, motivational, and behavioral training to reinforce the goal. | 2002-05-01
|  |  |  | 1. Business ethics training. | 2002-05-01
|  | Description of Specific Goal: | Measure of Success: | Milestones/Actions | When | Champion & contributors
|  | 1. More effective board use of technology | 1. Standardization of tools across board | 1. Line item created in budget for capital expense to purchase appropriate technology equipment and software | 2004-06-01 | C = Jenifer
| Technology |  |  | 1. Board specific technology training | 2004-06-01
|  |  |  | 1. Task force identified and charged with recommending hardware and software for board use. | 2003-06-01
|  |  |  | 1. Purchase of hardware and software, and distribution to National Board members | 2005-07-01