## Sheet1
IMIT Action Plan Status | [13 empty] | Schedule for Action Tasks
Action Plan Task Number | Task Title and Brief Description | Status | Next Steps -- these include suggestions and ideas from informal discussions and are up for review and refinement or consolidation in Dec 3-4 IMIT meeting |  | Roles listed by key FS groups -- some level of coordination and participation is expected/needed across all groups for most activities
|  |  |  | Closely interdependent tasks | IMIT | ESCT | EMC staff | IMI | S&PF, FHM and FIRE | R&D, FIA and Res Sci | WO Program Managers | Regions | IRM staff | FY 01 1st half | FY 01 2nd half | FY 02 1st half | FY 02 2nd half | FY 03 2nd half | FY 03 2nd half
Business Requirements We a lack a uniform, collective understanding of the purpose and objectives for inventory and monitoring programs clearly linked to the business requirements of the agency. More explicitly identifying the links between business needs of the agency and inventory and monitoring activities will help the agency reduce unnecessary efforts, identify priorities for needed work, direct resources to fulfilling those priorities, foster program efficiencies, provide for greater accountability, and improve our ability to share data and information.
TASK 1. Ensure inventory and monitoring activities meet Forest Service business requirements and the needs of our varied customers.
1A | Statement of purpose and objectives of IM | Completed by Doug Powell; put in FSM | Finalize FSM/FSH for I&M |  |  |  | Lead |  |  |  | Participation imperative | Participation imperative |  |  | Completed
1B | Approach for analyzing business requirements | Completed by IMI | Define the process, methods, standards that should be applied to future business rqts analyses (consider why model is needed, consider how the model needs to fit agency goals and objectives, etc). Ensure detailed business models are developed as a component of new protocol development efforts, incorporation of ‘existing’ protocols into the I&M Technical Guide series. Model the 8C process |  |  |  |  | Lead | [6 empty] | Completed
|  |  | Figure out how to overcome tech barriers (software usability, access, etc) |  |  |  |  | Lead
|  |  | Continue existing expertise available in the agency to provide the agency with continuing leadership and support for assessing business needs |  |  |  | Lead
1C | Conduct business requirements analyses | Implemented by protocol teams for Fauna, Human Dimensions, and Program Advisory coordination on I&M program management, partially modeled for agency wide activities driving I&M | Evaluate and publish previous modeling efforts and their products (existing models) to enable agency-wide access, determine strategy for long-term support for future revisions and access, provide advice on extent that bus rqts should be integrated or fully compatible. |  |  |  | Lead | Participation imperative |  |  | Participation imperative | Participation imperative | Participation imperative | Initiated in 2001, ongoing
|  |  | Evaluate if there is value to integrating existing models. Determine to what extent recent models needs or should be compatible in terms of the way and extent that they relate to each other. Determine processes for applying Bus Rqts Models to organizational change. |  |  |  | Lead
|  |  | Evaluate need to update and validate the overarching business model as revisions to BFES and agency performance/accountability systems are completed. Collaborate or use SME from SDIT and other areas when devising I&M models. |  |  |  | Lead |  | Participation imperative | Participation imperative | Participation imperative
1D |  |  | Evaluate how well the recent Bus Rqts work enables the agency to reduce unnecessary efforts, identify priorities for needed work, direct resources to fulfilling those priorities, foster program efficiencies, provide for greater accountability, and improve our ability to share data and information. |  | Lead
Ecological, Social and Economic Systems Different Forest Service units are in various stages of implementing inventory and monitoring programs that integrate data through the use of common database structures and integrated analyses to foster efficient field operations. These 'integrated' inventories attempt to combine parts of traditional inventories, however, the patterns and processes inherent in ecological, social, and economic systems (including biological, physical, and cultural aspects) are not reflected in the design. Therefore the flexibility of inventory and monitoring efforts to respond to changing issues and questions is limited. The agency needs to apply approaches that recognize the complexity of interactions and account for the dynamic nature, potential capabilities, and finite capacities of ecological, social, and economic systems at multiple scales to provide goods and services.
TASK 2. Use a systems approach as the basis for design of inventory and monitoring activities.
2A | Develop knowledge among personnel on systems approach to I & M | Draft systems paper has been completed and reviewed | Complete revisions of systems paper based on review comments adding examples and further explanations of applications |  | Participation imperative |  |  | Lead |  |  | Participation imperative | Participation imperative |  |  |  |  | Revision paper ongoing
|  |  | Publish (as either or both peer reviewed science paper or FS white paper). Describe assistance needed through Task 6G for agency to apply systems approach. | Some info needed to support Task 6G | Participation imperative |  |  | Lead
|  |  | Develop and implement training (info and ed) on systems approach (ensuring eco, soc, and econ systems are included). Explain differences between systems approach and some of the prior approaches to I&M. (will require Regions to sponsor sessions and encourage participation in training, participate in application "trials", complement systems training with other topics such as "sound/credible" data use/reuse, sampling, analysis methods, etc) Link work to Communication tasks 4B and 4C) | Need to include systems info throughout work in Tasks 4B and 4C | Participation imperative |  | Participation imperative | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative
|  |  | Provide consultation and pragmatic methods (cost effective, fit with Mgt objectives/bus needs) to using systems approach. Continue and formalize agency wide collaborative work across deputy areas (and cross-resource programs) to help transition research methods to practical I&M and Planning uses. This would be long-term commitment to service center (or virtual/shared responsibility closely coordinated). Link work to Tasks 8, 6, and 2C. | Systems approach needs to be understood in order to conduct Task 8, 6, and 2C |  |  |  | Lead | Lead | Lead
|  |  | Review and revise Framework to improve its utility to social and economic systems. |  |  |  | Lead | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative
2B | Description of ecological classification schemes | Protocols define appropriate schemes as needed. (documenting their specific scales of data collection and analysis.) | no further action |  |  |  | Lead |  |  |  | Participation imperative |  |  | Ongoing
2C | Evaluate current I&M against systems approach and I&M framework | Compilation of I&M programs feasible based on IMPP, no schedule for evaluation, no technical evaluation required as part of IMPP, no plans affecting S&PF or R&D programs or explicit evaluation across deputy area programs | Document proposal for how IMPP and program reviews can be used as vehicles for ongoing evaluation of I&M programs against framework principles. Expose proposal to review across deputy areas and among national, regional, and forest program managers (including GEB/GAC, RSAC, INFRA, NRIS, GSTC, IMI, and IREMCG). | Relies on info from Task 2A |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Lead | Participation imperative |  |  |  | Scheduled for 2002, not started
|  |  | Evaluate I&M programs against framework (incl systems approach) in organized methodical and comprehensive approach. Include looking at whole picture and evaluating degree that investments reflect business needs and priorities (equitable investment across resource areas). Take advantage of opportunities that arise through IMPP, protocol dev and revision, field I&M work, and directives development. Link work to Tasks 6, and 8 | Info and activities will be iterative with Task 6, Task 8 activities need to include this evaluation as integral to protocol dev. process |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Lead | Participation imperative
Collaboration Numerous partnerships related to inventory and monitoring work of the agency have been initiated in the past. In the absence of national leadership and oversight, field units have often independently developed and administered inventory and monitoring partnerships at the regional and local levels. From the perspective of partners, the diversity of agreements and contact persons is a disincentive to cooperation. National partnership agreements are needed to simplify regional or local agreements, clearly describe roles and responsibilities, and enable local units to benefit from national level commitments. Partnerships need to be forged with regulatory agencies (e.g.. EPA, FWS, NMFS) to foster consistency of interpretation of laws and regulations that drive many inventory and monitoring efforts within the Forest Service.
TASK 3. Improve ability to collaborate between administrative units, with partners, and customers of inventory and monitoring programs.
3A | Establish a process for sustaining and ensuring collaboration within the agency and with partners. | Draft proposal for evaluation of MOU's was presented to IMIT August 2002 | Complete an evaluation of national and regional MOU’s and agreements. Develop standard language for MOU’s and agreements that respond to collaboration goals. |  | Participation imperative |  | Lead |  |  |  | Participate |  |  |  |  | Proposal drafted in 2002
|  |  | With partners, identify specific areas/activities that need collaboration for I&M programs, Describe what seems insolvable and what can be successful, Characteristics of successful partnerships. Establish and implement a process for periodically reviewing national and regional I&M Programs against these goals. Link work to Task 4 to communicate successful partnerships (FHM, ISEM) and continuing challenges such as Range mapping and management collaboration between NRCS, BLM, and FS), broadscale monitoring of wildlife; aquatics; etc. | Include info in activity reviews done through Task 4 | Lead |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
|  |  | Establish and maintain the resource program managers group as a cross-deputy group. Broaden view of what constitute barriers to collaboration beyond IRM/Info Mgt technologies. Address barrier hunting/busting in terms of other barriers such as quality control, program management policies, legislation/regulation, and culture/comfort with collaboration. |  |  |  | Lead |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative
3B | Barriers to data exchange | RIC's in support of IREMCG are calling for increased attention to resolve shared data issues among the national applications (between federal groups and with in FS). | Share outcomes from IRM, GEB/GAC, and e-gov pilots | Relies in part on objectives and info from Task 4C. Some success from Task 5A may be required. | Participation imperative |  | Participation imperative |  |  |  | Participation imperative | Participation imperative | Lead | Ongoing
3C | Establish methods for negotiating/funding stewardship of shared data | NRIS module developers are incorporating links to external data sources such as NHD, PLANTS database. Stewards have been identified for most national data repositories. | Evaluate problems being encountered in Regions and WO staffs | [7 empty] | Participation imperative | Participation imperative | Lead |  |  | Scheduled for 2002, not started
Accountability and Communication Three major areas of concern are (1) our ability to communicate the purpose of and findings from inventory and monitoring activities in ways that demonstrate relevance to public interests and concerns, (2) the access and use of data gathered through inventories, and (3) the scientific credibility, management, and accountability for inventory and monitoring programs, including quality assurance and quality control. The Forest Service needs to improve the communication and accountability throughout all inventory and monitoring programs.
TASK 4. Clearly articulate the purpose, scope, operations, uses, and findings of inventory and monitoring programs.
4A | Communication Strategy | Draft strategy completed for I&M in general and Wilderness monitoring protocol development | Finalize the FS I&M program communications strategy. Formulate agency-wide strategy for collaborative or coordinated delivery of I&M program information across deputy areas. |  |  | Participation imperative | Lead | Participate | Participate | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Ongoing
Implement communication strategy through partnership across deputy area programs (such as FIA, FHM, FIRE, etc)
4B | Training Program | FS NR Applications (NRIS, INFRA, ALP) provides training for database use | Review draft protocols for training needs, Compile list of existing I&M training programs across WO program managers, Compile list of I&M related training being provided within Regions, FHM and FIA. | Include systems info from Task 2A |  |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  |  | Scheduled for 2002, not started
|  | Protocol testing process includes some training components for protocol implementation. Some resource areas provide training but the existing training is not linked to I&M Framework or new protocols. | Develop field operations training sessions that are specific to implementation of national protocols (lead shifts according to protocol specialty focus and lead resource program maintaining protocol and oversight for quality assurance of data and information resulting from protocol use). Linked to Task 8. | Include systems info from Task 2A and ensure training reflects Task 8 standards and Task 8 protocol dev includessystems information needed for training programs |  |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Lead | Participation imperative
|  | Have draft t outline of monitoring training for LRMP monitoring at general information level for managers | Develop a training program to increase understanding and core competencies related to inventory and monitoring design, quality management, data analysis, reporting, and information sharing (needs to complement not duplicate training expressed in systems 2A tasks and 8C protocol tasks). Develop program with comprehensive view of related training programs, not isolated training development and implementation. | Tasks 2A and 8C |  |  | Participation imperative | Lead, is this w/I mission? How to transition to long term? Relationship with HR training. | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
4C | Support concept of having knowledge bases that contain and provide field with access to generally accepted methods, technical know-how, experiences/applications) |  | Provide place to hold and serve series of technical papers addressing important topics such as statistical design and sampling methods, protocol selection, quality assurance practices, certification, technology applications, and analysis method. Build on proof-of-concept example from economist community of practice knowledge-system, R&D knowledge-system, etc. Link to 3B in terms of techno barriers. | Feed agency needs from this task to Task 3B | Participation imperative |  | Participation imperative | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  |  | Scheduled for 2002, not started
TASK 5. Improve information and the ease of access to inventory and monitoring data and information about our programs
5A | Info System Delivery designs/methods |  | Evaluate ongoing pilot and test projects related to information and data delivery using the worldwide web. Formulate a strategy for agency and public access that provides a one-stop clearinghouse or portal to access FS I&M data, protocols, and information (including resource maps). |  |  |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Lead | Ongoing
|  |  | Implement actions to remove identified technology barriers to the exchange of data and information between Forest Service units and principle partners via respective Chief Information Officers. Link work with Task 3B. | Successes from this task may be required to support Task 3B |  |  | Lead | [5 empty] | Support
|  | Development of enterprise models, implementation and e-gov initiatives -- there has been ongoing e-gov participation, there has been NHD delivery is in progress to all regions. Formation of E-Gov clearing house has been started at GSTC. Adaptive Mgt portal test expected for completion in FY 2003. | Identify and prioritize the types of information that should be better coordinated for accessibility and limitations or constraints on access (e.g.. NRIS, Research Natural Areas, raw data, summary data), describe relationship between improving agency information access and other federal activities such as Government Locator Service, EPA EMAP data directories, e-Gov, OMB data quality guidelines, etc. Continue to participate with IRM staff in development of Enterprise Architecture models and their implementation. |  |  |  | Participation imperative | Participation imperative |  |  |  |  | Lead
5B | Establish and maintain an information delivery methodology based upon the review of pilot and test projects. | GSTC and RSAC have presented proposed approach to GAC and have scheduled presentations to Chief in order to communicate resources needed to support delivery of geospatial data in cohesive and consistent manner to the public and partners. | Communicate findings and recommendations from pilot projects throughout agency. Explain linkages to e-Gov projects and formulate strategy for long-term support. Address NRIS, INFRA data and R&D information that is not geospatial (e.g. documented protocol methods, sampling bases for data acquired. Research findings, Research natural area study results) |  |  |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  | Participation imperative | Lead |  |  | Initiated through GEB/GAC work.
TASK 6. Strengthen scientific credibility, management, and accountability of inventory and monitoring programs.
6A | Performance measures and accountability | IMPP's and BFES models provide foundation for comparison with other organizations. | Prepare proposal describing benefits and process for conducting this comparison in context of GPRA, e-Gov, and other current initiatives, use IMIT as sounding board for proposal and resulting recommendations. Use information to improve Information Products Portrait (Task 6D) and Streamline reporting requirements (Task 6E). | Requires draft info from 6D and 6E | Participation imperative |  | Lead | Participation imperative | Participation imperative | Participation imperative |  |  |  | No proposal drafted |  | Limited progress for Wilderness Character monitoring
|  |  | Prepare national IMPP |  |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
6B | Activity Reviews | FAT’s conducted in all regions except R3. |  |  |  |  | Participation imperative |  | Participate | Participate | Lead |  |  | Assistance trips to R5, R6 | Assistance trip to R1 completed | Assistance trip to R2 completed | Assistance trip to R3 cancelled
|  |  | Continue NFS, SPF, and R&D activity reviews (incorporate I&M into existing reviews). |  |  |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
|  |  | Propose method to conduct cross-deputy program reviews based on similar approach applied in EPA, ARS, DoE program review models. Propose method and expose proposal to review, conduct proof-of-concept demonstration, and gain FS commitment to implement. |  |  | Lead |  | IMI could facilitate, is it w/within mission?
6D | Continue to refine annual Performance measures | Drafted table summarizing information products by spatial scale | Complete the “FS Information Products Portrait” to provide line officers and program managers a framework to refine annual performance measures. | Could benefit from implementation and completion of 6A |  |  | Lead | [6 empty] | Ongoing
|  | IMPP developed. | Review Regional Inventory and Monitoring Program Plans and Regional BFES submissions. |  |  |  | Lead
6E | Streamline reporting requirements | Substituting IMPP's for many prior reporting requirements, coordinating reporting across resource staffs through IMPP reporting. | Discontinue use of MAR items for FY03 once Regional Program Plans have been completed (aka – streamlining reporting requirements). | Could benefit from implementation and completion of 6A | [6 empty] | Lead |  |  | Ongoing
|  |  | Refine IMPP reporting and improve in FY 03 and beyond |  |  |  | Lead |  |  |  | Participation imperative | Participation imperative
6F | Revise FSM/FSH (1940 and 1970, and other parts of the manual) | Combined direction for resource inventory into FSM 1940 and designed new approach to linking stable manual and handbook guidance with more dynamic technical guide series | Issue FSM 1940 and FSH 1090.xx and approved I&M Technical Guides. Transition publication of technical guide series from RIG to other appropriate staff units and establish clearinghouse for I&M information and guidance. |  |  |  | Lead | Participation imperative |  |  | Participation imperative |  | Participation imperative | Ongoing
|  |  | Evaluate changing title and scope of 1940 to encompass ecologic, social, and economic systems for inventory and monitoring directives. |  |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
|  |  | Convene cross-deputy and interagency panel of quality control and assurance experts to evaluate challenges facing QA/QC in I&M programs and recommend actions. Learn from existing comprehensive quality management programs. |  | Participation imperative |  | Participation imperative | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative
6G | Identify advisory and assistance services |  | Identify critical advisory and assistance services Regions need to meet regional and field challenges. Review services needed with Directors of national and regional service and enterprise units (i.e. Stream Team, R&D, RSAC, MDTC, FMSC, FIA, IMI, GSTC, FHTET, etc.) to communicate priorities, evaluate capacity of units to provide assistance and support. Link work to Task 2, especially with regard to knowledge sharing/management, and clearinghouse functions and approaches. | Include info and needs identified through Task 2 | Lead |  | Participation imperative |  |  |  | Participation imperative | Participation imperative |  | Scheduled 2001, not started except possibly through WO detached unit review
|  |  | Create knowledge base or directory of sources of advice and assistance to Field offices. Hold directors of staffs providing assistance accountable for clearly describing and promoting the services they have for field offices, include performance measures linked to effectiveness of their communications with field offices. Link work to Task 2, especially with regard to knowledge sharing/management, and clearinghouse functions and approaches. | Include info and needs identified through Task 2
Organization Structure and Roles The distributed authority and responsibility for inventory programs throughout the Forest Service provides opportunities for individual program areas and offices to devise unique organizational structures, policies, and operations. Coordination across inventory and monitoring programs is usually limited to collaboration required by high-profile bioregional assessments. Relatively few positions within Regional Offices are designated to manage comprehensive (multi-resource) inventory and monitoring programs. This impedes funding and management of cross-program “systems-based” inventory and monitoring activities. Inventory and monitoring policy is dispersed and promulgated by independent staffs through informal and formal channels.
TASK 7. Clearly define the organizational structure and associated responsibilities for national and regional inventory and monitoring activities.
7A | Define organizational roles/responsibilities | Drafted FSM/FSH | Finalize FSM and FSH direction. Create strong link between Regional Resource Information Coordinators and Regional Program Managers. Establish performance measures for national and regional RICs and RPM’s to sustain dialog about work activities, business needs, and I&M strategies across deputy areas |  |  |  | Lead |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  | For WO, completed | For RO and others Ongoing through Regional I&M strategic planning
|  |  | Evaluate org structure and operations for efficiencies and effectiveness of I&M. (concern for litigation, competitive sourcing, integration vs. keeping arms length, integration across resource programs, accidents of history). Affect of structure on funding allocation (i.e. HD, equity of funding etc) |  |  | Strong stake/responsibility for this | Lead | Possible objective evaluator/facilitate. But is it w/I mission? |  |  | Lead
|  | Regions Info Coordinators and Stewards have been designated | Maintain lists of coordinators, include contacts (coordinators and data stewards as examples) in I&M clearing house information set (link to KB and clearing house) |  |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative
7B | Charter Resource program managers group to set priorities for protocol development and fiscal investments or other national I&M priorities | link to collaboration task 3B | Implement Charter for Resource program managers group to set priorities for protocol development and fiscal investments or other national I&M priorities, include method for periodic review of effectiveness of group. |  |  |  | Lead |  |  |  | Participation imperative
|  | We currently negotiate performance standards with Regions and evaluate effectiveness of structure and responsibilities through activity reviews. | Evaluate how well NFS representation with FHM and FIA Mgt teams is working to sustain coordination of funding, data collection, data sharing, and protocol development. Link to 3B, addressing org structures and performance measures. |  |  |  | Lead |  | Participation imperative | Participation imperative | Participation imperative | Participation imperative
7C | Designate R0 Staff Director responsible for IM | Regions, Stations, and Area have designated a contact at the Staff Director level or higher to provide leadership and program management responsibility for I&M programs, including budget allocation, and improving communication and collaboration. | [11 empty] | Completed
Protocols Sampling, data collection, and analysis methodologies or protocols used by inventory and monitoring programs are typically not consistent within and between administrative units. Some programs -- such as soils inventories -- are consistent because they are required to follow NRCS standards, and memoranda of understanding are in place at the national, State, and survey level to ensure consistency. However, even highly standardized inventory and monitoring activities are not consistently applied, making data exchange and aggregation difficult. Scientific credibility of data and results are being compromised when sampling, collection and analysis protocols are interpreted and adapted without rigorous review.
TASK 8. Ensure scientifically credible sampling, data collection, and analysis protocols are used in all inventory and monitoring activities.
8A | Catalog existing protocols (sampling, collection techniques, quality control and analysis methods, and tools) being used at multiple scales (link to 4B and 2B) | Review IMPP for lists of protocols in use and needed | Complete evaluation of ‘existing’ Field Guides and publications for inclusion in the I&M Technical Guide series and the knowledgebase. | Need to develop training (task 4B) based on info from tech guides (task 8A) |  |  | Participation imperative | Lead | [5 empty] | Scheduled for 2001
|  |  | Review IMPP status information for lists of protocols in use and clue us in on protocol needs (many local protocols may indicate need for national protocol) | Glean feedback from training provided through Task 4B to identify protocol needs/refinements |  |  | Lead |  |  |  | Participation imperative
8B | Identify gaps in protocols that need to be filled. Establish methods to determine priorities for national investments in protocol development | IREMCG/ESCT identified initial set of priority protocols with concurrence from WO program managers and Regions, TEUI, AEUI, high priority species population monitoring, and soc/econ analysis protocols | Develop a well-described and clear process for identifying currently used protocols and gaps in data collection and analysis needs. Include approach to incorporate “systems thinking” into protocol identification and development. Establish ongoing process for identifying protocol needs. | Ensure Training (Task 4B) reflects priority protocols |  |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  |  |  | Ongoing
|  |  | Identify priorities for protocol development thru national IMPP for managing funds/support for development see task 6. | Fund and implement training (Task 4B) to support use of protocols develeped |  |  | Lead
8C | Refine and implement the protocols | Continuous development process with FHM Mgt team and FIA Mgt team, NFS: RIG staff coordinating development of protocols, RIG staff drafting processes for development, testing, and publishing | Establish process for ensuring best science and QA/QC are incorporated appropriately in protocols. . | Include process as component of Training (4B) program |  |  | Lead | Participation imperative | [5 empty] | Protocols under development: TEUI, AEUI, Moonworts, Goshawk, Multi-species sampling, Social Issues identification --- ONGOING
|  |  | Continue current protocol development efforts and carefully capture level of resources and methods used to develop protocols (collaboration, science reviews, testing, field evaluation, analysis, etc). | Ensure protocol development includes Training course development and info to support training courses |  |  | Lead | Participation imperative
|  |  | Complete the publication of protocols developed. Determine and implement best approach to disseminating protocols and technical guides -- see 4B. | Include products as component of Training (4B) program |  |  | Lead | Participation imperative | Participation imperative | Participation imperative
8D | Develop, evaluate, and transfer technologies that improve the quality and efficiency of inventory and monitoring programs throughout the Forest Service. | Continuous development process with FHM Mgt team and FIA Mgt team IMI sustaining Technology Development Program with ENG and RIG, Remote Sensing Committee sponsoring development projects and limited technology transfer activities, GEB /GAC monitoring GIS tech transfer effectiveness | Continue to support the efforts of the IMIT, GEB/GAC, SDIT, and other teams to work in concert on technology development, QA/QC, and transfer. | Take advantage of existing units to support field operations training (Task 4B) |  | Lead | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative | Participation imperative |  | Ongoing
8E | Agreement on Data Standards | FGDC subcommittee meetings are continuing to result in the establishment of data standards. NBII meetings are leading to the establishment of standards for biological data elements. Most FS representation led through R&D. Additionally data standards are being negotiated and established through protocol dev efforts. | Ensure continued representation from FS programs in federal committees. | Include info on data standards and agreements in Training, Task 4B |  |  | Lead |  |  | Participation imperative | Participation imperative |  |  | Ongoing
Note on M4: FSDefaultUser: Includes RIC, IM coordinators, FHM prog mgr, FIA project ldrs
Note on D28: FSDefaultUser: Could this be specific new team chartered? Or IMIT subteam?