## Assets
ASSETS | [8 empty] | as at 7 April 2003
ASS/1 |  | ACTIVITY: Improve collections stewardship
Output: Percentage of collection in acceptable environmental conditions
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 24% | 24% |  |  |  |  | Output level currently under review
|  | 2002-'03 | 36% | ?
ASS/1 |  | 2003-'04 | 36% |  |  |  |  | ML
2004-'05
2005-'06
Quality standard: British Standard BS5454.2000
Outcome: Collection preserved for future generations
Headline risk(s): (see Risk Register for further details)
Lease on current stores
Damage to existing collection
ASS/2 |  | ACTIVITY: Improve collections stewardship
Output: Number of items assessed and conserved
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
ASS/2 |  | 2003-'04 | [5 empty] | ML | This measure a combination of previous measures: number of items assessed for condition and items conserved
2004-'05
2005-'06
Quality standard: Benchmark against other organisation
Outcome: Better collections care management
Headline risk(s): (see Risk Register for further details)
Resources not available to increase number of items assessed
Potential move of conservation staff and facilities
Damage to existing collections
Other work prevents meeting deadlines
Dependant upon requests for displays and loans
ASS/3 |  | ACTIVITY: Improve collections stewardship
Output: Conservation and display of Baltic stained glass
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ASS/3 |  | 2003-'04 | by March 2004 |  |  |  |  | ML
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
ASS/4 |  | ACTIVITY: Increase numbers of electronic assets
Output: Number of digitized images
Also in DCMS Funding Agreement (Supports Objective III, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 2000
|  | 2002-'03 | + 2,500
ASS/4 |  | 2003-'04 | + 2,000 |  |  |  |  | ML
|  | 2004-'05 | + 2,000
2005-'06
Quality standard: Zero faults on digitization
Outcome: Increasing value of resources
Headline risk(s): (see Risk Register for further details)
Equipment failure
Poor co-ordination with Art & Object Handling
Failure to retain staff responsible for tagging images to collections records
ASS/5 |  | ACTIVITY: Enhance collections management
Output: Number of site inventories completed
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | Kidbrooke | 1 |  |  |  |  | Target outlines general progression of the Inventory Project but work is being undertaken outside of the sequence of sites as necessary.
ASS/5 |  | 2003-'04 | LTE |  |  |  |  | ML
|  | 2004-'05 | B.F.
2005-'06
Quality standard: (see PID)
Outcome: Full inventory of collections
Headline risk(s): (see Risk Register for further details)
Loss of key staff
Failure of electronic cataloguing systems
ASS/6 |  | ACTIVITY: Enhance collections management efficiencies
Output: Rationalised storage
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | No Wevco | [5 empty] | Storage options appraisal. Plan for rationalising collections in Kidbrooke
ASS/6 |  | 2003-'04 | Plans (see notes) |  |  |  |  | RC/ML
2004-'05
2005-'06
Quality standard: Collections rehoused without compromising conditions
Outcome: Storage costs rationalised
Headline risk(s): (see Risk Register for further details)
Failure to locate suitable alternative storage
Costs
ASS/7 |  | ACTIVITY: Ensure a sharing of expertise
Output: Numbers of research papers given based on work in progress
Also in DCMS Funding Agreement (Museums Specific Target, Objective IV, Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 55 | 55
|  | 2002-'03 | 60 | 60
ASS/7 |  | 2003-'04 | 62 |  |  |  |  | ML
|  | 2004-'05 | 65
2005-'06
Quality standard: Synergy with major research subjects (e.g. CLIWOC)
Outcome: Wider NMM research programme
Headline risk(s): (see Risk Register for further details)
Loss of key personnel
No call for papers
ASS/8 |  | ACTIVITY: Increase available expertise
Output: Percentage of staff experiencing vocational training
Also in DCMS Funding Agreement (Museum Specific Target, Objective III, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 12% | 12%
|  | 2002-'03 | 15% | 15%
ASS/8 |  | 2003-'04 | 18% |  |  |  |  | EB
|  | 2004-'05 | 21%
2005-'06
Quality standard: Continuation of IIP status and achievement of VQ's
Outcome: More competent , knowledgeable and skilled staff
Headline risk(s): (see Risk Register for further details)
Lack of investment
Ineffective management
ASS/9 |  | ACTIVITY: Enhance people (asset) management
Output: Achieve IIP and implement findings of assessment
Also in DCMS Funding Agreement (Supports Objective IV, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | IIP status |  | IIP status
|  | 2002-'03 | Implement | Implement
ASS/9 |  | 2003-'04 | Re-accredit |  |  |  |  | AB
|  | 2004-'05 | Implement
2005-'06
Quality standard: Maintenance of external accreditation
Outcome: Assurance development investment continuously meets organisational needs
Headline risk(s): (see Risk Register for further details)
Implementation of IIP findings overlooked in favour of other work requirements
ASS/10 |  | ACTIVITY: Enhance estate (asset) management
Output: Spend on PPM against budget
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 300000 | 300000 |  |  |  |  | N.B. DCMS funds for South Building N.B. DCMS funds for South Building
|  | 2002-'03 | 291500 | £1.208m
ASS/10 |  | 2003-'04 | Budget t.b.a. |  |  |  |  | JH
2004-'05
2005-'06
Quality standard: Number of items on PPM register completed to forecast timetable
Outcome: Buildings preserved and improved
Headline risk(s): (see Risk Register for further details)
Individual contracts cost rise above estimates
ASS/11 |  | ACTIVITY: Undertake digital preservation
Output: Digital preservation strategy
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
Ass/11 |  | 2003-'04 | System & Policy |  |  |  |  | JH | Source and implement digital asset management system. Develop policy and procedures. (links with EDRM - below)
2004-'05
2005-'06
Quality Standard: Implemented to government timeframe
Outcome: Electronic access to information
Headline Risk(s): (see Risk Register for further details)
?
ASS/12 |  | ACTIVITY: Comply with Gov't target for E.D.R.M.
Output: Implement Electronic Digital Records Management system and culture
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | Policy & Inventory | [5 empty] | Policy, inventory appraisals, systems appraisals Follow EDRM routemap towards implementation, source system, identify staff resources required.
ASS/12 |  | 2003-'04 | Go live 1.1.04 |  |  |  |  | JH
2004-'05
2005-'06
Quality Standard: Implemented to government timeframe
Outcome: Electronic access to information
Headline Risk(s): (see Risk Register for further details)
Meeting the implementation deadline - project running some 2 years behind
Policy is subject to EB agreement

## Organisation
ORGANISATION | [8 empty] | as at 7 April 2003
ORG/1 |  | ACTIVITY: Greater efficiency and effectiveness
Key Ratio: GIA/total users (visitor, web, enquirer) numbers
Also in DCMS Funding Agreement (Core Target, Efficiency and Effectiveness Measures)
Risk Ref. | Status | Year | Forecast total | Forecast total | Forecast to date | Actual to date |  | Resp. | Notes
|  | 2001-'02 | 5.49 | 5.49 |  |  |  |  | Dependent on forecast grant/visits, web visits and enquirers (figures amended 14 Mar 03)
|  | 2002-'03 | 4.6127 | 5.08
ORG/1 |  | 2003-'04 | 4.6099 |  |  |  |  | EB
|  | 2004-'05 | 4.6854
|  | 2005-'06 | 4.4624
Outcome: Maximising efficiency and use of resources available
Headline risk(s): (see Risk Register for further details)
Major risk affecting any of user groups (see individual activity risks)
ORG/2 |  | ACTIVITY: Greater efficiency and effectiveness
Output: Reduction in average numbers of days lost per employee through short term sickness
Also in DCMS Funding Agreement (Museum Specific Target, Efficiency and Effectiveness Measures)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 6.5 | 6.5 |  |  |  |  | Changed from Core to Museum Specific Target in 2002
|  | 2002-'03 | 6.25 | 6.25
ORG/2 |  | 2003-'04 | 6 |  |  |  |  | EB
|  | 2004-'05 | 5.75
2005-'06
Quality standard: Monitor position of long-term sick
Outcome: Greater efficiency and effectiveness
Headline risk(s): (see Risk Register for further details)
Ineffective management
Epidemics
ORG/3 |  | ACTIVITY: Greater efficiency and effectiveness
Output: Improved efficiency in security costs
Also in DCMS Funding Agreement (Supporting Objective I, Strategic Purpose 2 and Effic. & Effec.)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | - 8% | - 8%
ORG/3 |  | 2003-'04 | - 4% |  |  |  |  | JH
2004-'05
2005-'06
Quality standard: Zero breaches of security
Outcome: Secure and safe environment
Headline risk(s): (see Risk Register for further details)
Unforeseen costs
ORG/4 |  | ACTIVITY: Greater efficiency and effectiveness
Output: Percentage of energy saved through efficiencies
Also in DCMS Funding Agreement (Supporting Objective I, Strategic Purpose 2 and Effic. & Effec.)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 10% | [5 empty] | NMM target in alignment with overall government target to reduce energy consumption by 20% based upon the energy consumption for 1990, the target date for achieving this is 2010.
|  | 2002-'03 | 5%
ORG/4 |  | 2003-'04 | 4% |  |  |  |  | JH
2004-'05
2005-'06
Quality standard: Successful renewal of energy award in 3 years
Outcome: Consumption reduced
Headline risk(s): (see Risk Register for further details)
Extra equipment of high consumption introduced
ORG/5 |  | ACTIVITY: Greater efficiency and effectiveness
Output: % reduction in external print costs through inhouse printing
Also in DCMS Funding Agreement (Supporting Objective I, Strategic Purpose 2 and Efficiency & Effectiveness)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 15%
ORG/5 |  | 2003-'04 | 13% |  |  |  |  | JH
2004-'05
2005-'06
Quality standard: Paper costs not to rise above x%
Outcome: Expenditure on equipment leads to cost savings
Headline risk(s): (see Risk Register for further details)
Breakdown of key items of machinery
ORG/6 |  | ACTIVITY: Greater efficiency and effectiveness
Output: Staff hours saved through implementation of one-stop help desk in OFMG
Also in DCMS Funding Agreement (Supporting Objective I, Strategic Purpose 2 and Efficiency & Effectiveness)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ORG/6 |  | 2003-'04 | Implement |  |  |  |  | JH | Improve quality of service through implementation of one-stop shop helpdesk
2004-'05
2005-'06
Quality standard: Benchmark against other help-desks
Outcome: Improve customer response, improve fault management; tracking and resolution
Headline risk(s): (see Risk Register for further details)
System fails
Failure of stakeholders to use system
ORG/7 |  | ACTIVITY: Increase NMME income generation
Output: Average value of transaction
Also in DCMS Funding Agreement (Museum Specific Target, Objective I, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 8.52 | [5 empty] | Replaces % increase in spend per head in Funding Agreement
|  | 2002-'03 | 8
ORG/7 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: ?
Outcome: Efficient use of retail space and resources
Headline risk(s): (see Risk Register for further details)
?
ORG/8 |  | ACTIVITY: Increase NMME income generation
Output: Conversion of site visitors into retail purchasers
Also in DCMS Funding Agreement (Museum Specific Target, Objective I, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 13% | [5 empty] | Replaces % increase in spend per head in Funding Agreement
|  | 2002-'03 | 13%
ORG/8 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: % increase in visitors using shop as measure by MORI
Outcome: Income for NMM
Headline risk(s): (see Risk Register for further details)
Location and size of shops not assisting conversion
ORG/9 |  | ACTIVITY: Increase NMME income generation
Output: Gross Profit percentage
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 58%
ORG/9 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: ?
Outcome: ?
Headline risk(s): (see Risk Register for further details)
?
ORG/10 |  | ACTIVITY: Increase NMME income generation
Output: Gross profit
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 876000 | [5 empty] | sum of NMME income activities
ORG/10a |  | 2003-'04 | 0 |  |  |  |  | CWa
2004-'05
2005-'06
Output: Gross profit in Neptune Court Shop
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 303000
ORG/10b |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Output: Gross profit in ROG Shop
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 342000
ORG/10c |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Output: Gross profit from Trade/Mail order/Internet sales
Also in DCMS Funding Agreement (Supporting Objective I, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 46000
ORG/10d |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Output: Gross profit from Corporate and Private Lettings
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2002-'03 | 175000
ORG/10e |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Output: Gross profit Regatta Café and Upper Deck Coffee Bar
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | 6000
|  | 2002-'03 | 10000
ORG/10f |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: Satisfied customers as indicated by MORI research
Outcome: Income for NMM
Headline risk(s): (see Risk Register for further details)
Overcrowding in shops
Retail products not attractive
Space restrictions for packaging trade mail order/internet order goods
Catering prices unreasonable
ORG/11 |  | ACTIVITY: Increase NMME income generation
Output: Net profit of total corporate loans and membership
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 173000
|  | 2002-'03 | 144000
ORG/11 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: Members and Loan agreements renewing
Outcome: Income for Museum and increased profile amongst stakeholders
Headline risk(s): (see Risk Register for further details)
Damage to object on loan
Loss of key personnel
Restriction on loan items available
ORG/12 |  | ACTIVITY: Increase income generation
Output: Value of annual interest
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 150000 | [5 empty] | 2003-'04 budget includes a reduction in reserves of over £1m which equates to £50k of lost interest per annum. Additionally interest rates are expected to be lower than in 2002-'03
|  | 2002-'03 | 250000
ORG/12 |  | 2003-'04 | 200000 |  |  |  |  | NR
2004-'05
2005-'06
Quality standard: Performance against average performance of market
Outcome: Good governance
Headline risk(s): (see Risk Register for further details)
Economic downturn
ORG/13 |  | ACTIVITY: Increase income generation
Output: Amount of (visitor and non-visitor) sponsorship and donations obtained
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 500000
|  | 2002-'03 | 500000
ORG/13 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality standard: % of donors giving more than once
Outcome: Income for Museums and increased reputation amongst stakeholders
Headline risk(s): (see Risk Register for further details)
Lack of project definition
World recession or change in domestic economy
ORG/14 |  | ACTIVITY: Ensure an off-setting of the costs of service and supply
Output: Engendered income from Research & Collections group activities
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 408237
|  | 2002-'03 | 443220
ORG/14 |  | 2003-'04 | Budget t.b.a. |  |  |  |  | ML
2004-'05
2005-'06
Quality standard: Satisfied customers as measure by refunds/complaints
Outcome: Offsetting costs of core activities
Headline risk(s): (see Risk Register for further details)
Failure to replace key staff
Further downturn in market
ORG/15 |  | ACTIVITY: Practise good governance
Output: Performance Management report communicated
Also in DCMS Funding Agreement (Supporting Efficiency & Effectiveness)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 12 | [5 empty] | With continuous improvements to be made in conjunction with EB requests
|  | 2002-'03 | 12
ORG/15 |  | 2003-'04 | 12 |  |  |  |  | RC
|  | 2004-'05 | 12
2005-'06
Outcome: Good and timely management information
Headline risk(s): (see Risk Register for further details)
Governance failure
ORG/16 |  | ACTIVITY: Practise good governance
Output: Risk management procedures in place
Also in DCMS Funding Agreement (Supporting Efficiency & Effectiveness)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | by March 2003
ORG/16 |  | 2003-'04 | Implement |  |  |  |  | NR
2004-'05
2005-'06
Quality standard: Externally audited?
Outcome: All risks for operation of Museum assessed
Headline risk(s): (see Risk Register for further details)
Failure to meet deadline
ORG/17 |  | ACTIVITY: Practise good financial management
Output: Limited value of bad debts
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 40000
ORG/17 |  | 2003-'04 | 20000 |  |  |  |  | NR
2004-'05
2005-'06
Quality standard: Low accounts charge to bad debts written off
Outcome: Satisfactory revenue management
Headline risk(s): (see Risk Register for further details)
One large bad debt can distort outcome
Revenue generation initiatives can increase bad debt risk
ORG/18 |  | ACTIVITY: Greater knowledge of the collections and subject
Output: Publish and implement a research strategy
Also in DCMS Funding Agreement (Supports Objective IV, Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ORG/18 |  | 2003-'04 | Publish strategy |  |  |  |  | ML
|  | 2004-'05 | Implementation
2005-'06
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
?
ORG/19 |  | ACTIVITY: Improve planning
Output: Planet Ocean programme developed
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | announced
ORG/19 |  | 2003-'04 | [5 empty] | ML
2004-'05
2005-'06
Quality standard: ?
Outcome: ?
Headline risk(s): (see Risk Register for further details)
?
ORG/20 |  | ACTIVITY: Improve planning
Output: Prepare draft programme for Trafalgar 200 festival
Also in DCMS Funding Agreement (Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ORG/20 |  | 2003-'04 | by Dec. 2003 |  |  |  |  | CWh | In conjunction with work on 'Year of the Sea'
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
ORG/21 |  | ACTIVITY: Improve planning
Output: Prepare blueprint for NMM 2005 Steering Group
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ORG/21 |  | 2003-'04 | by Aug. 2003 |  |  |  |  | CWh
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
?
ORG/22 |  | ACTIVITY: Improve planning
Output: Formulate plan for 2005 Year of the Sea
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ORG/22 |  | 2003-'04 | by March 2004 |  |  |  |  | SR
2004-'05
2005-'06
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
?

## Access
ACCESS | [8 empty] | as at 7 April 2003
ACC/1 |  | ACTIVITY: Increase onsite access
Output: Total number of visits
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 805000
|  | 2002-'03 | 930000
ACC/1a |  | 2003-'04 | 1000000 |  |  |  |  | EB
|  | 2004-'05 | 960000
|  | 2005-'06 | 1050000
Output: NMM Visits
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 330000 | [5 empty] | 47% of total visits during 2003-'04 due to conversion of Elizabeth visits
|  | 2002-'03 | 365406
ACC/1b |  | 2003-'04 | 470000 |  |  |  |  | EB
|  | 2004-'05 | 355200
|  | 2005-'06 | 388500
Output: ROG Visits
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 400000 | [5 empty] | 47% of total visits. Programme for flexible opening hours and gallery refurbishments/displays in place
|  | 2002-'03 | 473571
ACC/1c |  | 2003-'04 | 470000 |  |  |  |  | EB
|  | 2004-'05 | 547200
|  | 2005-'06 | 598500
Output: QH Visits
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 75000 | [5 empty] | 6% of total visits
|  | 2002-'03 | 91023
ACC/1d |  | 2003-'04 | 60000 |  |  |  |  | EB
|  | 2004-'05 | 57600
|  | 2005-'06 | 63000
Output: C2DE Visits
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/1d |  | 2003-'04 | 175000 |  |  |  |  | EB
|  | 2004-'05 | 173000
|  | 2005-'06 | 189000
Quality standard: 96% of visitors whose visit is 'at least satisfactory'
Outcome: Larger audience visiting
Headline risk(s): (see Risk Register for further details)
Failure of TOR system software
Costs growing more than revenues
ACC/2 |  | ACTIVITY: Increase onsite access
Output: Total child visits
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 2)
Risk Ref. | Status | Year | Target total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 258000 | [5 empty] | Forecast calculated as 32% of total visits (see Acc/1)
|  | 2002-'03 | 298000
ACC/2 |  | 2003-'04 | 275000 |  |  |  |  | EB
|  | 2004-'05 | 285000
|  | 2005-'06 | 300000
Quality standard: What % of children think their visit is 'at least satisfactory'
Outcome: Reaching visitors of tomorrow
Headline risk(s): (see Risk Register for further details)
Failure of TOR systems software
Displays fail to match needs of younger visitors
ACC/3 |  | ACTIVITY: Increase onsite access
Output: Total over 60s visits
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 120000 | [5 empty] | Forecast calculated as 15% of total visits (see Acc/1) using MORI data
|  | 2002-'03 | 140000
ACC/3 |  | 2003-'04 | 146000 |  |  |  |  | EB
2004-'05
2005-'06
Quality standard: What % of over 60s think their visit is 'at least satisfactory'
Outcome: Diverse audience
Headline risk(s): (see Risk Register for further details)
Failure of TOR systems software
ACC/4 |  | ACTIVITY: Increase onsite access
Output: Number of hours of public opening per annum over baseline
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 92 hours | [5 empty] | Forecast includes later summer opening, altered hours for London Marathon and New Year's Eve/New Year's Day
|  | 2002-'03 | 60 hours
ACC/4 |  | 2003-'04 | 60 hours |  |  |  |  | EB
2004-'05
2005-'06
Quality standard: ensure opening hours complement visitor entrance times
Outcome: Enhanced visitor experience
Headline risk(s): (see Risk Register for further details)
Benefits don't outweigh costs
Presently passing trade non-existent in Greenwich after 6pm
ACC/5 |  | ACTIVITY: Increase onsite access
Output: Number of new/temporary exhibitions and redeveloped galleries
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
| 2001-'02 | 2001-'02 | 9
ACC/5a | 2002-'03 | 2002-'03 | O. of Disc |  |  |  | 1/m | DS
Bridge
ROG
QH
Court Gall.
| 2003-'04 | 2003-'04 | Elizabeth
Eliz. Discovery
Bridge
NACF
Future of the Sea
Images of S/power
James Dodds
|  | 2004-'05 | Tin Tin
ROG Great E'torial
| 2004-'05 |  | Hodges
|  | 2005-'06 | Traf. 200
Output: Future of the Sea/Planet Ocean programme continued
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | Enhance display | [5 empty] | Oceans of Discovery, Beach Litter, Argo float completed Action plan to include wave tank developments, removal of cube from upper court, assessment of wind-turbine feasibility and development of new project aims
ACC/5b |  | 2003-'04 | Action plan |  |  |  |  | KL
2004-'05
2005-'06
Outcome: High public and professional perception
Headline risk(s): (see Risk Register for further details)
Failure to meet deadline
ACC/6 |  | ACTIVITY: Increase onsite access
Output: Number of incremental visits to special exhibitions
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 50000 | [5 empty] | South Oceans of Discovery Elizabeth
|  | 2002-'03 | 10000
ACC/6 |  | 2003-'04 | 100000 |  |  |  |  | DS
2004-'05
2005-'06
Quality standard: 96% visitor satisfaction
Outcome: Increasing visitor base/income for NMM
Headline risk(s): (see Risk Register for further details)
Exhibition topics do not generate sufficient interest to achieve number
ACC/7 |  | ACTIVITY: Increase onsite access
Output: Improve access from north side of site via Devonport House gate
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/7 |  | 2003-'04 | [5 empty] | JH
2004-'05
2005-'06
Quality standard:
Outcome: Ease of access for general public
Headline risk(s): (see Risk Register for further details)
Work schedule affected by external partners
ACC/8 |  | ACTIVITY: Improve physical access around sites
Output: Operation of Road Train between NMM and ROG
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/8 |  | 2003-'04 | by Summer 2003 |  |  |  |  | RC
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
?
ACC/9 |  | ACTIVITY: Increase offsite access
Output: Number of UK loan venues
Also in DCMS Funding Agreement (Core Target, Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 60 | [5 empty] | Includes travelling exhibitions to UK venues
|  | 2002-'03 | 80
ACC/9a |  | 2003-'04 | 62 |  |  |  |  | ML
|  | 2004-'05 | 73
|  | 2005-'06 | 84
Output: Number of loans to venues in England
Also in DCMS Funding Agreement (Core Target, Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/9a |  | 2003-'04 | 60 |  |  |  |  | ML
|  | 2004-'05 | 70
|  | 2005-'06 | 80
Output: Number of loans to UKMCS venues (subset of UK loan venues)
Also in DCMS Funding Agreement (Museum Specific Target, Objective II, Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 10
ACC/9b |  | 2003-'04 | 11 |  |  |  |  | ML
2004-'05
2005-'06
Quality standard: % of items in the collection not on public view
Outcome: Reputation and outreach
Headline risk(s): (see Risk Register for further details)
Loan requests not forthcoming
Resourcing
ACC/10 |  | ACTIVITY: Increase offsite access
Output: Number of overseas loan venues
Also in DCMS Funding Agreement (Core Target, Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 23 | [5 empty] | Includes travelling exhibitions to overseas venues
|  | 2002-'03 | 19
ACC/10 |  | 2003-'04 | 25 |  |  |  |  | ML
2004-'05
2005-'06
Quality standard: % of items in the collection not on public view
Outcome: Reputation and outreach and promotion of NMM abroad
Headline risk(s): (see Risk Register for further details)
Loan requests not forthcoming
Resourcing
Review of long term loans may result in transfer of Collections
ACC/11 |  | ACTIVITY: Increase offsite access
Output: Increase in collection records accessible via IT/ICT from last year
Also in DCMS Funding Agreement (Core Target, Objective IV, Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 2000
|  | 2002-'03 | 5992
ACC/11 |  | 2003-'04 | 4000 |  |  |  |  | ML
2004-'05
2005-'06
Quality indicator: Reduction in number of requests for collections information
Outcome: Increased access
Headline risk(s): (see Risk Register for further details)
Staffing difficulties in studio
Retention of key staff
AOH availability
Cross-boundary working with collections management
ACC/12 |  | ACTIVITY: Increase offsite access
Output: Number of website visits (per user session)
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 1500000
|  | 2002-'03 | 2000000
ACC/12 |  | 2003-'04 | 2000000 |  |  |  |  | ML
|  | 2004-'05 | 2100000
|  | 2005-'06 | 2200000
Quality standard:
Outcome: Virtual visitors
Headline risk(s): (see Risk Register for further details)
Failure of internet hardware/software
Merging of websites will mean less website visits in total
ACC/13 |  | ACTIVITY: Increase offsite access
Output: Additional foreign language translations on website
Also in DCMS Funding Agreement (Supports Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 6 languages | [5 empty] | Bengali and Sylheti, Panjabi, Gujarati, Hindi/Urdu Welsh
|  | 2002-'03 | + 1 language
ACC/13 |  | 2003-'04 | + 1 language |  |  |  |  | ML
|  | 2004-'05 | + 1 language
2005-'06
Quality standard: Languages chosen reflects countries accessing website
Outcome: Wider access to NMM services
Headline risk(s): (see Risk Register for further details)
Cost of professional translation
ACC/14 |  | ACTIVITY: Increase offsite access
Output: New content projects for Online Learning Centre
Also in DCMS Funding Agreement (Supports Objective III, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 3 projects
ACC/14 |  | 2003-'04 | 4 projects |  |  |  |  | ML
|  | 2004-'05 | 4 projects
2005-'06
Quality standard: Number of hits on specific pages
Outcome: Positive public perception
Headline risk(s): (see Risk Register for further details)
Retention of key staff
Unreliable NMM IT systems (e.g. downtime of Internet)
ACC/15 |  | ACTIVITY: Increase offsite access
Output: Number of touring exhibitions
Also in DCMS Funding Agreement (Supports Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 1
ACC/15 |  | 2003-'04 | Skin Deep |  |  |  |  | DS
Titanic
|  | 2004-'05 | Aberdeen exh.
|  | 2005-'06 | Peabody Essex
Quality standard: % increase in collections on display
Outcome: Collection available to wider public audience
Headline risk(s): (see Risk Register for further details)
Requests for exhibitions not forthcoming
Resourcing
ACC/16 |  | ACTIVITY: Increase offsite access
Output: Ship models to Chatham
Also in DCMS Funding Agreement (Supports Objective I, Strategic Purpose 1 & Objective II Strategic Purpose 3)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | HLF 1 bid | [5 empty] | not realised end of June 2003 June 2004
ACC/16 |  | 2003-'04 | HLF 1 bid |  |  |  |  | RC
|  | 2004-'05 | HLF 2 bid
|  | 2005-'06 | works
Quality standard: HLF applications granted
Outcome: More of collections on display
Headline risk(s): (see Risk Register for further details)
Failure of applications to secure funds
ACC/17 |  | ACTIVITY: Increase offsite access
Output: Number of publications
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 63
|  | 2002-'03 | 65
ACC/17 |  | 2003-'04 | 66 |  |  |  |  | ML
|  | 2004-'05 | 68
2005-'06
Quality standard: Sales and reprinted editions
Outcome: Enhance reputation, income
Headline risk(s): (see Risk Register for further details)
Failure to place new titles
Succession planning doesn't address specialist authors
Poor exhibition affecting sales of related books
Failure to understand market
ACC/18 |  | ACTIVITY: Increase offsite access
Output: NOF Port Cities project
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | partial launch | [5 empty] | agreed enhancements
ACC/18 |  | 2003-'04 | enhancements |  |  |  |  | ML
|  | 2004-'05 | completion
Quality standard: To satisfaction of ? DfEE and sponsors
Outcome: Collections available online
Headline risk(s): (see Risk Register for further details)
Loss of key staff
ACC/19 |  | ACTIVITY: Increase offsite access
Output: Secure publisher for Nelson letters volume
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/19 |  | 2003-'04 | by Dec. 2003 |  |  |  |  | CWh
2004-'05
Quality standard:
Outcome: Wider access to maritime heritage
Headline risk(s): (see Risk Register for further details)
ACC/20 |  | ACTIVITY: Increase specialist access
Output: Numbers of international conferences
Also in DCMS Funding Agreement (Museum Specific Target, Objective I, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 3
|  | 2002-'03 | 3
ACC/20 |  | 2003-'04 | 2 |  |  |  |  | ML
|  | 2004-'05 | 3
2005-'06
Quality standard: Conferences filled to capacity
Outcome: Higher Museum profile
Headline risk(s): (see Risk Register for further details)
Conferences fail to recruit
Poor budgetary control
ACC/21 |  | ACTIVITY: Increase specialist access
Output: Total number of enquirers (specialist, collection, astronomy)
Also in DCMS Funding Agreement (Museum Specific Target, Objective II, Specific Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 30000 | [5 empty] | Number of enquiries likely to decline as more information becomes available online
|  | 2002-'03 | 27250
ACC/21a |  | 2003-'04 | 25000 |  |  |  |  | ML
|  | 2004-'05 | 20000
2005-'06
Output: Number of maritime resources and collections expertise users
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 12000
|  | 2002-'03 | 12250
ACC/21b |  | 2003-'04 | [5 empty] | ML
2004-'05
2005-'06
Output: Number of specialist enquiries
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 13000
|  | 2002-'03 | 10000
ACC/21c |  | 2003-'04 | [5 empty] | ML
2004-'05
2005-'06
Output: Number of PPARC astronomy enquiries
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 7000
|  | 2002-'03 | 5000
ACC/21d |  | 2003-'04 | [5 empty] | ML
2004-'05
2005-'06
Quality standard: Target time for replying to user requests
Outcome: Audience understanding
Headline risk(s): (see Risk Register for further details)
Loss of key personnel, administrators of the systems
Failure to collect statistics
Poor management of specialist staff so they fail to meet needs
Fail to put adequate material on website so users can quickly find answers to queries
ACC/22 |  | ACTIVITY: Encourage learning
Output: Total number of learners in on-site and outreach programmes
Also in DCMS Funding Agreement (Core Target, Objective III, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 100000
|  | 2002-'03 | 130000
ACC/22a |  | 2003-'04 | 130000 |  |  |  |  | KL/ML
2004-'05
2005-'06
Output: Learners in on-site formal education programmes
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 39000
|  | 2002-'03 | 41900
ACC/22b |  | 2003-'04 | [5 empty] | KL
2004-'05
2005-'06
Output: Learners in on-site informal education programmes (including Open Museum)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 81000
|  | 2002-'03 | 87025
ACC/22c |  | 2003-'04 | [5 empty] | KL
2004-'05
2005-'06
Output: Learners in outreach programmes
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 1000
|  | 2002-'03 | 1075
ACC/22d |  | 2003-'04 | [5 empty] | KL
2004-'05
2005-'06
Output: Children in organised educational programmes both on-site and outreach
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/22d |  | 2003-'04 | 42000 |  |  |  |  | KL | Dependent on ROG Time and Space development
|  | 2004-'05 | 45000
|  | 2005-'06 | 50000
Quality standard: Level of satisfaction as indicated from comment cards
Outcome: Increased access and understanding
Headline risk(s): (see Risk Register for further details)
Under resourcing
Loss of key staff
Change in National Curriculum
ACC/23 |  | ACTIVITY: Encourage learning
Output: Total Open Museum adult education contact student hours per annum
Also in DCMS Funding Agreeement (Museum Specific Target, Objective III, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 10550
|  | 2002-'03 | 10575
ACC/23 |  | 2003-'04 | 10600 |  |  |  |  | ML
2004-'05
2005-'06
Quality standard: Content of course and teaching is satisfactory to students
Outcome: Educated audience/visitors
Headline risk(s): (see Risk Register for further details)
Poor programming leading to poor student recruitment
Staff retention
Staff illness
Poor liaison with Education Department leading to split market
ACC/24 |  | ACTIVITY: Encourage learning
Output: Number of hours of formal education provision per week
Also in DCMS Funding Agreement (Museum Specific Target, Objective III, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 65
|  | 2002-'03 | 65
ACC/24 |  | 2003-'04 | 65 |  |  |  |  | KL
|  | 2004-'05 | 65
2005-'06
Quality standard: Breadth of audience attending
Outcome: Educated audience/visitors
Headline risk(s): (see Risk Register for further details)
Loss of key staff
Hours not taken up by schools/educational groups
ACC/25 |  | ACTIVITY: Ensure a sharing of expertise
Output: UKMCS website updates per annum
Also in DCMS Funding Agreement (Museum Specific Target, Objective IV, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 12
ACC/25 |  | 2003-'04 | 12 |  |  |  |  | ML
|  | 2004-'05 | 12
2005-'06
Quality standard: Meets needs of UKMCS
Outcome: Sector aid and leadership
Headline risk(s): (see Risk Register for further details)
Museums fail to provide up to date information
ACC/26 |  | ACTIVITY: Ensure a sharing of expertise
Output: Increase in number of website visits on last year to National Register of Historic Vessels
Also in DCMS Funding Agreement (Museum Specific Target, Objective IV, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 10% increase
ACC/26 |  | 2003-'04 | 5% increase |  |  |  |  | SR
|  | 2004-'05 | 5% increase
2005-'06
Quality standard: Maintain average of 30% users who visit the site more than once
Outcome: Raising awareness of maritime issues and sector leadership
Headline risk(s): (see Risk Register for further details)
Failure of hardware disabling website
Very specialist field, number of users likely to be sustained but not improved
ACC/27 |  | ACTIVITY: Improve communication
Output: Cross-museum marketing support - to be confirmed
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/27 |  | 2003-'04 | t.b.a. |  |  |  |  | RC | Activity in here should comprise of target encouraging cross-museum activity marketing i.e. retail, catering, web, maritime resources, education, events as well as external marketing.
2004-'05
2005-'06
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
?
ACC/28 |  | ACTIVITY: Improve communication
Output: Number of media placings (excluding listings)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 950
|  | 2002-'03 | 1000
ACC/28 |  | 2003-'04 | [5 empty] | RC
2004-'05
2005-'06
Quality standard: Good publicity outweighs bad publicity
Outcome: Increase in awareness and reputation of Museum
Headline risk(s): (see Risk Register for further details)
Negative as well as positive promotion
Management of downside risks
No guarantee of press coverage
Unexciting material to promote
ACC/29 |  | ACTIVITY: Improve communication
Output: Raise public profile of Nelson and Trafalgar 200 through public lectures
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
ACC/29 |  | 2003-'04 | 12 lectures |  |  |  |  | CWh
2004-'05
2005-'06
Quality standard:
Outcome: Increase in awareness and reputation of Nelson related activities
Headline risk(s): (see Risk Register for further details)
?
ACC/30 |  | ACTIVITY: Improve planning
Output: Project plan for Time and Space development
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | Bid by June 02 | [5 empty] | Action on fundraising plan needs to be part of project development
ACC/30 |  | 2003-'04 | Project develops |  |  |  |  | RC
2004-'05
2005-'06
Quality standard: Meets customer needs
Outcome: Better visitor and education provision at ROG
Headline risk(s): (see Risk Register for further details)
Loss of project manager without succession planning
Failure to raise capital

## Stakeholder
STAKEHOLDER | [8 empty] | as at 7 April 2003
STA/1 |  | ACTIVITY: Value added customer care
Output: Number of repeat visits
Also in DCMS Funding Agreement (Core Target, Objective II, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 242000 | [5 empty] | As agreement with DCMS (29.4% of total visits) As agreement with DCMS (29.3% of total visits)
|  | 2002-'03 | 273000
Sta/1 |  | 2003-'04 | 286000 |  |  |  |  | EB
2004-'05
2005-'06
Outcome: Satisfied visitors
Headline risk(s): (see Risk Register for further details)
High proportion of overseas visitors who do not make repeat visits
Insufficient new material to persuade UK visitors to return
STA/2 |  | ACTIVITY: Value added customer care
Output: % of visitors whose overall impression of the Museum is at least satisfactory
Also in DCMS Funding Agreement (Museum Specific Target, Objective II, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 95%
|  | 2002-'03 | 96%
Sta/2 |  | 2003-'04 | 96% |  |  |  |  | EB
|  | 2004-'05 | 96%
2005-'06
Outcome: Satisfied visitors
Headline risk(s): (see Risk Register for further details)
Subjective measurement
STA/3 |  | ACTIVITY: Value added customer care
Output: % of visitors who would recommend a visit to others
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 80%
|  | 2002-'03 | 80%
Sta/3 |  | 2003-'04 | 80% |  |  |  |  | KL
2004-'05
2005-'06
Outcome: Satisfied visitors
Headline risk(s): (see Risk Register for further details)
Subjective measurement
STA/4 |  | ACTIVITY: Value added customer care
Output: Customer response mechanism: % reply rate within 10 days
Also in DCMS Funding Agreement (Supports Objective II, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 80%
Sta/4 |  | 2003-'04 | 90% |  |  |  |  | KL
2004-'05
2005-'06
Outcome: Enhanced reputation
Headline risk(s): (see Risk Register for further details)
Some replies dependent on curatorial/subject expertise/knowledge
Computerised CRM system not sufficient to do job
STA/5 |  | ACTIVITY: Value added customer care
Output: Percentage of gallery defect jobs completed to deadline (excluding long-term project items)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | 40% | [5 empty] | Revised database, new figures inputted. Note, target excludes items identified for work in long-term projects. 2003-'04 target is 60% at year end allowing for problems which might arise from new database and new reporting.
STA/5 |  | 2003-'04 | 60% |  |  |  |  | KL
|  | 2004-'05 | 70%
|  | 2005-'06 | 75%
Quality standard: Continuous improvement in defect clear-up rate
Outcome: Higher quality of product for visitor
Headline risk(s): (see Risk Register for further details)
General maintenance may suffer due to resource requirements on major projects
Database meets expectations
STA/6 |  | ACTIVITY: Improve customer care
Output: Report outcomes of investigation into Volunteer programme
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/6 |  | 2003-'04 | late summer 2003 |  |  |  |  | AB
2004-'05
2005-'06
Quality standard:
Outcome:
Headline risk(s): (see Risk Register for further details)
?
STA/7 |  | ACTIVITY: Ensure a sharing of expertise
Output: Partnerships or links in place
Also in DCMS Funding Agreement (Museum Specific Target, Objective VI, Specific Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 32
|  | 2002-'03 | 35
STA/7 |  | 2003-'04 | 40 |  |  |  |  | EB
|  | 2004-'05 | 42
2005-'06
Quality standard: Ability to maintain partnerships
Outcome: Reputation enhanced
Headline risk(s): (see Risk Register for further details)
Partnerships terminated for reasons beyond NMM control
Insufficient resources
STA/8 |  | ACTIVITY: Ensure a sharing of expertise
Output: Support NMMC with advice and expertise and assist them to achieve museum registration
Also in DCMS Funding Agreement (Museum Specific Target, Objective IV, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | NMMC open | [5 empty] | Continuing support in line with financial gurantee. Continuation of funding for curatorial post.
STA/8 |  | 2003-'04 | give support |  |  |  |  | SR
|  | 2004-'05 | aid registration
2005-'06
Quality Standard:
Outcome: NMMC is a successful venture
Headline Risk(s): (see Risk Register for further details)
?
STA/9 |  | ACTIVITY: Ensure a sharing of expertise
Output: Aid Cutty Sark in making HLF bid for preservation
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/9 |  | 2003-'04 | Bid by Dec. 2003 |  |  |  |  | SR
2004-'05
2005-'06
Quality Standard:
Outcome: NMMC is a successful venture
Headline Risk(s): (see Risk Register for further details)
?
STA/10 |  | ACTIVITY: Ensure a sharing of expertise
Output: National Register of Historic Vessels development project
Also in DCMS Funding Agreement (Museum Specific Target, Objective VI, Specific Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/10 |  | 2003-'04 | As per P.I.D. |  |  |  |  | SR | Activity to include site visits to entire Core Collection by May 2003
2004-'05
2005-'06
Quality standard:
Outcome: Items of important maritime heritage identified for the nation
Headline risk(s): (see Risk Register for further details)
Insufficient resources
STA/11 |  | ACTIVITY: Maritime Heritage Leadership
Output: Aid development of DCMS policy for historic ships
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/11 |  | 2003-'04 | Policy created |  |  |  |  | SR
Quality standard: to satisfaction of Department
Outcome: Informed policy
Headline risk(s): (see Risk Register for further details)
STA/12 |  | ACTIVITY: Improve communication with stakeholders
Output: Audience reached by NMM publicity (output to be decided)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | not established
|  | 2002-'03 | not established
STA/12 |  | 2003-'04 | [5 empty] | RC
2004-'05
2005-'06
Quality standard: Is audience consistent with NMM target audience
Outcome: Increase in awareness
Headline risk(s): (see Risk Register for further details)
Media circulation figures no guarantee of articles being read
STA/13 |  | ACTIVITY: Improve communication
Output: Internal communication (output to be decided)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2002-'03 | not established
STA/13 |  | 2003-'04 | [5 empty] | RC
2004-'05
2005-'06
Quality standard: Satisfaction as measure by IIP report and staff survey
Outcome:
Headline risk(s): (see Risk Register for further details)
STA/14 |  | ACTIVITY: Communicate/Feedback with staff
Output: Annual staff survey
Also in DCMS Funding Agreement (Supports Objective III, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
|  | 2001-'02 | Year end | Year end
|  | 2002-'03 | Year end | Year end
STA/14 |  | 2003-'04 | Revaluate |  |  |  |  | AB
|  | 2004-'05 | Survey by Mar
2005-'06
Quality standard: Implement action on findings from previous year
Outcome: Accurate picture of staff morale/potential gauged - informs HR Strategy
Headline risk(s): (see Risk Register for further details)
Funding/reward potential
Third party influence
Specific issues
STA/15 |  | ACTIVITY: Improve facilities for staff
Output: Completion of Staff Restroom
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of Forecast | Resp. | Notes
STA/15 |  | 2003-'04 | Year end |  |  |  |  | JH
Quality standard: Satisfaction of staff
Outcome: Better facilities for staff
Headline risk(s): (see Risk Register for further details)
STA/16 |  | ACTIVITY: Maintain integrity of the Official Nelson Commemorations Committee
Output: 6 meetings of the ONCC Executive Comittee per annum
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/16 |  | 2003-'04 | 6 meetings |  |  |  |  | CWh
|  | 2004-'05 | 6 meetings
Quality Standard: To satisfaction of all parties
Outcome: Raising the reputation of the NMM
Headline Risk(s): (see Risk Register for further details)
?
STA/17 |  | ACTIVITY: Developing new audiences and access
Output: Annual report on all programmes to increase social inclusion submitted to DCMS
Also in DCMS Funding Agreement (Museum Specific Target, Objective VI, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | Annual report
|  | 2002-'03 | Annual report
STA/17 |  | 2003-'04 | Annual report |  |  |  |  | KL
|  | 2004-'05 | Annual report
|  | 2005-'06 | Annual report
Quality Standard: To satisfaction of DCMS
Outcome: Programme of activities to enhance social inclusion
Headline Risk(s): (see Risk Register for further details)
?
STA/18 |  | ACTIVITY: Developing new audiences and access
Output: Executive Board agreement of outreach events programme
Also in DCMS Funding Agreement (Supports Objective VI, Strategic Purpose 2)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/18 |  | 2003-'04 | by June 2003 |  |  |  |  | KL | Including annual programmes such as: Black History month, World Mental Health Day, Chinese Festival, Diwali, Eid etc.
2004-'05
2005-'06
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
?
STA/19 |  | ACTIVITY:
Output: World Heritage Site/Local Community measure (to be agreed)
Also in DCMS Funding Agreement (Objective VI, Strategic Purpose 1)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/19 |  | 2003-'04 | [5 empty] | RC
2004-'05
2005-'06
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
?
STA/20 |  | ACTIVITY: Ensuring good sponsor relations
Output: Sponsors measure (to be agreed)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/20 |  | 2003-'04 | [5 empty] | CWa
2004-'05
2005-'06
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
?
STA/21 |  | ACTIVITY: Ensuring good DCMS relations
Output: Half year and full year reports on Funding Agreement meeting or exceeding targets
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | 2 reports
|  | 2002-'03 | 2 reports
STA/21 |  | 2003-'04 | 2 reports |  |  |  |  | RC
2004-'05
2005-'06
Quality Standard: To satisfaction of DCMS at time of performance discussion
Outcome: Good relations with major sponsor
Headline Risk(s): (see Risk Register for further details)
Failure to meet targets
STA/22 |  | ACTIVITY: Practising good governance
Output: Trustee measure (to be agreed)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
STA/22 |  | 2003-'04 | [5 empty] | RC
2004-'05
2005-'06
Quality Standard:
Outcome:
Headline Risk(s): (see Risk Register for further details)
?

## Template
No. |  | ACTIVITY: xxx
Output: xxxxx
Also in DCMS Funding Agreement (Objective X, Strategic Purpose X)
Risk Ref. | Status | Year | Forecast total | Forecast to date | Actual to date | Forecast to Actual variation | % of forecast | Resp. | Notes
|  | 2001-'02 | xx | [5 empty] | xxxxxx
|  | 2002-'03 | xx
XX |  | 2003-'04 | XX |  |  |  |  | XX
2004-'05
2005-'06
Quality Standard: xxxxx
Outcome: xxxx
Headline Risk(s): (see Risk Register for further details)
xxxx
xxxx