## Sheet1
School/District:______Oakridge SD___________________________________
Student Academic Development
Objective/Activity | Measure/baseline | Assessment Tool | Timeline
Implement CIS at Westridge MS | Purchase, implementation of CIS at Westridge MS |  | Fall, 2003
Introduce College Ed into Middle School curriculum | Purchase or materials and addition of materials into curriculum |  | Fall, Winter 2003
Implement DISCOVER Program at MS | Purchase materials |  | as available
Provide curriculum supports for high school and middle school program | Hire educational assistants at OHS and WMS to work with special ed and "at risk" students |  | Hire in Fall and keep entire year
Provide GEAR UP personnel to work with staff members and students | Building Principals, GEAR UP counselor and GEAR P coordinator |  | Start in Fall and continue
Provide homework assistance for students at the middle school | Hire staff and provide space for "Homework Club" |  | All year
Provide PSAT free of charge to all juniors at OHS | Sign up juniors and give test | Number of students taking the test | Oct. 2003
Provide Distance Learning in some format to provide academic classes not available at OHS | Have students sign up to take classes using some form of "off-campus" learning. | Number of students and hiring of educational assistant to administer program | Start as soon as staff, students and classes are available
Professional Development
Objective/Activity | Measure/baseline | Assessment Tool | Timeline
Subs for staff training to use CIS | Sending 4 staff members to training | Attendance at training | Fall 2003
Subs for staff training to use College Ed | Sending staff members to training | Attendance at training | Fall 2003
PASS training for high school staff | Sending staff to PASS training | Attendance at training | When available
Community Involvement
Objective/Activity | Measure/baseline | Assessment Tool | Timeline
Field trips to colleges and work related activities | Students attending and subs provided for staff. Budget provided for 5 trips at each building or 10 trips. | Attendance at activities | As available throughout the year.
Guest speakers for classroom and Career Day | Invite local and regional presenters | Holding Career Day and having guest speakers in the classrooms | As scheduled
Outreach & College Partnerships
Objective/Activity | Measure/baseline | Assessment Tool | Timeline
Continue partnership with Lane CC | Continue work with LCC and Depts. | Attend activities at LCC and invite LCC personnel to visit OHS/WMS | As scheduled
Work with ESD to develop more partnerships | Continue current work with ESD and continue to develop partnerships with their assistance | Attend meetings at Lane ESD and use their resources to find speakers and activities | As needed and scheduled