## Sheet1
IMIT Action Plan Status
Action Plan Task Number | Task Title and Brief Description | Status | Next Steps | Roles listed by key FS groups | [8 empty] | IMIT assessment of progress
|  |  |  | IMIT | ESCT | RIG staff | IMI | S&PF, FHM | R&D, FIA | WO Program Managers | Regions | IRM staff | IMIT assessment of progress
Business Requirements We a lack a uniform, collective understanding of the purpose and objectives for inventory and monitoring programs clearly linked to the business requirements of the agency. More explicitly identifying the links between business needs of the agency and inventory and monitoring activities will help the agency reduce unnecessary efforts, identify priorities for needed work, direct resources to fulfilling those priorities, foster program efficiencies, provide for greater accountability, and improve our ability to share data and information.
TASK 1. Ensure inventory and monitoring activities meet Forest Service business requirements and the needs of our varied customers.
1A | Statement of purpose and objectives of IM | Completed by Doug Powell; put in FSM | Finalize FSM/FSH for I&M |  |  | Lead |  |  |  | Participate | Participate
1B | Approach for analyzing business requirements | Completed by IMI | Need approach for the agency and has enduring implementation
1C | Conduct business requirements analyses | Implemented by protocol teams for Fauna, Human Dimensions, and Program Advisory coordination on I&M program management, partially modeled for agency wide activities driving I&M | Update Program Management Business Model to reflect changes in the Budget Formulation and Execution process.Review and publish for general agency access, determine strategy for long-term support for future revisions and access |  |  | Lead | Participate |  |  | Participate | Participate | Participate
|  |  | Evaluate information requirements stemming from the SDIT’s efforts to ensure they are incorporated within the overarching model and protocol development efforts. | Lead |  |  | Facilitate
|  |  | Update the overarching business model as revisions to BFES are completed. |  |  | Lead
|  |  | Complete detailed business models as a component of new protocol development efforts, incorporation of ‘existing’ protocols into the I&M Technical Guide series. Model of 8C process |  |  | Lead | Facilitate
|  |  | Convert TERRA and FSVEG NRIS hierarchical outline business models into form that enables comparison and integration with other graphical business models |  |  | Lead
|  |  | Need to complete more dimensions, conduct analysis of models and integrate to extent needed. |  |  | Lead
Ecological, Social and Economic Systems Different Forest Service units are in various stages of implementing inventory and monitoring programs that integrate data through the use of common database structures and integrated analyses to foster efficient field operations. These 'integrated' inventories attempt to combine parts of traditional inventories, however, the patterns and processes inherent in ecological, social, and economic systems (including biological, physical, and cultural aspects) are not reflected in the design. Therefore the flexibility of inventory and monitoring efforts to respond to changing issues and questions is limited. The agency needs to apply approaches that recognize the complexity of interactions and account for the dynamic nature, potential capabilities, and finite capacities of ecological, social, and economic systems at multiple scales to provide goods and services.
TASK 2. Use a systems approach as the basis for design of inventory and monitoring activities.
2A | A peer/science reviewed paper on systems approach to I & M | Draft completed and reviewed | Complete revisions based on review comments adding examples and further explanations of applications |  |  |  | Lead |  |  | Participate | Participate
|  |  | Publish (as either or both peer reviewed science paper or FS white paper) |  |  |  | Lead
2B | Description of classification schemes | Compilation planned based on NFS IMPP | Finalize and publish a description of classification schemes for ecological info that tiers to FGDC standards as appropriate. Complete and include FHM and FIA program info also |  |  | Lead |  |  |  | Participate
|  | Protocols are documenting their specific scales of data collection and analysis. | Develop common language or description of the scales of inventory and monitoring, possibly focus on levels of analyses such as National, Region, Forest, and Project (level of analyses)
New protocol development would define and publish classification as needed.
2C | Evaluate current I&M against framework | Compilation of I&M programs feasible based on IMPP, no schedule for evaluation, no technical evaluation required as part of IMPP, no plans affecting S&PF or R&D programs or explicit evaluation across deputy area programs | Use the IMPP and program reviews as vehicles for ongoing evaluation of I&M programs against framework principles |  |  | Lead |  |  |  | Participate | Participate
2D | Agreement on Data Standards | FGDC subcommittee meetings are continuing to result in the establishment of data standards. NBII meetings are leading to the establishment of standards for biological data elements. Most FS representation led through R&D. Additionally data standards are being negotiated and established through protocol dev efforts. | Ensure continued representation from FS programs in federal committees. |  |  | Lead |  |  |  | Participate
2E | Evaluate existing data stds against Natnl stds | The tech guide development process includes steps that require the development teams to evaluate national standards. The evaluation of data standards also occurs as part of the change management process for data repositories, data dictionaries, applications, and protocols. | Ensure data repositories are compatible with standards |  |  | Lead
|  |  | Use the IMPP and program reviews as vehicles for ongoing evaluation of data standards application, usefulness, effectiveness. |  |  | Lead |  |  |  | Participate | Participate
Collaboration Numerous partnerships related to inventory and monitoring work of the agency have been initiated in the past. In the absence of national leadership and oversight, field units have often independently developed and administered inventory and monitoring partnerships at the regional and local levels. From the perspective of partners, the diversity of agreements and contact persons is a disincentive to cooperation. National partnership agreements are needed to simplify regional or local agreements, clearly describe roles and responsibilities, and enable local units to benefit from national level commitments. Partnerships need to be forged with regulatory agencies (e.g.. EPA, FWS, NMFS) to foster consistency of interpretation of laws and regulations that drive many inventory and monitoring efforts within the Forest Service.
TASK 3. Improve ability to collaborate between administrative units, with partners, and customers of inventory and monitoring programs.
3A | Collaboration Goals | Draft proposal for evaluation in presented to IMIT August 2002 | Complete an evaluation of national and regional MOU’s and agreements. | Lead | [5 empty] | Participate
|  |  | Define collaboration goals and establish a process for periodically reviewing national and regional I&M agreements against these goals. | Lead | [5 empty] | Participate
|  |  | Develop standard language for MOU’s and agreements that respond to collaboration goals. |  |  | Lead |  |  |  | Participate
3B | Establish a process for sustaining and ensuring collaboration within the agency and with partners. |  | Evaluate the need for other Service-wide Agreements between programs to ensure collaboration and efficiency in FS programs (e.g. FIA and FHM). | Lead
|  |  | Establish and maintain the resource program mangers group. |  |  | Lead |  | Participate | Participate | Participate
3C | Barriers to data exchange | RIC's in support of IREMCG are calling for increased attention to resolve shared data issues among the national applications. Unknown, need list of recent efforts, include participation on steering committees | Share outcomes from IRM, GEB/GAC, and e-gov pilots | Participate |  | Participate |  |  |  | Participate | Participate | Lead
3D | Establish methods for negotiating/funding stewardship of shared data | NRIS module developers are incorporating links to external data sources such as NHD, PLANTS database. Stewards have been identified for most national data repositories. | Evaluate problems being encountered in Regions and WO staffs | [6 empty] | Participate | Participate | Lead
Accountability and Communication Three major areas of concern are (1) our ability to communicate the purpose of and findings from inventory and monitoring activities in ways that demonstrate relevance to public interests and concerns, (2) the access and use of data gathered through inventories, and (3) the scientific credibility, management, and accountability for inventory and monitoring programs, including quality assurance and quality control. The Forest Service needs to improve the communication and accountability throughout all inventory and monitoring programs.
TASK 4. Clearly articulate the purpose, scope, operations, uses, and findings of inventory and monitoring programs.
4A | Communication Strategy | Draft strategy completed for I&M in general and Wilderness monitoring protocol development | Finalize the FS I&M program communications strategy. |  |  | Lead
4B | Training Program | NRIS provides training for data management | Review draft protocols for training needs, Compile list of existing I&M training programs across WO program managers, Compile list of I&M related training being provided within Regions, FHM and FIA. |  |  |  | Lead | Participate | Participate | Participate | Participate | Participate
|  | Protocol testing process includes some training components for protocol implementation | Develop training programs specific to implementation of national protocols | [6 empty] | Lead
|  | Have draft t outline of monitoring training for LRMP monitoring at general information level for managers | Develop a training program to increase understanding and core competencies related to inventory and monitoring design, quality management, data analysis, reporting, and information sharing |  |  | Lead |  | Participate | Participate | Participate | Participate
4C | Series of Technical Papers |  | Prepare a series of technical papers addressing important topics such as statistical design and sampling methods, protocol selection, quality assurance practices, certification, technology applications, and analysis method. |  |  |  | Participate | Participate | Lead |  | Participate
|  | Protocol testing process includes some literature search targeted specific to their I&M methods | Conduct literature search for key issues and concerns on use of remote sensing, quality management, sampling design, etc. | [5 empty] | Lead | Participate | Participate
|  | Review of protocol methods is conducted throughout protocol development process. | Ensure science review of protocols and regional methods technical papers. | [5 empty] | Lead
TASK 5. Improve information and the ease of access to inventory and monitoring data and information about our programs
5A | Info System Delivery designs/methods |  | Evaluate ongoing pilot and test projects related to information and data delivery using the worldwide web. Formulate a strategy for agency and public access that provides a one-stop clearinghouse or portal to access FS I&M data, protocols, and information (including resource maps). |  |  | Participate | Participate | Participate | Participate | Participate | Participate | Lead
|  |  | Implement actions to remove identified technology barriers to the exchange of data and information between Forest Service units and principle partners via respective Chief Information Officers. |  |  | Lead | [5 empty] | Support
|  | Developmemt of enterprise models, implementation and e-gov initiatives -- there has been ongoing egove participation, there has been NHD delivery is in progress to all regions. Formation of E-Gov clearing house has been stated at GSTC. Adaptive Mgt portal test expected for completion in FY 2003. | Continue to participate with IRM staff in development of Enterprise Architecture models and their implementation. |  |  | Participate | [5 empty] | Lead
TASK 6. Strengthen scientific credibility, management, and accountability of inventory and monitoring programs.
6A | Compare FS accountability of I&M | IMPP's and BFES models provide foundation for comparison with other organizations. | Prepare proposal describing benefits and process for conducting this comparison in context of GPRA, e-Gov, and other current initiatives |  |  | Participate | Lead | Participate | Participate
|  |  | Review proposal above and formulate strategy, revise, approve, or drop | Lead |  | Participate
6B | Activity Reviews | FY02 FAT’s scheduled for Regions 2, 8,9 | Continue to strengthen Regional/Station I&M program management roles. |  |  | Participate |  | Participate | Participate | Lead
|  |  | Conduct I&M program management reviews in 3 regions during FY03. (R1, R4, and R3) Add participation by regional reps, IMI, IRM and other WO programs |  |  | Lead
6C | Process for departing from I&M standards |  | Require managers to formally assess proposed and existing inventory and monitoring activities to justify departures from standard agency protocols before activities are funded (i.e., a technical approval process). | [6 empty] | Lead
|  |  | Ensure sufficient direction and policy through the FS Manual direction |  |  | Lead |  |  |  | Participate
6D | Performance measures | Drafted table summarizing information products by spatial scale (GET MORE INFO FROM RICK ULLRICH) | Complete the “FS Information Products Portrait” to provide line officers and program managers a framework for evaluating information needs. |  |  | Lead
|  | IMPP developed. | Review Regional Inventory and Monitoring Program Plans and Regional BFES submissions. |  |  | Lead
6E | Streamline reporting requirements | Substituting IMPP's for many prior reporting requirements, coordinating reporting across resource staffs through IMPP reporting. | Discontinue use of MAR items for FY03 once Regional Program Plans have been completed (aka – streamlining reporting requirements). | [6 empty] | Lead
|  |  | Refine IMPP reporting and improve in FY 03 and beyond |  |  | Lead |  |  |  | Participate | Participate
6F | Revise FSM/FSH | Combined direction for resource inventory into FSM 1940 and designed new approach to linking stable manual and handbook guidance with more dynamic technical guide series | Issue FSM 1940 and FSH 1090.xx and approved I&M Technical Guides. Transition publication of technical guide series from RIG to other appropriate staff units and establish clearinghouse for I&M information and guidance. |  |  | Lead | Participate |  |  | Participate |  | Participate
6G | Identify advisory and assistance services |  | Review IMPP for mention of services, review detached unit "report." Identify critical advisory and assistance services Regions need to meet regional and field challenges. Review services needed with Directors of national and regional service and enterprise units (i.e. Stream Team, R&D, RSAC, MDTC, FMSC, FIA, IMI, GSTC, FHTET, etc.) to communicate priorities, evaluate capacity of units to provide assistance and support. |  |  | Lead |  |  |  | Participate | Participate
|  | Need some status from NRIS< ALP, and steering committees | Improve communication between Regions, National Apps and IRM to ensure that resolution of issues is followed-up upon. |  |  | Lead |  |  |  |  | Participate | Participate
Organization Structure and Roles The distributed authority and responsibility for inventory programs throughout the Forest Service provides opportunities for individual program areas and offices to devise unique organizational structures, policies, and operations. Coordination across inventory and monitoring programs is usually limited to collaboration required by high-profile bioregional assessments. Relatively few positions within Regional Offices are designated to manage comprehensive (multi-resource) inventory and monitoring programs. This impedes funding and management of cross-program “systems-based” inventory and monitoring activities. Inventory and monitoring policy is dispersed and promulgated by independent staffs through informal and formal channels.
TASK 7. Clearly define the organizational structure and associated responsibilities for national and regional inventory and monitoring activities.
7A | Define organizational roles/responsibilities | Drafted FSM/FSH | Finalize FSM and FSH direction | Lead
|  | Regions Info Coordinators and Stewards have been designated | Maintain lists of coordinators, include contacts (coordinators and data stewards as examples) in I&M clearing house information set | Lead
7B | Establish cross-deputy budget advisory team | Used budget coordinators from all program areas as advisors to I&M budget plans in 2002. Coordinate fiscal support to S&PF and R&D through existing mgt team representation from NFS | Reevaluate original charter for NFS-focused Program Advisory Group; Evaluate how well NFS representation with FHM and FIA Mgt teams is working to sustain coordination of funding, data collection, data sharing, and protocol development |  |  | Lead
|  |  | Charter Resource program managers group to set priorities for protocol development and fiscal investments or other national I&M priorities |  |  | Lead |  |  |  | Participate
|  |  | Evaluate how well NFS representation with FHM and FIA Mgt teams is working to sustain coordination of funding, data collection, data sharing, and protocol development |  |  | Lead |  | Participate | Participate | Participate | Participate
7C | Designate R0 Staff Director responsible for IM | Regions, Stations, and Area have designated a contact at the Staff Director level or higher to provide leadership and program management responsibility for I&M programs, including budget allocation, and improving communication and collaboration. | Evaluate how well NFS, S&PF and FIA coordination is working with designated representatives at Regional levels | [7 empty] | Lead
Protocols
TASK 8. Ensure scientifically credible sampling, data collection, and analysis protocols are used in all inventory and monitoring activities.
8A | Catalog existing protocols (sampling, collection techniques, quality control and analysis methods, and tools) being used at multiple scales | Review IMPP for lists of protocols in use and needed | Complete evaluation of ‘existing’ Field Guides and publications for inclusion in the I&M Technical Guide series. |  |  | Lead
|  |  | Review IMPP status information for lists of protocols in use and clue us in on protocol needs (many local protocols may indicate need for national protocol) |  |  | Lead |  |  |  | Participate
8B | Identify gaps in protocols that need to be filled. Establish methods to determine priorities for national investments in protocol development | Identified initial set of priority protocols with concurrence from WO program managers and Regions, TEUI, AEUI, high priority species population monitoring, and soc/econ analysis protocols | Establish ongoing process for identifying protocol needs and managing funds/support for development |  |  | Lead |  | Participate | Participate | Participate | Participate
|  |  | Document the process of determining priorities for protocol development |  |  | Lead |  |  |  | Participate
8C | Establish process for development, testing, evaluation, and adoption of protocols for collection and analysis of data for inventory and monitoring programs | S&PF: continuous development process with FHM Mgt team, R&D: continuous development process with FIA Mgt team, NFS: RIG staff coordinating development of protocols, RIG staff drafting processes for development, testing, and publishing | Complete development of protocols selected in FY02. |  |  | Lead | Participate
|  |  | Complete testing and evaluation of TEUI, AEUI, Existing Vegetation and Social & Economic protocols, publish I&M Technical Guides and implement in FY03. |  |  | Lead | Participate
|  |  | Complete the publication of protocols developed, tested in FY 02 and 03. |  |  | Lead | Participate
8D | Develop, evaluate, and transfer technologies that improve the quality and efficiency of inventory and monitoring programs throughout the Forest Service. | S&PF: continuous development process with FHM Mgt team, R&D: continuous development process with FIA Mgt team, IMI sustaining Technology Development Program with ENG and RIG, Remote Sensing Committee sponsoring development projects and limited technology transfer activities, GEB /GAC monitoring GIS tech transfer effectiveness | Ensure the efforts of the IMIT, GEB/GAC, SDIT, and other teams are working in concert. Institutionalize processes for developing, and supporting protocols across all deputy areas |  | Lead |  |  |  |  | Participate | Participate