## IKM
Activity | Time-Frame | [14 empty] | Human Resources | Materials | Financial Resources | Person Responsible
| O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
a) website, interactive components, web publishing: | [15 empty] | LB, project staff, programming contracted out |  | 15000 | LB
share procedures for web work with IEP | [18 empty] | LB | bar: Time-Frame O to Time-Frame D
draft new website for consultation | [18 empty] | LB | bar: Time-Frame O to Time-Frame D
launch new website | [18 empty] | LB | bar: Time-Frame O to Time-Frame J
maintenance website | [18 empty] | LB
monthly discussion and feed-back on website | [18 empty] | LB
b) MAPA | [15 empty] | LB, trainers, tutors |  | 80000 | LB
workshops in countries | [15 empty] | LB, country staff, trainers |  |  | LB | bar: Time-Frame N; Time-Frame M; Time-Frame J; Time-Frame S
MAPA evaluation workshop | [15 empty] | LB |  |  | LB | bar: Time-Frame F
handbook in English | [15 empty] | LB, OSI Publishing |  |  | LB | bar: Time-Frame D to Time-Frame J
handbook in Russian | [15 empty] | LB, ELP New York |  |  | LB | bar: Time-Frame F to Time-Frame M
new MAPA website | [15 empty] | LB, programmer |  |  | LB | bar: Time-Frame J to Time-Frame F
c) publishing | [15 empty] | LB, project staff |  | 10000 | LB
procedures for publications | [15 empty] | LB |  |  | LB | bar: Time-Frame O to Time-Frame D
IEP leaflet | [15 empty] | LB |  |  | LB | bar: Time-Frame O to Time-Frame N
PR Publishing | [15 empty] | LB, project staff |  |  | LB
graphics design for IEP publications | [15 empty] | LB, project staff |  |  | LB | bar: Time-Frame O to Time-Frame D
d) journal | [15 empty] | LB, editor (KS?) |  | 5000
set Boards | [15 empty] | LB, editor (KS?) | bar: Time-Frame O to Time-Frame D
graphics design | [15 empty] | LB, editor, OSI Publishing | bar: Time-Frame O to Time-Frame D
call for papers I | bar: Time-Frame N to Time-Frame D
deadline papers | bar: Time-Frame J to Time-Frame F
deadline reviewers | bar: Time-Frame F to Time-Frame M
corrections | bar: Time-Frame M
publication I | bar: Time-Frame A
call for papers II | bar: Time-Frame F to Time-Frame M
deadline papers | bar: Time-Frame M to Time-Frame J
deadline reviewers | bar: Time-Frame J to Time-Frame A
corrections | bar: Time-Frame A to Time-Frame S
publication II | bar: Time-Frame N
call for papers III | bar: Time-Frame J to Time-Frame A
deadline papers | bar: Time-Frame S to Time-Frame O
e) Library | [15 empty] | LB, library assistant (TB) |  | 10000 | LB
update database | [15 empty] | TB |  |  | LB
order publications | [15 empty] | LB |  |  | LB
put library sub-site on the web | [15 empty] | TB, LB |  |  | LB | bar: Time-Frame F to Time-Frame M
call for book reviews | [15 empty] | LB | bar: Time-Frame N to Time-Frame D; Time-Frame A to Time-Frame M; Time-Frame A to Time-Frame S
f) NGO papers | [17 empty] | 40000
call for papers | bar: Time-Frame O
deadline for papers | bar: Time-Frame D to Time-Frame J
reviews and feed-back loops | bar: Time-Frame F to Time-Frame J
EL editing | bar: Time-Frame S
publication
g) network of collaborators | [17 empty] | 12000
call for co-operation | bar: Time-Frame O to Time-Frame N
set up web pages | bar: Time-Frame D to Time-Frame J
update web pages | bar: Time-Frame J to Time-Frame D
h) database of consultants | [15 empty] | LB, TB, OSI NY |  | 0
change format | bar: Time-Frame O to Time-Frame N
test database | bar: Time-Frame N to Time-Frame D
out datbase | bar: Time-Frame D to Time-Frame J
TOTAL | [17 empty] | 172000