## Summary
Classification | Total Work In Process | Academics | Business Services | Engagement | Housing & Food Services | Institutional Research | ITaP / ITEA | Physical Facilities | Research Admin. | Student Services | University Advancement | Total # of Request for Service (RFS)
Non-Electives | 155 | [10 empty] | 324
New Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Investigations | 27 | 0 | 30 | 0 | 3 | 0 | 3 | 0 | 0 | 14 | 1 | 51
Emergency Fixes | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5
Application Fixes | 49 | 0 | 27 | 11 | 5 | 0 | 5 | 2 | 0 | 40 | 12 | 102
Scheduled Modification | 59 | 0 | 48 | 0 | 3 | 0 | 17 | 0 | 0 | 39 | 31 | 138
Production Support | 15 | 0 | 18 | 0 | 2 | 0 | 5 | 0 | 0 | 3 | 0 | 28
OnePurdue | 3 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 5
Electives | 30 | 0 | 30 | 4 | 5 | 0 | 15 | 3 | 0 | 89 | 34 | 180
Total | 188 | 0 | 157 | 15 | 18 | 1 | 48 | 5 | 0 | 187 | 78 | 509

## Electives
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Not Started | 14355 | Improve Ariba documentation | 2003-10-14 | 2005-06-30 | 150 | 300
Business Services | Ariba | Not Started | 14356 | Automate user load | 2003-10-14 | 2005-12-31 | 80 | 120
Business Services | Ariba | Not Started | 14359 | Implement Change Order Processing | 2003-10-14 |  | 100 | 150
Business Services | Ariba | Not Started | 14360 | Implement Email Approval | 2003-10-14 |  | 100 | 150
Business Services | Ariba | Not Started | 14637 | Show more data on the chooser screen for approver | 2003-11-14 | 2004-12-31 | 24 | 40
Business Services | Ariba | Pending | 14474 | Find a way to disable the "new ship tor" button for all users | 2003-10-31 |  | 30 | 50
Business Services | Ariba | Ready for Class Review | 15004 | Replace helpdesk phone number on POs | 2004-01-23 |  | 40 | 80
Business Services | BUDG | Started | 14008 | Elective modifications for 2004-05 Budget year | 2003-08-08 |  | 100 | 300
Business Services | CAAC | Not Started | 14314 | CADE - Modify to add audit on screen A922 14314 | 2003-10-06 |  | 20 | 50
Business Services | CARS | Not Started | 14118 | CARS - Agency Payment Report 14118 | 2001-09-27 |  | 40 | 80
Business Services | CARS | Not Started | 14119 | CARS - Expand comment screen limit 14119 | 2003-09-15 |  | 80 | 120
Business Services | COEUS | Pending | 14124 | COEUS - Implement new modules of COEUS 14124 | 2003-09-15 |  | 1000 | 2000
Business Services | E-Commerce | Not Started | 14441 | Commas in Amounts in Purdue-pay | 2003-09-11 |  | 20 | 40
Business Services | E-Commerce | Not Started | 14443 | Partial Refunds in IPS | 2003-03-19 |  | 80 | 120
Business Services | E-Commerce | Not Started | 14444 | Update ability for rejected ACH payments | 2003-04-08 |  | 80 | 120
Business Services | E-Commerce | Not Started | 14446 | Administrative site access without update | 2003-04-08 |  | 60 | 100
Business Services | E-Commerce | Not Started | 14447 | Purdue-pay e-mail links on payer pages | 2003-04-08 |  | 60 | 100
Business Services | E-Commerce | Started | 14440 | Libraries’ TIS IPS appl.ication | 2002-06-18 |  | 90 | 150
Business Services | FMIS | Not Started | 14121 | FMIS - FIJ3 14121 | 2003-09-15 |  | 40 | 100
Business Services | FMIS | Pending | 14122 | FMIS - FIJ4 14122 | 2003-09-15 |  | 40 | 100
Business Services | FMIS | Pending | 14125 | FMIS - On-Line Travel Booking System 14125 | 2003-09-15 |  | 500 | 1000
Business Services | FMIS | Pending | 2513 | FMIS - e-routing of CRV's & other Acct docs 2513 | 1994-11-01 |  | 500 | 1000
Business Services | FMIS | Started | 14662 | e-Comm - Implement ReconNET 14662 | 2003-11-10 | 2003-12-15 | 15 | 30
Business Services | HRMT | Not Started | 14700 | HR Self Service - Add Update Capabilities | 2003-12-05 | 2004-03-15 | 1000 | 1500
Business Services | HRMT | Not Started | 14701 | HR Self Service - Benefits Open Enrollment | 2003-12-05 | 2003-09-01 | 1000 | 1500
Business Services | HRMT | Started | 13577 | HR Self Service (13577) | 2003-01-13 |  | 1000 | 2000
Business Services | PAFX | Not Started | 13658 | FLEX Ad Hoc Report Request | 2003-02-18 |  | 80 | 100
Business Services | PAYR | Pending | 14329 | Determine an easy way to track Temporary Positions | 2003-10-13 | 2003-10-20 | 150 | 200
Business Services | RFSP | Not Started | 13540 | SPS - Award Notification (EARNIP) Phase II 13540 | 2002-12-01 | 2004-06-30 | 200 | 300
Business Services | SLAC | Pending | 11017 | SLAC - Est ACH draw down student loan pmts 11017 | 2000-10-30 |  | 200 | 400
Engagement | PREMIS | Ready for Advisory Group | 14575 | Purdue Registration & Event Management Information System (PREMIS) Phase IV | 2003-11-05 | 2004-07-01 | 1000 | 9999
Engagement | PREMIS | Ready for Advisory Group | 14576 | Purdue Registration & Event Management Information System (PREMIS) Phase V | 2003-11-05 | 2004-09-03 | 1000 | 9999
Engagement | PREMIS | Started | 14573 | Purdue Registration & Event Management Information System (PREMIS) Phase II | 2003-11-05 | 2004-02-20 | 1000 | 9999
Engagement | PREMIS | Started | 14574 | Purdue Registration & Event Management Information System (PREMIS) Phase III | 2003-11-05 | 2004-05-07 | 1000 | 9999
ITaP | WAI | Not Started | 14385 | Fix the Probability of earning a C in the Profile table. | 2003-10-16 | 2004-01-01 | 5 | 10
ITaP | WAI | Not Started | 14387 | Change the Student Program Change table to pick up the semester information prior to and subsequent from a person's change in campus or school. | 2003-10-16 | 2004-01-01 | 10 | 20
ITaP | WAI | Not Started | 14388 | Describe the CA_POSTPAY file to the DSS data warehouse so users can query as the person level detail for payroll data and balance with the University general ledger. | 2003-10-16 | 2004-06-30 | 100 | 500
ITaP | WAI | Not Started | 14709 | Define COEUS data models and load corresponding information to the Data Warehouse | 2003-12-08 | 2004-07-01 | 200 | 500
ITaP | WAI | Started | 14166 | Remove access to Instructional Tables | 2003-09-17 | 2004-01-31 | 10 | 20
ITaP | WAI | Started | 14381 | Expand 'regular hours' field for Athletics. | 2003-10-16 | 2004-01-31 | 20 | 30
ITaP | WAI | Started | 14384 | Correct Years in Position Calculation. | 2003-10-16 | 2004-01-31 | 10 | 30
ITaP | WAI | Started | 14386 | Remove Disability information from DSS for HIPAA.. | 2003-10-16 | 2004-01-21 | 10 | 20
ITaP | WAI | Started | 14393 | Correct the Grade Index field in Student DSS. | 2003-10-17 | 2004-01-31 | 20 | 40
ITaP | WAI | Started | 14607 | Remove address fields from DSS Student table. | 2003-11-11 | 2004-01-21 | 10 | 15
ITEA | Standards | Started | 12603 | Enterprise Scheduling Project | 2001-11-01 | 2002-02-28 | 1 | 1
ITEA | Standards | Started | 14271 | Portfolio Management Project | 2003-10-01 | 2004-01-30 | 1 | 100
ITEA | Standards | Started | 14274 | Implementing the Project Mgmt Software, Processes On Demand (POD) | 2003-10-01 | 2003-12-01 | 50 | 100
ITEA | Standards | Started | 14276 | RAMIS Phase Out | 2003-10-01 | 2003-12-31 | 200 | 500
ITEA | Standards | Started | 14277 | ITEA Software Administration Database | 2003-10-01 | 2003-12-01 | 50 | 150
Physical Facilities | PFPM | Pending | 12914 | PFPM - Closing work order labor 12914 | 2002-04-09 |  | 10 | 100
Physical Facilities | PFPR | Pending | 14193 | PFPR - Replace M/F Parking systems 14193 | 2003-09-18 |  | 750 | 1500
Physical Facilities | PFPR | Pending | 14200 | PFPR - Exclude Staff from annual Ticket Purge 14200 | 2003-09-22 |  | 10 | 50
Student Services | CN | Not Started | 14295 | OCEC System "Continuity 2000" interfaces to Student Systems | 2003-10-02 |  | 500 | 750
Student Services | DFA | Not Started | 14470 | Implement Parent Loan Master Prom Note (14470) | 2003-10-30 | 2004-04-15 | 100 | 200
Student Services | DFA | Started | 13890 | EFT for Alternative Loans (13890) | 2003-05-28 | 2004-01-30 | 25 | 40
Student Services | REGI | Not Started | 13709 | Honors/Convo - Update Population | 2003-03-10 | 2004-02-01 | 1 | 50
Student Services | REGI | Not Started | 14111 | Rename 6th byte of immunization data | 2003-09-15 | 2003-12-03 | 75 | 125
Student Services | REGI | Not Started | 14112 | POS Site Code - Additions & Deletions | 2003-09-15 |  | 100 | 150
Student Services | REGI | Not Started | 14225 | Change Font on encumbrance letters | 2003-09-23 |  | 25 | 50
Student Services | REGI | Not Started | 14226 | Change POS field names | 2003-09-23 |  | 100 | 200
Student Services | REGI | Not Started | 14227 | Please modify the process which creates the RESMA095 reports so that no historical reports are ‎created. Only current and future (if any) are needed.‎ | 2003-09-23 |  | 5 | 10
Student Services | REGI | Not Started | 14228 | New Campus Wide Office of Programs for Study Abroad Tracking System | 2003-09-23 |  | 1 | 9999
Student Services | REGI | Not Started | 14281 | Modify Dropped Student Encumbrance | 2003-10-02 |  | 1 | 50
Student Services | REGI | Not Started | 14282 | Modify Output for Honors Convocation | 2003-10-02 |  | 1 | 100
Student Services | REGI | Not Started | 14283 | Modify Repeat Course Audit | 2003-10-02 |  | 101 | 500
Student Services | REGI | Not Started | 14284 | Modify REAC Algorithm | 2003-10-02 |  | 101 | 500
Student Services | REGI | Not Started | 14285 | Modify Encumbrance Handling | 2003-10-02 |  | 1 | 100
Student Services | REGI | Not Started | 14286 | Status Note Sort | 2003-10-02 |  | 1 | 100
Student Services | REGI | Not Started | 14287 | Automate Final Cancel | 2003-10-02 |  | 1 | 100
Student Services | REGI | Not Started | 14288 | Modify Degree Data and Posting to Handle a Third Degree | 2003-10-02 |  | 1000 | 1500
Student Services | REGI | Not Started | 14289 | Scholastic Index by School Not Grouped Correctly | 2003-10-02 |  | 101 | 500
Student Services | REGI | Not Started | 14316 | Allow DSE to Process Foreign Addresses | 2003-10-06 |  | 1 | 100
Student Services | REGI | Not Started | 14551 | Replace or utilize PUID in Legacy Systems | 2003-11-04 |  | 1 | 9999
Student Services | REGI | Not Started | 14553 | Provide centralized PUID Solution | 2003-11-04 |  | 101 | 500
Student Services | REGI | Not Started | 14584 | Update local address directly from RMS to SI | 2003-11-07 |  | 101 | 500
Student Services | REGI | Pending | 12326 | Modification to Freshman Probablilty Index | 2001-09-20 |  | 1 | 100
Student Services | REGI | Pending | 14229 | An application integration framework must be designed and developed to facilitate the ‎move to an ERP in the future.‎ | 2003-09-23 |  | 600 | 700
Student Services | REGI | Pending | 14492 | Add PUID to SI | 2003-10-31 |  | 101 | 500
Student Services | REGI | Started | 14305 | Modification to "Address Updates from Student Housing" Report - REHCD565 | 2003-10-03 |  | 1 | 100
Student Services | SIAD | Not Started | 14297 | Prospective Student Portal | 2003-10-02 |  | 1 | 9999
Student Services | SIAD | Not Started | 14659 | ADM - Day On Campus data feed to RMS (14659) | 2003-11-20 | 2004-05-01 | 10 | 40
Student Services | SIAD | Started | 13780 | PFAE Enhancements and Scholarship BPR (13780) | 2003-04-16 | 2004-03-15 | 200 | 500
Student Services | SIS | Not Started | 14114 | E-mail addresses in SIS | 2003-09-15 |  | 300 | 400
Student Services | SIS | Not Started | 14210 | Add SIS User Preferences | 2003-09-23 |  | 100 | 150
Student Services | SIS | Not Started | 14211 | Harvest High School and Core GPA from SI. Add a field in SIS to store the Core GPA. ‎ | 2003-09-23 |  | 100 | 200
Student Services | SIS | Not Started | 14212 | E-project for SSINFO summer financial aid application | 2003-09-23 |  | 200 | 300
Student Services | SIS | Not Started | 14213 | E-project for SSINFO payroll authorization form (PAF)‎ | 2003-09-23 |  | 500 | 600
Student Services | SIS | Not Started | 14214 | E-project for display of aggregate financial aid information on SSINFO | 2003-09-23 |  | 200 | 300
Student Services | SIS | Not Started | 14215 | E-project to display the Preliminary Financial Aid Estimate (PFAE) and Scholarship Information ‎on SSINFO ‎ | 2003-09-23 |  | 700 | 800
Student Services | SIS | Not Started | 14217 | E-project to expand the loan information available on SSINFO | 2003-09-23 |  | 500 | 600
Student Services | SIS | Not Started | 14218 | E-project for interactive award letter allowing students to accept/reject/reduce various types of ‎financial aid in their aid package on SSINFO.‎ | 2003-09-23 |  | 600 | 700
Student Services | SIS | Not Started | 14220 | Application Status on SSINFO - Provide status of file‎ | 2003-09-23 |  | 50 | 100
Student Services | SIS | Not Started | 14221 | SSINFO Accounts Training & Support for Newly Admitted Students - Provide earlier ‎communication of SSINFO access to new students and inform them of their career account and ‎email login | 2003-09-23 |  | 200 | 300
Student Services | SIS | Not Started | 14222 | Please modify course roster displays and downloads to include the students who have ‎cancelled/withdrawn from the section and the date of schedule change. This inclusion could be in ‎the regular listing or as an addendum, whichever is most practical.‎ | 2003-09-23 |  | 600 | 700
Student Services | SIS | Not Started | 14223 | Please re-create the system for creation and maintenance of Progress Report Specifications ‎Matrix in the SIS system. ‎ | 2003-09-23 |  | 300 | 400
Student Services | SIS | Not Started | 14224 | Please modify the person finder screen in SIS to include options which will indicate whether the ‎person is or was ever an actual purdue student. These might include "last session of attendance", ‎campus, school, major, or classification.‎ | 2003-09-23 |  | 300 | 400
Student Services | SIS | Not Started | 14296 | Vista Deployment SIS Integration Sub-Project | 2003-10-02 |  | 1 | 9999
Student Services | SIS | Not Started | 14399 | SIS Authoritative Source for Test Scores | 2003-10-21 |  | 400 | 500
Student Services | SIS | Not Started | 14499 | BGR Registration Via the Web | 2003-11-03 |  | 250 | 500
Student Services | SIS | Not Started | 14500 | Electronic Customer Interface Developments | 2003-11-03 |  | 750 | 1000
Student Services | SIS | Not Started | 14501 | Transfer Credit | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14502 | Campus Map | 2003-11-03 |  | 100 | 200
Student Services | SIS | Not Started | 14503 | Commencement Participation Data Collection on SSINFO | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14504 | Instructor Specific Information on Course Depository in SIS | 2003-11-03 |  | 100 | 200
Student Services | SIS | Not Started | 14505 | Key Word Search for the Course Repository | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14506 | Add textbook information in the course depository on SIS | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14508 | On-line Registration | 2003-11-03 |  | 1000 | 2000
Student Services | SIS | Not Started | 14509 | On-line Plan of Study‎ | 2003-11-03 |  | 501 | 1000
Student Services | SIS | Not Started | 14510 | Enhance Student Schedule Display on SSINFO | 2003-11-03 |  | 500 | 600
Student Services | SIS | Not Started | 14511 | Student Schedule Download from SSINFO | 2003-11-03 |  | 500 | 750
Student Services | SIS | Not Started | 14512 | Wait List Enhancement on SSINFO ‎ | 2003-11-03 |  | 1 | 9999
Student Services | SIS | Not Started | 14513 | What-if Grade Calculation in SSINFO | 2003-11-03 |  | 200 | 300
Student Services | SIS | Not Started | 14514 | Electronic Grade Reporting | 2003-11-03 |  | 1 | 9999
Student Services | SIS | Not Started | 14515 | Student Organizations Enhancements on SSINFO | 2003-11-03 |  | 100 | 150
Student Services | SIS | Not Started | 14516 | Make SSINFO and SIS on the Web work on PDAs | 2003-11-03 |  | 500 | 750
Student Services | SIS | Not Started | 14517 | On-line Forms | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14518 | Off-campus Housing‎ | 2003-11-03 |  | 100 | 200
Student Services | SIS | Not Started | 14520 | Electronic Bill Presentment and Payment (replacement of Purdue Pay) ‎ | 2003-11-03 |  | 1000 | 2000
Student Services | SIS | Not Started | 14521 | Purdue-Pay Enhancements ‎ | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14522 | On-line Promissory Notes ‎ | 2003-11-03 |  | 100 | 200
Student Services | SIS | Not Started | 14523 | On-line Loan Exit Counseling | 2003-11-03 |  | 100 | 200
Student Services | SIS | Not Started | 14524 | On-line Refund Calculator | 2003-11-03 |  | 1000 | 1200
Student Services | SIS | Not Started | 14525 | TRA97‎ Enhancements | 2003-11-03 |  | 75 | 100
Student Services | SIS | Not Started | 14527 | A/R payments on-line | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14528 | On-line payment of parking tickets | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14529 | On-line payment of thesis charges | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14530 | On-line payment of application fees | 2003-11-03 |  | 1000 | 1500
Student Services | SIS | Not Started | 14532 | Display student name on SSINFO | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14533 | Provide tuition/fee charges on SSINFO after "Registered" | 2003-11-03 |  | 1 | 100
Student Services | SIS | Not Started | 14534 | Display payments on SSINFO | 2003-11-03 |  | 250 | 500
Student Services | SIS | Not Started | 14535 | Provide housing information on SSINFO | 2003-11-03 |  | 101 | 500
Student Services | SIS | Not Started | 14537 | Graduate School Bulletin | 2003-11-03 |  | 200 | 300
Student Services | SIS | Not Started | 14564 | Provide the student with a way to electronically transfer funds from his personal bank account to Boiler Express. | 2003-11-05 |  | 1 | 9999
Student Services | SIS | Not Started | 14565 | Capture alternate email addresses for parents or others as designated by the student. | 2003-11-05 |  | 1 | 100
Student Services | SIS | Not Started | 14566 | Prevent the display of the student's schedule of classes if the student is encumbered and not billed. | 2003-11-05 |  | 1 | 100
Student Services | SIS | Not Started | 14674 | Complete the Academic and Extracurricular Ranking Functionality in SIS/SIQ | 2003-11-21 | 2004-08-01 | 100 | 250
Student Services | SIS | Pending | 14230 | PUID on Course Roster | 2003-09-23 |  | 100 | 200
Student Services | SIS | Pending | 14526 | Display SSN/SID and PUID | 2003-11-03 |  | 500 | 750
Student Services | SIS | Pending | 14540 | ‎1Purdue Portal Pilot Project‎ | 2003-11-03 |  | 1 | 9999
Student Services | SIS | Started | 14209 | SIS Employee Data Upgrade | 2003-09-23 |  | 600 | 700
Student Services | SIS | Started | 14219 | Noel-Levitz 14219 | 2003-09-23 |  | 700 | 800
University Development |  | Pending | 123 | Prospect Search - Add Group Criterea | 2003-02-28 |  | 101 | 101
University Development |  | Pending | 259 | Advance Web Communities- Cathy's back up
University Development |  | Pending | 261 | Annual Giving Support (High Level Project)
University Development |  | Pending | 262 | OIR Support (High Level Project)
University Development |  | Pending | 263 | Research Support (High Level Project)
University Development |  | Pending | 265 | Vet Med client database integration (high level project)
University Development |  | Pending | 266 | WBAA application interface (High Level Project)
University Development |  | Pending | 267 | Convocations application interface (High level project)
University Development |  | Pending | 268 | Events credit card processing back end integration (High level project)
University Development |  | Pending | 269 | Advance C/S version 7 upgrade (High level project)
University Development |  | Started | 237 | Contact Report Email Send a weekly email to each fundraiser listing contact reports filed on his/her prospects. Also ‎include gifts and pledges $1,000 or higher on his/her prospects.‎ |  |  | 101 | 101
University Development | Advance C/S | Acceptance Testing | 202 | Sport Code Conversion (with Paciolan Athletics Interface) | 2003-06-23 | 2003-07-11 | 1 | 1
University Development | Advance C/S | Pending | 112 | Event management-BSR coming June 2005 |  |  | 1 | 1
University Development | Advance C/S | Pending | 159 | Coordinate PUID addition to Advance database | 2003-04-28
University Development | Advance C/S | Pending | 170 | Purgable Record Process | 2003-05-06 |  | 1 | 1
University Development | Advance C/S | Pending | 260 | Advance Web Community (High Level Project)
University Development | Advance C/S | Started | 111 | Implement Advance Web Communities - Mentoring |  |  | 501 | 501
University Development | Advance C/S | Started | 270 | Load phone numbers received from Alumni Finder on 11/10/2003‎ |  |  | 1 | 1
University Development | Advance C/S | Started | 96 | HEP matching company data load (Data Load) | 2003-05-01 |  | 1 | 1
University Development | Appeals | Pending | 273 | Add Priority School and Priority Department fields to Appeal Wizard output. ‎(if the column conatins a value of 'NULL' convert to a null value).‎ | 2004-01-15
University Development | Express Lane | Pending | 271 | Eliminate inactive allocations from displaying as a choice when ‎entering gifts | 2003-11-11
University Development | Express Lane | Pending | 8 | replace ud_send_mail.pl script | 2002-11-26
University Development | ODS | Pending | 252 | Modify head of household routine in donor refresh to include staff member test. See flowchart ‎for details.‎ | 2003-11-06 |  | 1 | 1
University Development | PAA | Pending | 264 | PAA Suport (high level Project)
University Development | Reports | Acceptance Testing | 257 | Changes to Acknowledgment Wizard for Student Services (Pres. Council) Student Services would like the ability to breakout more departments in the Acknowledgment ‎Wizard. A drop down box similar to that used for Agriculture, Science, and others is prefe | 2003-11-24 |  | 1 | 1
University Development | Reports | Pending | 224 | Alumni club download maintenance |  |  | 101 | 101
University Development | SmartCall | Pending | 140 | Improve Senior/Parent calling process. | 2003-03-25 |  | 101 | 101
University Development | SmartCall | Pending | 253 | Automation of Telefund FY Comparison Report. This report shows the number of contacts, ‎pledges, dollars pledged, pledge rate, average pledge amount, dollars raised per contact, size of ‎the population, and penetration percentage for past years and allows | 2003-11-05 |  | 101 | 101
University Development | SmartCall | Pending | 256 | Adjust the current Telefund pledge cards for IPFW, West Lafayette, Calumet and North Central ‎so that the address with show in in a standard window envelope. Currently, we have to order ‎special envelopes with larger windows in order to mail pledge cards. | 2003-11-18 |  | 101 | 101
University Development | SmartCall | Started | 5 | SmartCall thank yous | 2002-10-11 |  | 101 | 101
University Development | United Way Production | Pending | 178 | Automating UW for Regional Campuses | 2003-05-01 |  | 1 | 1
University Development | Web Processes | Started | 144 | Implement e-alumni (core product) | 2003-04-01 |  | 501 | 501
University Development | Web Processes | Started | 145 | Upgrade online giving to work with e-alumni core product | 2003-04-01 |  | 501 | 501
University Development | Web Processes | Started | 258 | Prospect Management Application web page. See attached for details.‎ | 2003-11-25 |  | 101 | 101
University Residences | Housing | Not Started | 14259 | RMS - Access to Res Hall application web data‎ 14259 | 2003-09-29 | 2003-10-01 | 2 | 20
University Residences | Housing | Not Started | 14260 | RMS - Impl e-comm for $75 deposit 14260 | 2003-09-29 | 2004-01-01 | 100 | 300
University Residences | Housing | Not Started | 14261 | RMS - Add e-mail addr to data import 14261 | 2003-09-29 | 2004-01-01 | 50 | 200
University Residences | RHCA | Pending | 11794 | RHCA - Dev card access recon for RH,BU,RE 11794 | 2001-05-04 |  | 400 | 600
University Residences | UR Data Warehouse | Pending | 14262 | UR - Design UR data warehouse strategy 14262 | 2003-09-29 | 2004-01-01 | 100 | 400

## OnePurdue
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | E-Commerce | Not Started | 14450 | help with RFI for new ecommerce solution. | 2003-02-07 |  | 100 | 150
Institutional Research | OIR | Started | 14057 | IDN Data Mart & Metrics Reporting-Phase I | 2003-04-15 | 2004-03-01 | 1800 | 2500
ITaP | Data Admin | Placeholder | 14578 | Information Quality | 2003-11-06 | 2004-12-31 | 1000 | 9999
ITaP | Data Admin | Started | 14056 | Business Intelligence | 2002-11-25 | 2004-04-01 | 8000 | 16000
ITaP | WAI | Started | 14173 | Complete the Profile Project Phase I | 2003-01-01 | 2004-01-31 | 650 | 950

## New Applications
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate

## Investigations
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Not Started | 14358 | Pcard percent variance tolerances | 2003-10-14 | 2004-03-31 | 40 | 80
Business Services | Ariba | Not Started | 14476 | Status of received orders not "processed" | 2003-10-31 |  | 20 | 100
Business Services | Ariba | Not Started | 14851 | ‎Investigate alternatives to use of SysAdmin role | 2004-01-07 | 2004-12-31 | 80 | 100
Business Services | Ariba | Started | 14351 | User load issue | 2003-10-14 | 2004-09-30 | 40 | 80
Business Services | Ariba | Started | 14427 | Check Ariba logs daily for a 6 month period | 2003-10-22 | 2004-12-22 | 950 | 950
Business Services | Ariba | Started | 14486 | ASN orders are sometimes showing "failed" status | 2003-10-31 | 2004-03-31 | 40 | 80
Business Services | Ariba | Started | 14630 | Need to add more detail to the PCard testing plan. | 2003-11-14 |  | 3 | 10
Business Services | Ariba | Started | 14852 | Verify accessibility of csv files on UNIX box | 2004-01-07 | 2004-12-31 | 20 | 30
Business Services | ASER | Pending | 14087 | ASER - Mtch Error Rpt not ‎recog 098 instruc 14087 | 2003-09-14 | 2004-08-01 | 40 | 100
Business Services | CARS | Started | 11855 | CARS - Bottom of bill not adding up 11855 | 2001-05-23 |  | 40 | 120
Business Services | COEUS | Started | 14860 | COEUS - Avg # days in UCG report problem 14860 | 2004-01-09 |  | 30 | 90
Business Services | FMIS | Started | 14945 | FMIS - Problem w/ Canadian prov. code 14945 | 2004-01-05 | 2004-01-20 | 4 | 8
Business Services | FMIS | Started | 14965 | FMIS - MSA Software Review 14965 | 2004-01-16 |  | 50 | 100
Business Services | FMIS | Started | 14987 | FMIS - Investig bank table used for EC 35 14987 | 2004-01-21 | 2004-01-23 | 4 | 8
Business Services | PAFX | Started | 14903 | FLEX "Wednesday morning" last-year process (14903) | 2004-01-09 | 2004-01-22 | 2 | 8
Business Services | PAFX | Started | 14977 | Gale/Julie noticed text on CARS billing records not same as in plan file | 2004-01-16 |  | 1 | 10
Business Services | PAIS | Pending | 14859 | PAIS Reappointment Issues (14859) | 2004-01-09 | 2004-02-27 | 10 | 40
Business Services | PAVE | Pending | 14129 | PAVE - Risk Mgt Information System/Software 14129 | 2003-09-16 |  | 100 | 200
Business Services | PAYR | Not Started | 14895 | Justification report excess ins message (14895) | 2004-01-13 | 2004-03-31 | 20 | 100
Business Services | PAYR | Pending | 14140 | Test CICS Bank Description Issue (14140) | 2003-09-16 |  | 10 | 20
Business Services | PAYR | Started | 14054 | Payroll Charge File Change at YTD Rollback (14054) | 2003-09-05 |  | 8 | 40
Business Services | PESN | Not Started | 14641 | "T" in Level Field in PEDB Current Staff (14641) | 2003-11-17 | 2004-02-27 | 4 | 8
Business Services | PESN | Not Started | 14642 | Missing Effective Date on Terminations (14642) | 2003-11-17 | 2004-03-31 | 2 | 4
Business Services | PESN | Started | 13998 | PEBLOCK related Clean-Up (13998) | 2003-08-04 | 2004-03-31 | 4 | 16
Business Services | PESN | Started | 14817 | NRA Student Adresses on IN New Hire File (14817) | 2003-12-31 | 2004-02-27 | 2 | 4
Business Services | RFSP | Pending | 14691 | SPS - Consult Interim Routing Discvry Park 14691 | 2003-12-02 |  | 30 | 60
Business Services | RFSP | Started | 14864 | SPS - Wrong e-mail verbiage for Attrib 14864 | 2004-01-09 |  | 10 | 100
Business Services | SLAC | Not Started | 14327 | SLAC - Erroneous Late Chrgs on Pd-off Loans 14327 | 2003-10-10 | 2004-07-01 | 40 | 120
Business Services | SLAC | Pending | 14185 | SLAC - E-Prom Note Functionality Investig 14185 | 2003-09-17 |  | 30 | 50
Business Services | SLAC | Started | 14097 | SLAC - Fix errors on Encumb Discrepancy Rpts 14097 | 2003-09-12 | 2004-07-01 | 40 | 120
ITAP | PUID | Not Started | 14728 | People in source file with no PUID | 2003-12-15 |  | 40 | 200
ITAP | PUID | Started | 14688 | Include Alumni relationships in PUID | 2003-12-01 | 2004-02-01 | 15 | 40
ITaP | WAI | Not Started | 14600 | Modifications required to load budget data. | 2003-11-10 | 2004-02-01 | 1 | 10
Student Services | Bursar | Not Started | 14633 | Enable Lab Course Special Fees | 2003-11-14 | 2004-07-01 | 100 | 500
Student Services | Bursar | Pending | 11377 | Add mailers choice sorting to Housing invoices. | 2001-02-09 |  | 40 | 80
Student Services | Bursar | Pending | 14377 | Fold up Designated Fees into General Fees | 2003-10-16 | 2004-07-01 | 25 | 50
Student Services | Bursar | Started | 14009 | Mainframe Support July 03 - June 04 (14009) | 2003-08-08 | 2004-06-30 | 100 | 1000
Student Services | CN | Started | 12308 | Support Replacement of PACERS | 2001-04-30 |  | 25 | 150
Student Services | DFA | Started | 14464 | Mainframe Support July 03-June 04 (14464) | 2003-10-28 | 2004-06-30 | 1 | 800
Student Services | REGI | Pending | 7287 | Year 2000-date of birth. Admissions office and Regional campuses currently use birthdate of 01/01/00 or maybe some other month-day/00 to mean unknown birthday. (see SIREFA20 for example) | 1998-04-16 | 2003-01-01 | 1 | 40
Student Services | REGI | Pending | 8321 | Ethnicity - There are new standards for reporting race/ethnicity data for all individuals on all federal surveys. The new standards require that ethnicity (Hispanic/Latino versus non-Hispanic/Latino) be reported independently from race | 1999-03-11 |  | 1 | 500
Student Services | REGI | Pending | 13727 | WF index problem research | 2003-03-24 | 2003-05-07 | 1 | 80
Student Services | REGI | Started | 13138 | Mainframe Support July 03-June 04 (13138) | 2002-06-26 | 2003-06-30 | 1000 | 2000
Student Services | REGI | Started | 14280 | ICHE SIS Country Codes (14280) | 2003-10-02 |  | 1 | 100
Student Services | REGI | Started | 14299 | Bug in POS (14299) | 2003-10-02 | 2004-02-15 | 1 | 50
Student Services | REGI | Started | 14304 | ICHE Follow-up (14304) | 2003-10-03 | 2004-04-01 | 101 | 500
Student Services | SIAD | Pending | 14979 | Changes in bulk mail | 2004-01-20 |  | 25 | 50
University Development | Advance C/S | Pending | 203 | Label Update | 2003-06-23
University Residences | RHCA | Not Started | 11795 | RHCA - Reduce Duplicate '999' #s 11795 | 2001-05-04 | 2004-07-01 | 50 | 75
University Residences | RHCA | Started | 14980 | RHCA - Questionable Entry on Error Report 14980 | 2004-01-20 |  | 1 | 5
University Residences | RHCA | Started | 15001 | RHCA - Support Designated Fee Chg 15001 | 2004-01-23 |  | 10 | 100

## Emergency Fixes
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Started | 14428 | Research reported log problems and fix as needed | 2003-10-22 | 2004-12-22 | 560 | 560
Business Services | E-Commerce | Started | 14432 | Rejected pmnts and unsuccessful pmnts for 6 months | 2003-10-23 | 2004-04-22 | 200 | 250
Business Services | E-Commerce | Started | 14459 | Daily Maintenance Job and support for a 6 months | 2003-10-28 | 2004-04-28 | 520 | 600
Student Services | Bursar | Started | 14776 | Deferred Fee Bill Window (14776) | 2003-12-24 | 2004-01-30 | 10 | 50
Student Services | Bursar | Started | 14777 | Aid type 93 disbursement problem (14777) | 2003-12-24 | 2004-02-15 | 10 | 50

## Application Fixes
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Not Started | 14475 | Modify shell script for supplier load. | 2003-10-31 | 2004-09-30 | 20 | 40
Business Services | Ariba | Not Started | 14671 | Add an auxiliary part number filter to the system | 2003-11-21 |  | 16 | 32
Business Services | Ariba | Not Started | 14672 | Fix filter by purchasing card number | 2003-11-21 | 2004-02-27 | 40 | 60
Business Services | Ariba | Not Started | 14716 | Order does not appear in the approver's box | 2003-12-09 |  | 40 | 80
Business Services | Ariba | Started | 14344 | bad approvables causing user problems | 2003-11-26 |  | 10 | 120
Business Services | Ariba | Started | 14345 | Fix Punchout catalogs - Kirby Risk example | 2003-10-14 |  | 80 | 120
Business Services | Ariba | Started | 14346 | Performance Issues | 2003-10-14 |  | 100 | 200
Business Services | Ariba | Started | 14348 | Migrating suppliers to the ASN | 2003-10-14 |  | 40 | 80
Business Services | Ariba | Started | 14350 | PC charge push to G/L | 2003-10-14 | 2004-12-31 | 20 | 40
Business Services | Ariba | Started | 14353 | Behavior of the reserve code on the user interface | 2003-10-14 | 2004-09-30 | 40 | 80
Business Services | Ariba | Started | 14673 | Make country code required on "new ship to" | 2003-11-21 | 2004-01-30 | 40 | 60
Business Services | Ariba | Started | 14884 | Ariba Purges for 12 months | 2004-01-12 | 2004-12-12 | 48 | 48
Business Services | Ariba | Started | 14885 | Reset the aribasystem password every 30 days for 6 months. | 2004-01-12 | 2004-06-12 | 1 | 1
Business Services | Ariba | Started | 14893 | Find out which search filters are indexed in Ariba | 2004-01-09 |  | 40 | 80
Business Services | Ariba | Started | 14894 | Build a mini ODS for searches needed by PFSB/Lilly | 2004-01-09 | 2004-02-27 | 75 | 100
Business Services | CAAC | Not Started | 2507 | CAAC - Abend on CAACT923 rpt group bud scrn 2507 | 2003-09-15 |  | 10 | 50
Business Services | CARS | Not Started | 11639 | CARS - Encumb files upd problems for type W 11639 | 2001-04-03 | 2004-08-01 | 40 | 160
Business Services | CARS | Not Started | 14853 | CARS- Acct# for SPS on Master, not on name 14853 | 2004-01-08 |  | 40 | 100
Business Services | CARS | Started | 14863 | CARS - Printing Serv problems w/ AR ‎mail‎ 14863 | 2004-01-09 | 2004-03-01 | 10 | 100
Business Services | E-Commerce | Not Started | 14436 | Time-zone problem for IPS applications | 2003-10-27 |  | 60 | 100
Business Services | E-Commerce | Not Started | 14449 | PGP Encryption Changes at Mellon | 2003-07-30 |  | 60 | 80
Business Services | E-Commerce | Started | 14437 | Change the server address used in external procedures as requested by IT | 2003-10-27 |  | 8 | 16
Business Services | FMIS | Started | 14127 | FMIS - Purdue Foundation Rewrite (FMIS) 14127 | 2003-09-16 |  | 30 | 60
Business Services | FMIS | Started | 15005 | FMIS - Add Explosion Rules for Fund 920 15005 | 2004-01-06 | 2004-01-30 | 4 | 20
Business Services | PAVE | Not Started | 14998 | PAVE - Problem with deleting fields in sys - 14998 | 2004-01-23 |  | 24 | 40
Business Services | PROP | Started | 13908 | PROP - New field not added in equip file 13908 | 2003-06-27 | 2003-06-27 | 40 | 80
Business Services | SLAC | Started | 14194 | SLAC - Negative Transaction Edits 14194 | 2003-09-19 | 2004-04-01 | 40 | 160
Engagement | PACERS | Ready for Class Review | 14952 | Provide support for the Home and Family conference | 2004-01-15 | 2004-06-07 | 1 | 100
Engagement | PACERS | Ready for Class Review | 14953 | Provide support for the 4-H Workshops | 2004-01-15 | 2004-06-09 | 1 | 100
Engagement | PACERS | Started | 14589 | TRA 97 Reporting for 2003 | 2003-11-07 | 2004-01-09 | 1 | 100
Engagement | PACERS | Started | 14590 | Indiana Wine and Grape | 2003-11-07 | 2004-07-01 | 1 | 100
Engagement | PACERS | Started | 14591 | Science Fair 2004‎ | 2003-11-07 | 2004-03-05 | 100 | 500
Engagement | PACERS | Started | 14595 | Sports Camps 2004‎ | 2003-11-07 | 2004-05-30 | 100 | 500
Engagement | PACERS | Started | 14596 | Road School 2004‎ | 2003-11-07 | 2004-03-10 | 100 | 500
Engagement | PACERS | Started | 14652 | Compressor Conference | 2003-11-18 | 2004-03-30 | 1 | 100
Engagement | PACERS | Started | 14653 | Pest Technology Course | 2003-11-18 | 2004-01-23 | 1 | 100
Engagement | PACERS | Started | 14755 | Exciting Science at Purdue | 2003-12-22 | 2004-03-06 | 1 | 100
Engagement | PACERS | Started | 14756 | Mortarboard Leadership Conference | 2003-12-22 | 2004-01-31 | 1 | 100
ITaP | WAI | Not Started | 13624 | Need to create JCL to skip over empty files so that jobs don't abend. | 2003-09-17 | 2004-03-31 | 10 | 20
ITaP | WAI | Not Started | 14838 | Load Grad test scores to DSS | 2004-01-06 | 2004-06-30 | 20 | 40
ITaP | WAI | Started | 14598 | Annual fall and beginning of spring DSS refreshes. | 2003-11-10 | 2004-01-31 | 25 | 100
ITaP | WAI | Started | 14737 | Correct Report Type field in Proposal Award Table | 2003-12-16 | 2004-02-01 | 5 | 20
ITaP | WAI | Started | 14878 | Fix the Student Course Table | 2004-01-09 | 2004-02-28 | 100 | 150
Physical Facilities | PPWP | Not Started | 14049 | PPWP - Fiscal Year 2003-04 14049 | 2003-08-29 | 2004-08-01 | 20 | 50
Physical Facilities | PUST | Started | 13269 | PUST - Decommission Old PUST/SIRS System 13269 | 2002-08-28 |  | 50 | 100
Student Services | Bursar | Pending | 14774 | Monitor Year End Calendar for 2004 (14774) | 2003-12-24 |  | 10 | 25
Student Services | Bursar | Pending | 14778 | Monitor annual TRA process (14778) | 2003-12-24 |  | 20 | 75
Student Services | Bursar | Pending | 14779 | Fall Fee Modifications and Testing (14779) | 2003-12-24 |  | 40 | 120
Student Services | Bursar | Pending | 14780 | Summer Fee Modifications and Testing (14780) | 2003-12-24 |  | 40 | 70
Student Services | Bursar | Pending | 14782 | Study Abroad Summer Testing (14782) | 2003-12-24 |  | 20 | 40
Student Services | Bursar | Pending | 14785 | Implement new housing rates (14785) | 2003-12-24 |  | 5 | 10
Student Services | Bursar | Started | 14775 | Usage of the 4 line address routine (14775) | 2003-12-24 | 2004-03-01 | 50 | 100
Student Services | DFA | Pending | 14797 | 2003-2004 Purge (14797) | 2003-12-30 |  | 10 | 100
Student Services | DFA | Pending | 14803 | SSACI Notification (14803) | 2003-12-30 | 2004-06-30 | 10 | 100
Student Services | DFA | Pending | 14804 | Summer TOS Pell Reporting (14804) | 2003-12-30 | 2004-07-30 | 250 | 350
Student Services | DFA | Pending | 14805 | ICHE Reporting (14805) | 2003-12-30 | 2004-09-30 | 50 | 100
Student Services | DFA | Pending | 14806 | Fall TOS's (14806) | 2003-12-31 | 2004-12-15 | 150 | 250
Student Services | DFA | Pending | 14807 | ISIR for New Year (14807) | 2003-12-31 | 2005-01-07 | 10 | 25
Student Services | DFA | Pending | 14808 | CVO Payment, Update, Billing (14808) | 2003-12-31 |  | 25 | 50
Student Services | DFA | Pending | 14811 | Mass Pass Fall/Spring (14811) | 2003-12-31 |  | 10 | 25
Student Services | DFA | Pending | 14813 | Mass Auth Fall (14813) | 2003-12-31 |  | 10 | 25
Student Services | DFA | Pending | 14814 | Mass Auth Spring (14814) | 2003-12-31 |  | 5 | 25
Student Services | DFA | Pending | 14815 | Spring Loan Start Up (14815) | 2003-12-31 |  | 20 | 30
Student Services | DFA | Ready for Class Review | 14810 | Mass Pass Summer (14810) | 2003-12-31 | 2004-03-29 | 10 | 25
Student Services | DFA | Ready for Class Review | 14812 | Mass Auth Summer (14812) | 2003-12-31 | 2004-04-19 | 10 | 25
Student Services | DFA | Started | 14490 | Correct FAM print value for Pell grants as needed | 2003-10-31 | 2004-04-01 | 100 | 500
Student Services | DFA | Started | 14491 | ICHE Problem - Calumet FA data (14491) | 2003-10-31 | 2003-02-15 | 1 | 100
Student Services | DFA | Started | 14645 | Fix bug in CDVU program (14645) | 2003-11-17 | 2004-02-01 | 50 | 75
Student Services | DFA | Started | 14795 | Fed Regs 2004 (14795) | 2003-12-30 | 2004-03-01 | 250 | 500
Student Services | DFA | Started | 14796 | INAS for New Year (14796) | 2003-12-30 | 2004-03-31 | 10 | 50
Student Services | DFA | Started | 14798 | PARS Changes/Simulations (14798) | 2003-12-30 | 2004-03-31 | 10 | 100
Student Services | DFA | Started | 14799 | ANL/MIL (14799) | 2003-12-30 | 2004-03-31 | 10 | 100
Student Services | DFA | Started | 14800 | Summer Mod Loans (14800) | 2003-12-30 | 2004-03-31 | 10 | 40
Student Services | DFA | Started | 14801 | Summer Mod Auth (14801) | 2003-12-30 | 2004-03-31 | 10 | 40
Student Services | DFA | Started | 14802 | SSACI Application (14802) | 2003-12-30 | 2004-03-31 | 10 | 100
Student Services | DFA | Started | 14809 | Summer/Fall Loan Disb Date (14809) | 2003-12-31 | 2004-03-30 | 10 | 25
Student Services | REGI | Pending | 14791 | Grade Support - Spring & Summer (14791) | 2003-12-30 |  | 10 | 25
Student Services | REGI | Pending | 14792 | Grade Support - Fall (14792) | 2003-12-30 |  | 10 | 25
Student Services | REGI | Pending | 14794 | Load Support Summer and Fall (14794) | 2003-12-30 |  | 10 | 50
Student Services | REGI | Started | 14585 | Modify Regional Audit program RERCSPLT | 2003-11-07 | 2004-02-15 | 1 | 100
Student Services | REGI | Started | 14793 | Load Support Spring (14793) | 2003-12-30 | 2004-01-30 | 10 | 25
Student Services | SIAD | Pending | 14769 | Annual Sorority Rush Support (14769) | 2003-12-24 | 2004-12-01 | 10 | 30
Student Services | SIAD | Pending | 14770 | Day on Campus Annual Support (14770) | 2003-12-24 |  | 50 | 100
Student Services | SIAD | Pending | 14771 | Annual VMCAS Modifications (14771) | 2003-12-24 |  | 10 | 100
Student Services | SIAD | Pending | 14772 | Annual PFAE Modifications (14772) | 2003-12-24 |  | 50 | 150
University Development |  | Not Started | 104 | Redevelop manage cache process (Analysis to be completed in January)
University Development | Advance C/S | Acceptance Testing | 125 | Load Miscellaneous data from Alumni Finder | 2003-03-03 |  | 1 | 1
University Development | Advance C/S | Awaiting Implementation | 231 | Adance C/S - Orbital batch detail getting user name stamp on update. Should be Telefund stamp for Orbital report. | 2003-09-02 |  | 1 | 1
University Development | Advance C/S | Pending | 7 | Purge old unix log files | 2002-11-26 |  | 1 | 1
University Development | Advance C/S | Pending | 99 | Resolve PVCS/Powerbuilder issue
University Development | Advance C/S | Pending | 107 | Oracle upgrade to version 9i
University Development | Advance C/S | Pending | 196 | Reset the PCC number in the Orbital ID generator to start again at PCC0000001. | 2003-06-17 |  | 1 | 1
University Development | ITEA Internal Applications | Pending | 103 | Supplemental account refresh |  |  | 1 | 1
University Development | ITEA Internal Applications | Pending | 105 | Error checking in Unix shell scripts |  |  | 1 | 1
University Development | ODS | Pending | 72 | Balance UDODSDEV | 2003-01-15
University Development | ODS | Started | 236 | Process ODS Refresh on Records with Multiple Maiden Name and Nickname Errors | 2003-09-16 |  | 101 | 101
University Development | SmartCall | Started | 189 | Adjustment to Telefund Reminder Process | 2003-06-09 |  | 1 | 1
University Residences | FSMIS-Food Service | Started | 10659 | FSMIS - CBORD - Remove FSMIS 10659 | 2000-01-01 | 2004-07-01 | 50 | 600
University Residences | RHAC | Not Started | 14868 | RHAC - User Friendly mod - add entry 14868 | 2004-01-09 | 2004-07-01 | 10 | 100
University Residences | RHAC | Pending | 6020 | RHAC - Eliminate CDE for Budget Projects 6020 | 1997-04-22 | 2004-09-30 | 1 | 5
University Residences | RHCA | Started | 12873 | RHCA - Review CICS files to eliminated 12873 | 2002-03-28 | 2004-07-01 | 10 | 15
University Residences | RHCA | Started | 14865 | RHCA - Better tailor Activity Rpt for needs 14865 | 2004-01-09 | 2004-02-15 | 10 | 100

## Scheduled Modifications
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Not Started | 14357 | Remove MERS number | 2003-10-14 | 2004-06-30 | 40 | 80
Business Services | Ariba | Not Started | 14821 | Work with zone to create monthly list of csv files | 2004-01-05 | 2004-03-31 | 20 | 30
Business Services | Ariba | Started | 14349 | Investigate and implement Ariba standard reports | 2003-10-14 | 2004-09-30 | 80 | 120
Business Services | Ariba | Started | 14352 | PCR reroute back to the approver | 2003-10-14 | 2004-12-31 | 40 | 80
Business Services | Ariba | Started | 14819 | Try to produce report of orders over the $100 cap | 2004-01-05 | 2004-03-31 | 50 | 150
Business Services | Ariba | Started | 14820 | Store only last 6 digits of SS# in user.csv file | 2004-01-05 | 2004-06-30 | 50 | 100
Business Services | ASER | Started | 14626 | HR - Med Contrib Field Expan in FI, Ag, ASER 14626 | 2003-11-13 | 2004-01-31 | 100 | 150
Business Services | BUDG | Started | 13985 | Annual Budget System Mods for 04-05 Budget (13985) | 2003-07-30 |  | 100 | 500
Business Services | CAAC | Pending | 11008 | SPS - Create new F&A Base for SPS Accounts 11008 | 2000-11-16 | 2001-06-30 | 5 | 10
Business Services | CARS | Not Started | 14731 | CARS - Reflect in FMIS chg acct from CARS - 14731 | 2003-12-15 | 2004-07-01 | 100 | 300
Business Services | CARS | Pending | 12870 | CARS - Modify FMIS feeds payments to write-offs 12870 | 2002-03-28 | 2002-05-31 | 20 | 60
Business Services | CARS | Pending | 13108 | CARS - Credit balance on type W accounts 13108 | 2002-06-20 |  | 30 | 60
Business Services | CARS | Pending | 14546 | CARS - W-O NFEE not posting bad debt to FMIS 14546 | 2003-10-30 |  | 20 | 40
Business Services | CARS | Started | 14732 | CARS - Incl Reg Campus 1-2140 on Mo Recon - 14732 | 2003-12-15 | 2004-03-01 | 20 | 40
Business Services | COEUS | Not Started | 14071 | COEUS - Impl IRB module - Phase I & Phase II 14071 | 2003-09-10 |  | 800 | 1600
Business Services | FMIS | Not Started | 15006 | FMIS - Add Obj 49102 to SPS Front End Edit 15006 | 2004-01-02 | 2004-01-30 | 8 | 20
Business Services | FMIS | Pending | 14094 | FMIS - Fix Schedule I object mapping 14094 | 2003-09-15 |  | 20 | 40
Business Services | ODS Replication | Started | 14949 | Replicate 11 new tables for Paciolan interface | 2003-05-01 | 2003-12-31 | 160 | 240
Business Services | ODS Reporting | Started | 14913 | Pacesetter - Move withdrawn proposals to result report | 2003-07-22 | 2003-09-01 | 100 | 160
Business Services | PAFX | Started | 13710 | Employer Medical Field Expansion (13710) | 2003-03-10 |  | 900 | 1200
Business Services | PAFX | Started | 13783 | FSA Duplicate Claims Problem (13783) | 2003-04-14 |  | 8 | 40
Business Services | PAFX | Started | 13887 | Spousal Opt-out without Medical Credit (13887) | 2003-06-16 |  | 4 | 8
Business Services | PAYR | Not Started | 14724 | Need to Handle 2 PayPeriod 80s in FY 04-05 (14724) | 2003-12-12 | 2005-06-30 | 800 | 1200
Business Services | PAYR | Placeholder | 15002 | Modify Regional Grad Health Insurance in Paryoll Charge | 2004-01-23 |  | 30 | 50
Business Services | PAYR | Started | 12277 | COBOLII Conversions (12277) | 2001-09-06 |  | 90 | 100
Business Services | PAYR | Started | 13958 | Payroll Year End 2003 (13958) | 2003-07-17 |  | 100 | 500
Business Services | PAYR | Started | 14242 | Excess Insurance W-2 Modification (14242) | 2003-09-26 | 2004-03-31 | 200 | 400
Business Services | PAYR | Started | 14467 | SS/OASDI Wage Base for 2004 (14467) | 2003-10-29 | 2003-12-30 | 4 | 8
Business Services | PAYR/PAFX | Pending | 10999 | Modify Liberty Mutual Workers Comp Data (10999) | 2000-09-05 |  | 40 | 80
Business Services | PAYR/PAFX | Placeholder | 14974 | Health Assessment Benefit (14974) | 2004-01-16 |  | 1 | 999
Business Services | PAYR/PAFX | Placeholder | 14975 | Health Savings Account Benefit (14975) | 2004-01-16 |  | 1 | 999
Business Services | PAYR/PAFX | Placeholder | 14976 | Direct Charge Leave Accruals (14976) | 2004-01-16 |  | 1 | 999
Business Services | PAYR/PAFX | Started | 14373 | Voluntary Benefit Bill & Remit Vendor File (14373) | 2003-10-15 | 2003-12-01 | 200 | 300
Business Services | PESN | Not Started | 14702 | Replace Student/Personnel Interface (14702) | 2003-12-03 | 2003-11-26 | 1 | 1
Business Services | PESN | Started | 13977 | Missing Form 4 Biweekly Updates (13977) | 2003-07-29 | 2003-08-12 | 40 | 120
Business Services | PESN | Started | 13978 | Academic Rank Date Fix (13978) | 2003-07-29 | 2003-08-13 | 40 | 120
Business Services | PESN/PAYR | Placeholder | 14972 | Research Faculty Position Code (14972) | 2004-01-16 |  | 1 | 999
Business Services | PESN/PAYR | Placeholder | 14973 | New Grad Student Classification (14973) | 2004-01-16 |  | 1 | 999
Business Services | PROP | Pending | 12958 | PROP - Action History File problms - Form data missing 12958 | 2002-01-01 | 2002-04-30 | 40 | 200
Business Services | PUPO | Pending | 14092 | PUPO - Bill 1811 - Part 2 14092 | 2003-09-15 |  | 60 | 80
Business Services | PUPO | Pending | 14093 | PUPO - Bill 1811 - Part 3 14093 | 2003-09-15 |  | 40 | 80
Business Services | SLAC | Not Started | 14095 | SLAC - Sep Disab/Death Cancel for PU Loans 14095 | 2003-08-26 | 2004-07-01 | 40 | 120
Business Services | SLAC | Not Started | 14141 | SLAC - Perkins Promissory Note 14141 | 2003-09-16 | 2004-07-01 | 40 | 120
Business Services | SLAC | Not Started | 14664 | SLAC - NOTIF in bal file w/ "B" on 0 bal 14664 | 2003-11-21 | 2004-09-30 | 50 | 100
Business Services | SLAC | Not Started | 14665 | SLAC - Est new interest rate for PU loans 14665 | 2003-11-21 | 2004-07-01 | 120 | 240
Business Services | SLAC | Not Started | 14714 | SLAC - Remove Defer 35 & 47 from Loan List 14714 | 2003-12-08 | 2004-08-08 | 40 | 120
Business Services | SLAC | Pending | 12709 | SLAC - Calumet to reactivate FTP 05 Trns 12709 | 2002-01-14 |  | 4 | 16
Business Services | YREND | Placeholder | 14971 | FMIS - Annual Yr End Mods 14971 | 2004-01-16 | 2004-07-01 | 200 | 300
ITAP | PUID | Not Started | 14685 | Improve PUID Matching / Scoring process | 2003-11-25 | 2004-03-31 | 200 | 500
ITAP | PUID | Not Started | 14726 | PUCC Feed Flag Issues | 2003-12-15 |  | 80 | 120
ITAP | PUID | Not Started | 14727 | Send Expunge when last active relationship removed | 2003-12-15 |  | 40 | 200
ITAP | PUID | Not Started | 14729 | Timing of student status | 2003-12-15 |  | 40 | 200
ITAP | PUID | Not Started | 14730 | Data not updating from Source files into PUID | 2003-12-15 |  | 40 | 200
ITAP | PUID | Started | 14686 | Additional PUID Assignment | 2003-11-25 | 2004-02-27 | 80 | 400
ITAP | PUID | Started | 14687 | SI-Purge Clean-up | 2003-12-01 | 2004-01-12 | 80 | 120
ITaP | WAI | Not Started | 14862 | Move Financial Aid data to the Data Warehouse | 2004-01-09 | 2004-09-01 | 500 | 1000
ITaP | WAI | Not Started | 14867 | Move Regional Campus Application Data to the DW | 2004-01-09 | 2004-09-01 | 250 | 600
ITaP | WAI | Placeholder | 14699 | Extend PUID system to resolve identity problems before they are propagated to legcy systems and the Data Warehouse. | 2003-12-04 |  | 100 | 499
ITaP | WAI | Ready for Class Review | 14697 | DSS Student, Financial, and employee (including the Workforce file) data all have departmnet names/codes associated with them independently. A method needs to be developed to match departments across the different data types. | 2003-12-04 | 2004-07-01 | 101 | 500
ITaP | WAI | Started | 13625 | Remove the current test scores from Student Table | 2003-09-23 | 2004-01-31 | 2 | 5
ITaP | WAI | Started | 14169 | Clean up records in student DSS with 2 query ids | 2003-09-17 | 2004-01-31 | 200 | 350
ITaP | WAI | Started | 14174 | Move Admissions Application data to the D W. | 2003-09-17 | 2004-01-31 | 650 | 950
ITaP | WAI | Started | 14599 | Complete the Student DSS Profile Project Phase II | 2003-11-10 | 2004-07-01 | 650 | 900
ITEA | PACII | Started | 13689 | PACII - Remove Vacation Tracking System. | 2003-02-28 |  | 25 | 50
ITEA | PACII | Started | 14106 | PACII - Archive and shut down. | 2003-09-15 |  | 50 | 100
Student Services | Bursar | Not Started | 10742 | Print Archived Advice Forms (10742) | 2000-10-04 | 2005-01-01 | 100 | 499
Student Services | Bursar | Not Started | 13499 | Commonline v 5.0 Upgrade (13499) | 2002-12-05 | 2005-06-01 | 150 | 300
Student Services | Bursar | Not Started | 13501 | Purge Advice History | 2002-12-05 | 2005-01-01 | 50 | 100
Student Services | Bursar | Started | 13786 | TRA New Requirements (13786) | 2003-04-17 | 2004-03-01 | 120 | 500
Student Services | DFA | Not Started | 12992 | Earn Paid for Pell and SWT (12992) | 2002-04-26 | 2004-06-01 | 40 | 120
Student Services | DFA | Not Started | 13503 | Delete Alpha Check Audit Report (13503) | 2002-12-06 | 2004-03-01 | 15 | 30
Student Services | DFA | Not Started | 13768 | DOE common record (13768) | 2003-04-10 | 2004-07-30 | 300 | 1000
Student Services | DFA | Not Started | 14323 | Annual SSACI Reconciliation (14323) | 2003-10-07 | 2004-09-30 | 80 | 200
Student Services | DFA | Not Started | 14463 | FISAP (14463) | 2003-10-28 | 2004-09-15 | 15 | 40
Student Services | DFA | Not Started | 14478 | Update PLUSENRL for summer 2004 (14478) | 2003-10-31 | 2004-04-15 | 1 | 10
Student Services | DFA | Not Started | 14873 | PFAE Data Capture for Noel Levitz (14873) | 2004-01-09 |  | 50 | 100
Student Services | DFA | Ready for Class Review | 14981 | DBD Update | 2004-01-20 | 2004-02-16 | 1 | 5
Student Services | DFA | Started | 12611 | Mod the download to include alt loans (12611) | 2002-01-02 | 2004-01-31 | 20 | 80
Student Services | DFA | Started | 14341 | 2002-2003 Purge (14341) | 2003-10-14 | 2004-01-30 | 1 | 100
Student Services | DFA | Started | 14489 | Modify CDVB program (14489) | 2003-10-31 | 2004-02-01 | 50 | 100
Student Services | DFA | Started | 14704 | Mod aid auth to always look for AUTH doc (14704) | 2003-12-05 | 2004-03-15 | 50 | 150
Student Services | DFA | Started | 14767 | Carry Forward (14767) | 2003-12-23 | 2004-03-01 | 50 | 150
Student Services | REGI | Pending | 14816 | Annual ICHE Support (14816) | 2003-12-31 |  | 40 | 80
Student Services | REGI | Started | 14790 | IUPUI Interface (14790) | 2003-12-30 | 2004-10-01 | 25 | 100
Student Services | SIAD | Not Started | 13508 | Modify SAT fields, SISO and reports (13508) | 2002-12-06 | 2005-02-01 | 200 | 500
Student Services | SIAD | Not Started | 14001 | Annual Web App Support (14001) | 2003-08-05 | 2004-08-15 | 100 | 500
Student Services | SIAD | Started | 14003 | Mainframe Support July 03 - June 04 (14003) | 2003-08-05 | 2004-06-30 | 10 | 50
Student Services | SIS | Not Started | 14206 | SAT/PSAT Major Code Change | 2003-09-23 |  | 25 | 50
Student Services | SIS | Not Started | 14238 | SAT I External Load | 2003-09-26 |  | 10 | 25
Student Services | SIS | Not Started | 14407 | Natl Merit and IRTSAP Mods (annual) | 2003-10-22 |  | 8 | 40
Student Services | SIS | Not Started | 14409 | JETS Engr Ext Data Load 14208 | 2003-10-22 |  | 5 | 15
Student Services | SIS | Not Started | 14411 | Geomarket Update (EPS) (annual) | 2003-10-22 |  | 8 | 24
Student Services | SIS | Not Started | 14413 | High School Load Mods (annual) | 2003-10-22 |  | 8 | 24
Student Services | SIS | Not Started | 14415 | ACT Load Mods (annual) | 2003-10-22 |  | 8 | 24
Student Services | SIS | Not Started | 14417 | SAT Load Mods (annual) | 2003-10-22 |  | 8 | 24
Student Services | SIS | Not Started | 14419 | Jr. Survey Data Load (annual) | 2003-10-22 |  | 8 | 24
Student Services | SIS | Pending | 10934 | Twenty-First Century Scholar Load Mods (annual) | 2000-11-02 |  | 8 | 24
Student Services | SIS | Pending | 10939 | PSAT Load Mods (annual) 10939 | 2000-11-02 |  | 8 | 24
Student Services | SIS | Pending | 12662 | Plan EOS Data Load Mods (annual) 12662 | 2002-01-04 |  | 8 | 40
Student Services | SIS | Pending | 12663 | Ventures Scholars Load Mods (annual) 12663 | 2002-01-04 |  | 8 | 40
Student Services | SIS | Ready for Class Review | 14933 | Replicate all Registrar-relevant SIS tables to SIQ.‎ | 2004-01-14 |  | 75 | 100
Student Services | SIS | Started | 13923 | SAT/ACT Modifications 13923 | 2003-07-02 | 2005-03-01 | 100 | 499
Student Services | SIS | Started | 14421 | ISIRS Mods (annual) 14421 | 2003-10-22 | 2004-02-29 | 40 | 100
Student Services | SIS | Started | 14705 | Cleanup bogus PUID's | 2003-12-05 | 2004-01-24 | 10 | 25
University Development |  | Awaiting Implementation | 120 | Replicate 11 new tables for Paciolan interface | 2003-05-01 |  | 1 | 1
University Development |  | Awaiting Implementation | 208 | JPC download link-Alert |  | 2003-08-15 | 1 | 1
University Development |  | Started | 218 | Assist with Athletics interface |  |  | 1 | 1
University Development | Advance C/S | Acceptance Testing | 127 | Set up codes for IU Records at IPFW | 2003-03-03 |  | 101 | 101
University Development | Advance C/S | Awaiting Implementation | 248 | Remove PC Joint Formal Salutation rows (Type'PC') from ADVANCE.SALUTATION | 2003-11-04 |  | 1 | 1
University Development | Advance C/S | Awaiting Implementation | 250 | Work with BSR to fix gift club maintenance issue in client.‎ | 2003-11-04 |  | 101 | 101
University Development | Advance C/S | Not Started | 15008 | Advance C/S upgrade | 2004-01-26 | 2004-09-01 | 480 | 640
University Development | Advance C/S | Pending | 106 | Advance C/S upgrade |  |  | 1 | 1
University Development | Advance C/S | Started | 88 | PF/Accounting Rewrite | 2003-04-30 | 2003-10-10 | 501 | 501
University Development | Advance C/S | Started | 90 | Paciolan Athletics Interface | 2003-05-01 | 2003-05-31 | 101 | 101
University Development | Advance C/S | Started | 249 | Document how names are built in various applications; strive to use name wizard as re-usable ‎object in all applications that generate names of communication with donors. Applications ‎identified are: Name wiz itself, Appeal Wiz, Label Wiz, Directory Do | 2003-11-04 |  | 501 | 501
University Development | Advance C/S | Started | 14914 | Assist with Athletics interface | 2004-01-13 |  | 500 | 1000
University Development | Advance C/S | Started | 14915 | Set up codes for IU Records at IPFW | 2003-03-03 | 2003-04-01 | 160 | 200
University Development | Advance C/S | Started | 14919 | JPC Giftclub (with Paciolan Athletics Interface) | 2003-05-09 | 2004-02-21 | 320 | 480
University Development | Advance C/S | Started | 14947 | Gift club inactivation | 2003-04-23 | 2004-02-24 | 320 | 640
University Development | Advance C/S | Started | 14948 | Weekly process to inactivate JPC memberships (with Paciolan Athletics Interface) | 2003-08-08 | 2003-12-15 | 160 | 240
University Development | Advance C/S | Started | 14950 | AKA/nickname clean-up | 2003-11-04 | 2004-01-01 | 160 | 240
University Development | Advance C/S | Started | 15009 | Paciolan Athletics Interface | 2003-01-26 |  | 640 | 800
University Development | Advance C/S | Started | 15010 | PF/Accounting Rewrite | 2003-04-01 | 2003-07-31 | 640 | 800
University Development | Advance C/S | Started | 15011 | JPC download link-Alert | 2003-05-09 | 2003-10-01 | 320 | 480
University Development | Advance C/S | Started | 15012 | Remove PC Joint Formal Salutation rows (Type'PC') from ADVANCE.SALUTATION | 2003-10-01 | 2004-01-01 | 160 | 320
University Development | Advance C/S | Started | 15013 | Document how names are built in various applications | 2003-10-01 | 2004-01-01 | 160 | 320
University Development | Advance C/S | Started | 15014 | Work with BSR to fix gift club maintenance issue in client.‎ | 2003-10-01 | 2004-01-01 | 160 | 320
University Development | Gift Clubs | Awaiting Implementation | 217 | Weekly process to inactivate JPC memberships (with Paciolan Athletics Interface) | 2003-08-08 |  | 1 | 1
University Development | Gift Clubs | Started | 153 | JPC Giftclub (with Paciolan Athletics Interface) | 2003-05-09 |  | 1 | 1
University Development | Gift Clubs | Started | 156 | Gift club inactivation | 2003-04-23 |  | 501 | 501
University Development | Reports | Acceptance Testing | 215 | Pacesetter - Move withdrawn proposals to result report | 2003-07-22 |  | 1 | 1
University Development | SmartCall | Started | 247 | SmartCall 9.2 Upgrade‎ | 2003-10-29 |  | 101 | 101
University Development | Smartcall | Started | 15015 | SmartCall 9.2 Upgrade‎ | 2003-10-29 | 2003-12-31 | 80 | 160
University Development | United Way Production | Acceptance Testing | 176 | Create a Match between SSN and PUID for Payroll deductions | 2003-04-21 |  | 1 | 1
University Development | United Way Vendor Implementati | Awaiting Implementation | 154 | Replace the United Way mainframe system | 2002-10-01 | 2003-06-01 | 101 | 101
University Residences | RHCA | Started | 13704 | RHCA - Card Access Redgn Interface - add DOC 13704 | 2003-03-01 | 2004-07-31 | 300 | 1000
University Residences | RMS | Not Started | 14481 | RMS - SI Import mod 2‎ - RDL Override 14481 | 2003-10-30 | 2004-01-01 | 25 | 50
University Residences | RMS | Not Started | 14482 | RMS - SI Import mod- Change in PUID number 14482 | 2003-10-31 | 2004-01-01 | 25 | 50

## Production Support
V.P. Area | System | Status | ITEA RFS # | Short Description | Date Received | Target Date | Low Estimate | High Estimate
Business Services | Ariba | Not Started | 14997 | Follow up with infrastructure staff to run diagnostic suggested by Ariba in conference call on 1/22/04. Provide feedback to Ariba so that they can help determine if there is a way to lower the CPU being used by the bin process. | 2004-01-22 |  | 20 | 40
Business Services | BUDG | Started | 7145 | General Support - Budget (7145) | 1998-03-02 |  | 40 | 400
Business Services | COEUS | Started | 14999 | COEUS - Support Rollout to Regionals 14999 | 2004-01-23 |  | 10 | 30
Business Services | FMIS | Started | 14967 | FMIS - Fund Explosion File Listing‎ 14967 | 2004-01-16 |  | 1 | 10
Business Services | FMIS | Started | 14968 | FMIS - Attribute File Data Load 14968 | 2004-01-16 |  | 1 | 10
Business Services | PAFX | Not Started | 14956 | Flex Open/Close Enrollment 2004 (14956) | 2004-01-15 | 1931-01-31 | 100 | 200
Business Services | PAFX | Started | 8098 | Audit Emergency ACID's for FlexSystem (8098) | 1998-12-28 |  | 40 | 40
Business Services | PAFX | Started | 9460 | General Support - Flex (9460) | 1999-12-03 |  | 100 | 300
Business Services | PAIS | Started | 12585 | General Support - PAIS (12585) | 2001-12-26 |  | 4 | 100
Business Services | PAYR | Not Started | 14938 | Salary Budget Forward 2004 (14938) | 2004-01-14 | 2004-07-31 | 200 | 400
Business Services | PAYR | Not Started | 14939 | August AY Payroll 2004 (14939) | 2004-01-14 | 2004-09-30 | 100 | 200
Business Services | PAYR | Not Started | 14954 | Payroll Year-End 2004 (14954) | 2004-01-15 | 2005-03-01 | 200 | 400
Business Services | PAYR | Started | 10495 | General Support - Payroll Calculator (10495) | 2000-08-02 |  | 80 | 100
Business Services | PAYR | Started | 12415 | General Support - Payroll (12415) | 2001-10-22 |  | 1 | 40
Business Services | PESN | Started | 8317 | General Support - Resumix (8317) | 1999-03-10 |  | 100 | 150
Business Services | PESN | Started | 11435 | General Support - Personnel (11435) | 2001-02-19 |  | 1 | 100
Business Services | PESN | Started | 13628 | Administrative Overhead for HR team (13628) | 2003-02-05 |  | 100 | 200
Business Services | YREND | Not Started | 14160 | FMIS - Year end support 2004 14160 | 2003-09-17 |  | 50 | 100
ITaP | WAI | Ready for Class Review | 14889 | Maintenance procedures for Data Cubes | 2004-01-12 | 2004-06-01 | 200 | 400
ITaP | WAI | Ready for Class Review | 14994 | Investigate DSS Refresh Data Load Procedures | 2004-01-21 |  | 20 | 40
ITaP | WAI | Started | 14848 | Financial trouble shooting and system admin | 2004-01-07 | 2004-01-31 | 10 | 50
ITaP | WAI | Started | 14849 | Student DSS system admin and trouble shooting | 2004-01-07 | 2004-01-31 | 10 | 50
ITaP | WAI | Started | 14870 | Trouble Shooting/mainrtenance of ETL environment | 2004-01-09 | 2004-01-31 | 10 | 50
Student Services | SIS | Pending | 14935 | Predictive Modeling - Annual Support Prospect | 2004-01-14 |  | 75 | 125
Student Services | SIS | Pending | 14936 | Predictive Modeling - Annual Support Inquiry | 2004-01-14 |  | 75 | 125
Student Services | SIS | Pending | 14937 | Predictive Modeling - Annual Support Admit | 2004-01-14 |  | 75 | 125
University Residences | PRIDE | Not Started | 13992 | PRIDE - Remove and Archive PRIDE System 13992 | 2003-09-01 | 2005-01-01 | 50 | 100
University Residences | RHAC | Not Started | 14255 | RHAC - Annual Reporting 2003-2004 14255 | 2003-09-29 | 2004-09-29 | 100 | 200

## By V.P Area
Classification | Business Services | Porfolio for Business Services
Non-Electives
New Applications | 0
Investigations | 30
Emergency Fixes | 3
Application Fixes | 27
Scheduled Modification | 48
Production Support | 18
OnePurdue | 1
Electives | 30
Classification | Housing & Food Services | Porfolio for Housing & Food Services
Non-Electives
New Applications | 0
Investigations | 3
Emergency Fixes | 0
Application Fixes | 5
Scheduled Modification | 3
Production Support | 2
OnePurdue | 0
Electives | 5
Classification | ITaP / ITEA | Porfolio for ITaP / ITEA
Non-Electives
New Applications | 0
Investigations | 3
Emergency Fixes | 0
Application Fixes | 5
Scheduled Modification | 17
Production Support | 5
OnePurdue | 3
Electives | 15
Classification | Physical Facilities | Porfolio for Physical Facilities
Non-Electives
New Applications | 0
Investigations | 0
Emergency Fixes | 0
Application Fixes | 2
Scheduled Modification | 0
Production Support | 0
OnePurdue | 0
Electives | 3
Classification | Student Services | Porfolio for Student Services
Non-Electives
New Applications | 0
Investigations | 14
Emergency Fixes | 2
Application Fixes | 40
Scheduled Modification | 39
Production Support | 3
OnePurdue | 0
Electives | 89
Classification | University Advancement | Porfolio for University Advancement
Non-Electives
New Applications | 0
Investigations | 1
Emergency Fixes | 0
Application Fixes | 12
Scheduled Modification | 31
Production Support | 0
OnePurdue | 0
Electives | 34
Classification | Institutional Research | Porfolio for Institutional Research
Non-Electives
New Applications | 0
Investigations | 0
Emergency Fixes | 0
Application Fixes | 0
Scheduled Modification | 0
Production Support | 0
OnePurdue | 1
Electives | 0

## Glossary of System Names
System | System Name
ACAG | Agriculture Accounting
Advance C/S | Advance C/S
Ariba | Ariba
ASER | Analytical Studies - Effort Reporting
BADR | Bus. Admin. - Dept Reference
BUDG | Budget
BUFC | Faculty Contracts
Bursar | Bursar
Business Intel Arch | Business Intelligence Architecture
CAAC | Sponsored Programs Accounting
CARS | Centralized Accounts Receivable System.
CN | OCEC
COEUS | Sponsored Programs System (MIT)
Data Admin | Data Administration
Data Administration | Data Administration
DFA | Division Financial Aid
DPDS | Data Warehouse
E-Commerce | E-Commerce
EWOTS | Elect. Work Order Transmittal System
Expresslane | Expresslane
External Procedures | External Procedures
FMIS | Financial Management Information System
Housing | Housing Process Support
IDN Data Mart & Metrics | IDN Data Mart & Metrics
Information Quality | Information Quality
INSU | Building Insurance
IVAC | Investments - Cash Magnagement Support
ODS Replication | University Development Operational Data Store Replication
ODS Reporting | University Development Operational Data Store Reporting
ODS Star Refresh | University Development Operational Data Store Star Refresh
PAAC | Adjusting Payroll Charge
PACERS | Purdue Advanced Continuing Education Registration System
PACII | PAC II - Time Entry
PAFX | Flex Benefits
PAIS | Payroll Appointment Information System
PAVE | Vehicle Insurance
PAYR | Payroll
PAYR/PAFX | Payroll/Flex Interface
PAYR/PPWP | Payroll/Work in Process Interface
PEAR | Applicant Retrieval
PESN | Personnel
PESN/PAYR | Personnel/Payroll Interface
PFPA | Parking Services
PFPF | PF - General
PFPM | PF Project Management
PFPR | Parking Services - Permit System
PFTI | Parking Services - Ticket System
PHIR-911 | COMIT - 911 Interface (consulting)
PHON | COMIT - General/Ledger Interface
PPMT | Material Transfer (General/Ledger Transaction entry) System.
PPWP | Work-in-Process Payroll System
PREMIS | Purdue Registration and Event Management Information System
PROP | Property Accounting
PUGA | Demurrage System General/Ledger Interface
PUIB | Incidental Billing System
PUID | Purdue University Identifier
PUPO | Purchasing - Purchase Orders
PUPR | Printing Services G/L Interface Support
Purdue OLTP | University Development Purdue Online Transaction Processing
PUTR | Transportation G/L Interface Support
REGI | Registrar
RFSP | Sponsored Programs Tracking System.
RHAC | Residence Hall Accounting
RHBO | Residence Hall Business Office
RHCA | Access Card Interfaces
RMS | RMS Interfaces
SIAD | Admissions
SIS | Stiudent Information System/Student Information Query/Student Services Information
SLAC | Student Loans
Smartcall | Univeristy Development Smartcall
Standards | Standards
Task Access | The Task System
Task Access/3 Month Plan | Decision Support - Planning
UFUND | United Way
UR Data Warehouse | Housing & Food Servcies Decision Support System (Pending)
WAI | Data Warehouse
WEB - Housing App | WEB - Housing Application
WIPI | Work-in-Process Inquiry System
WIPR | Work-in-Process Reporting System
YREND | Financial Year End Processing
Note on B52: greg1: Time Entry System of WIP time cards.
Note on B55: greg1: Demurrage converted to VB and transferred to PFCS. We support FMIS interface now.