## July
Activities |  | July
| Mon | Tues | Wed | Thurs | Fri
| 1st | 2nd | 3rd | 4th | 5th
Documentation for Phase2 | [5 empty] | B & R
Database Design Research | [5 empty] | B
Website layout & content | [5 empty] | R
Phase 2 submit @ 10am | [5 empty] | B & R
Presentation & prep @ 10am | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 8th | 9th | 10th | 11th | 12th
Database Design Research | [5 empty] | B
Website Development | [5 empty] | R
Database Planning | [5 empty] | B
Testing analysis | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 15th | 16th | 17th | 18th | 19th
Database Design Research | [5 empty] | B
Website Development | [5 empty] | R
Database Planning | [5 empty] | B
Documentation | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 22nd | 23rd | 24th | 25th | 26th
Phase 3 submit | [5 empty] | B & R
Presentation & prep | [5 empty] | B & R
Phase 4 planning | [5 empty] | B & R
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R
| Mon | Tues | Wed
| 29th | 30th | 31st
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R

## August
Activities |  | August
|  |  |  | Thurs | Fri
|  |  |  | 1st | 2nd
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R
User Testing | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 5th | 6th | 7th | 8th | 9th
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R
User Testing | [5 empty] | B & R
User Testing Analysis | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 12th | 13th | 14th | 15th | 16th
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R
User Testing | [5 empty] | B & R
User Testing Analysis | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 19th | 20th | 21st | 22nd | 23rd
Database Development | [5 empty] | B
Website Development | [5 empty] | R
Content Development | [5 empty] | B & R
User Testing | [5 empty] | B & R
User Testing Analysis | [5 empty] | B & R
Documentation | [5 empty] | B & R
Presentation Prep | [5 empty] | B & R
| Mon | Tues | Wed | Thurs | Fri
| 26th | 27th | 28th | 29th | 30th
Phase 4 due | [5 empty] | B & R
Presentation? | [5 empty] | B & R
User Testing | [5 empty] | B & R
Bug Testing | [5 empty] | B & R
Bug Fixing | [5 empty] | B & R

## September
Activities |  | September
| Mon | Tues | Wed | Thurs | Fri
| 2nd | 3rd | 4th | 5th | 6th
User Testing | [5 empty] | B & R
Bug Testing | [5 empty] | B & R
Bug Fixing | [5 empty] | B & R
Major Project Submit | [5 empty] | B & R
Critical Evaluation | [5 empty] | B & R