## Weekly SUS Telecon
Weekly SUS Meeting
Agenda & Summary Notes from November 11, 2003
Every Tuesday at 9am Pacific/Noon Eastern/5pm Glasgow
MEETING AGENDA
1 | Review of action items
2 | Suspension modeling - MATLAB and Mathematica
3
4
5
Attendees
1 | Calum, Russell and Janeen |  |  |  |  | CIT
2 | Caroline, Mike P-L, Mike P., Ken |  |  |  |  | Glasgow
3 | [5 empty] | Standford
4 | Justin, Ian |  |  |  |  | RAL
5 | [5 empty] | MIT
6 | [5 empty] | Florida
7 | Stuart |  |  |  |  | Birmingham
8 | Mark Barton |  |  |  |  | LHO
SUMMARY NOTES AND ACTIONS FROM PREVIOUS MEETINGS
1 | Document Updates
ACTION | M000202 Development Plan |  |  |  |  | Dennis | ASAP | High
ACTION | T000053 Universal SUS DRD |  | Mark is still incorporating comments from Norna |  |  | Mark | 2003-11-18 | High
ACTION | T010007 SUS DRD |  |  |  |  | Mark | 2003-11-18 | High
ACTION | E000037 Configuration Control |  |  |  |  | Dennis | ASAP | High
2 | Structure Resonance Requirements
ACTION | Dennis/Systems to provide direction |  | Dennis summarized his work and his e-mail to Joe G.,Brian Lantz and Ken S.. Dennis will see Joe and Brain next week at the LSC. |  |  | Systems | Oct 1st | High
Norna asked and Dennis agreed that the issue is whether there is colocation or non-colocation of the sensing in the SEI feedback. If there's only local feedback in the corners
(colocated) it's not an issue for modal based feedback, there is a problem. Dennis believes that the SEI group wants to keep modal feedback as an option.
In theory, Dennis says that his report will include options of lower Q/lower 1st mode configurations but he believes that this will be difficult.
3 | Catcher Product Design Specification - more feedback?
Calum has feedback on catcher which he will forward to Russell.
There is a telecon with Betsy, Russell, Calum and Janeen tomorrow at 8am. Please e-mail Janeen if you'd like to be included.
ACTION | Please respond to Russell - even with an "OK" or "no comment" |  |  |  |  | All | Oct 7th | Medium
4 | David's e-mail SUS Questions - see Daylinks.
http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/Davids_email_SUS_questions.pdf
| 1) Damping approach for the mode cleaner |  | Ken's paper T030241-00
DECISION | Leave all global osems at test mass and penultimate mass for MC prototype.
2) Actual hanging mass for all suspensions
ACTION | Dennis will finalize by Oct 1st the seismic payload which will include contingency. |  |  |  |  | Dennis/SEI | Oct 1st | High
4) LASTI Controls prototype test plan
ACTION | Janeen will work with Mark and provide a preliminary test plan by the end of October |  |  | Mark will distribute this soon. |  | Janeen/Mark | Oct 31st | Medium
5 | Optical Layout
Althought Luke is not here, Dave R. talked about the request to make the MMT2 250mm as opposed to 314mm. Dave said that there are two issues. The first is
clipping. The clipping is about 80ppm. The other issue is boresighting down the arms with a smaller MMT mirror. A smaller MMT loses the flexibility of moving around the beam a lot.
Janeen said that this needs to be know in about a year. If it is a big departure from an LOS1, we need to add design time into the schedule.
6 | Optics Layout - | Luke is still out. Table till next week.
7 | Calum's e-mail issues
c) creep test - dimensional change or microslip events. Yes, the concern is microslip events. Mark used what amounted to a microphone for creep tests he did with Joe Giaime.
Justin reported that when he'd spoken with Riccardo, who said that creep is usually reduced if you stress the wire and heat it to 100 deg or so.
Jim said that one should heat the wire and pre-stretch it. Ken reported that Virgo uses maraging steel wire that is formed by machining out of rod. It's inconvenient to use. Geppo
has a paper that compares the thermal noise. The Qs are very high. Justin said that Riccardo reports that you get significantly higher strength if you heat treat for a long period of time.
David suggests a meeting with Riccardo. After the meeting, adopt a plan. The plan should allow for folding in new ideas.
ACTION | Calum/Janeen will set up a meeting on maraging steel with Riccardo and adopt a plan. |  |  |  | Dec 2nd at SUS telecon | Janeen/Calum | 2003-11-30 | Medium
8 | Length of quads and their proposed installation at LASTI
The SEI group will design to 210.5cm with the option of going to 200.5cm.
ACTION | Norna will look at the shorter ITM and ETM. |  |  |  |  | Norna | 2003-02-01 | Medium
ACTION | There was agreement that the conceptual design for the quad shall be made up of 2 parts, a top and a bottom, which may be installed separately.
ACTION | The suspension team will have a more advanced design on aspects of the quad that matter to the SUS team by Feb 1st |  |  |  |  | SUS Team | 2003-02-01 | Medium
9 | Controls Prototype Coils
Russell went over his document T030257-00 on the coils and spares needed for the controls prototypes. There was agreement with the quantity of 72. Russell will check
with Ken and start ordering them. Janeen will order more, thicker insulated QML wire from MWS for them. Russell will order 72 total but will order them in batches.
The coils will be wound near Caltech. Dennis cautioned that when Larry had the Pasadena
company wind some coils they were slow, but the coils used square cross section wire and polyimide paint. The part didn't look good either, had a crease it it.
Dennis also mentioned that the RGA scan for the polyimide paint was barely acceptable for initial LIGO. He's going to do a more detailed analysis to determine if it's usable
for advanced LIGO. At first blush he believes it will not be.
It is agreed that additional machining for the brackets will be done at CIT. CIT will make the Macor and Teflon spacers. The quantity includes in process and shelf spares.
Doug asks that shelf spares be assembled with their brackets and pigtails and such. Helena believes that with the thicker insulated wire and her oversight of Bob Taylor's
| assembly work, that there will not be a problem with shorts. |  |  | All the drawings have been checked by Calum and Larry Jones.
Russell got an OK from Ken. He's waiting for responses from his RFQs.
10 | Blade Matching | See Justin's email from Oct 29th
ACTION | Send Mark any valuable blade parameters and their assumed values. He will collect and release this data. |  |  |  |  | SUS Team | 2003-11-11 | High
Although Norna couldn't be here today it seemed to make sense to go forward on this discussion. Justin asked if everyone agreed that there are essentially two
kinds of errors - the wrong spring constant and that the tips are in the wrong place. There was agreement. So, what kinds of errors are these?
Also, what effect do these errors produce. He assumed cross couplings of isolation and noise
and the effects these errors have on global and local controls. Ken said they're similarly problematic. Mark's analysis should produce results about the cross couplings.
Justin agreed to Calum's query that this is all about cost. Calum said that for GEO, the blade costs reduce dramatically the more one asks for.
Calum and Mike P. feel that this is due to tooling costs, learning curve and quantity.
ACTION | Calum and Mike P. have agreed to provide Justin some history of the cost of the GEO blades |  |  |  |  | Calum & Mike P. | 2003-12-31 | Medium
ACTION | Mark will provide the calculations that Justin asked for in his e-mail on Oct 29th |  |  |  |  | Mark | 2003-12-31 | Medium
SUMMARY NOTES AND ACTIONS FROM THIS MEETING
11 | Suspension Modeling - MATLAB and Mathematica
a) Function "Opt.m" in the MATLAB files? - CIT, MB,NAR
b) Quad parameter file to Mark to run through Mathematica code - CIT,MB
c)Reivew of requests from Helena's meeting on modeling team - CIT,NAR
It was agreed to send MATLAB zip files to the DCC via Linda Turner. Just include in the submittal e-mail "DO NOT UNZIP". She puts them into a folder. Include a comments
page about why the release is being made and what we hope gets done with it. Mark suggests getting an E number for a description page with baseline info.
They'll do two separate releases - MATLAB and Simulink. Mark will send the Simulink portion around for review. Calum reminds that everyone should be using MATLAB version 6.5
and Simulink version 13 or 13.01. All input info wasn't in the input file - any numbers that could change. Ken said it probably bears looking at. For the springs, one is interested in the
mechanical stiffness, so he can make the parameter the uncoupled frequency divided by the mass. Mark would like to adjust the Mathematica program a bit, I.e. various limits
and step sizes. So, by the time he does a systematic release of MATLAB, he'd like to have a Mathematica file to go with it. Foks seemed to agree that making these changes
makes sense to do now and wait on doing Justin's analysis.
Mark will release Norna's new conceptual design info, produce a parameter file, remove 90% of spring stuff and put in a spring parameter that comes from the uncoupled
frequency data, and then fold that into his MATLAB. So, Calum will update the conceptual design data and release that.
Mark suggests just sending it to him and he'll work it into his tidied-up MATLAB work.
Agenda items for next meeting, November 18, 2003
1) Review of action items
2)Optical Layout - Luke
3) Suspension modeling - MATLAB & Mathematica