## Action Plan
| 11/11-11/18 | 11/19-11/24 | 11/25-12/1 | 12/2-12/8 | 12/9-12/15 | 12/16-12/22 | 12/23-1/29 | 12/30-1/5 | 1/6-1/12 | 1/13-1/19 | 1/20-1/26 | 1/27-2/2 | 2/3-2/9 | 2/10-2/16 | 2/17-2/23 | 2/24-2/28 | 3/1+ (during and after conference)
Agenda |  |  |  |  | scope out possible protest targets for action | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | plan out SEAC meeting time and rough agenda; come up with action ideas |  |  |  | plan materials for action; solicit agenda ideas for SEAC meeting time | plan out fun time and open-mike ideas | designate facilitators for SEAC meeting time, caucuses & alt. groups | plan/print materials for SEAC meeting time
Presenters |  |  | pick 80% of workshop topics; start lining up presenters |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  |  | 100% of speakers confirmed | get info on A/V and transport needs of speakers to host |  | follow up to ensure that speakers have directions, time of their workshops & figure out their housing needs |  |  | send thank you notes to workshop presenters; pay those who need to be paid and get kick-backs from those who owe them
Phone Outreach |  |  | get 5 state/area coordinators designated; do targeted outreach to state schools | get phone lists to coordinators | get 5 more coordinators | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  | get 5 more coordinators (15 total); make sure that all areas accounted for; follow up; get tally to hosts; goal: 50 schools contacted |  | follow up; get tally to hosts; goal: 100 schools contacted | follow up; get tally to hosts; goal: 200 schools contacted; 50 confirmed | follow up; get tally to hosts; goal: 300 schools contacted; 100 confirmed | follow up; get tally to hosts; goal: 400 schools contacted; 200 confirmed | call through confirmed lists; follow up; get tally to hosts
Field Organizing | get free state maps for states in region from someone with a AAA membership; make a very basic postcard/flyer announcing the event | get database of all colleges in the region from the SEAC office; buy colored dot stickers; copy and bring flyers to SOA protests | map the colleges with the colored dots; laminate it when done |  | distribute the maps to state coordinators | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | have coordinators / field organizers start calling the main campuses/communities you hope to recruit from and get themselves set up with appointments to visit the campus and promote the conference to their groups | visit some campuses to get people excited about the conference | promote conference at National Conference on Organized Resistance in DC; visit some campuses to get people excited about the conference | visit some campuses to get people excited about the conference | visit some campuses to get people excited about the conference | visit some campuses to get people excited about the conference | visit some campuses to get people excited about the conference
Web | ask SEAC Office to have event added to the SEAC web calendar |  | ask SEAC National folks to start a crude webpage for the conference (or make your own) |  | set up the website with a registration form that forwards info to conference planners and the appropriate regional/state/area coordinators and travel coordinators | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | get the website registered on various activist calendars (like campusactivism.org) | get directions & teasers on web | get crude agenda on website |  | get contact info from registration forms to those doing the phone outreach | put cell phone number of conference organizers on the site so that people coming last minute can reach you | get contact info from registration forms to those doing the phone outreach |  | take down websites
Email | email an initial announcement to the SEAC regional list and ask for people to get involved in the planning, if they're interested | brainstorm a list of lists (regional ones; national ones on particular issues, etc.) where the conference can be advertized | do a preliminary mass email to SEAC database contacts in the region and any other contacts/lists |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | do a preliminary mass email to SEAC database contacts in the region and any other contacts/lists; point people to the website and ask them to register |  |  | do another mass email | ask workshop presenters to forward the conference announcement to their networks (particularly ones related to the topic they're teaching) |  | do another mass email | special mass email to those who registered and to workshop presenters | clean out database of bad addresses
Mass Mailings |  | mail postcards to the good addresses in SEAC National (and regional?) databases and any others you can think of |  |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  | design a 1-2 page mailing with registration form, directions, agenda, etc. | mail the mailing to database contacts plus webform registrants and any new contacts from phone outreach | [5 empty] | clean out database of bad addresses
PR / Media | brainstorm list of places to advertise | contact the publications that might need early notice (monthly/quarterly magazines & newsletters) |  |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  |  |  | invite other cool groups to have info tables | PSAs on local radio stations | letters to the editor of local press | do advance press work on action | do press work on action | clip news and tape other media on action
$ Money |  | find a way to fund state/area coordinator phone calls (phone card donations?) | open a bank account, if needed |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | see if $$ will be available to help fund vans or other transportation costs for attendees | figure out who people can write checks to (mention this on website and in mailing) | [6 empty] | get $$ situation straightened out
Food | Does food have to be done through a monopoly provider on campus? |  |  |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | plan a (vegan!) menu | ask for food donations | ask for food donations | ask for food donations |  | figure out food composting situation | confirm cooking helpers | buy & get food on-site; get helpers from the conference to aid in cooking | clean up
Housing |  | seek out mass housing that is close to conference activities |  |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  |  |  | ensure that housing meets projected attendence | ensure that housing meets projected attendence | ensure that housing meets projected attendence | ensure that housing meets projected attendence | ensure that housing meets projected attendence | thank the hosts
Travel | [5 empty] | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK | get directions (flying and public transit as well) on website and in mailing | ask people to start reserving vans from major student populations |  | scope out how many areas will have/need vans | travel coordination | travel coordination | travel coordination | travel coordination; assign tasks for picking up speakers and others who need shuttling | make sure everyone has a way to get home
Logistics | make list of possible conference hosting sites | look into availability of various sites; check for scheduling conflicts | reserve rooms, general conference gathering spaces and food preparation and eating locations |  |  | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  |  |  |  | request sound system for open-mike & other A/V needs; get videocameras reserved if possible for taping workshops; speakers & action; buy videotapes | plan out registration packet materials; get a message board (butcher paper, chalkboard or dry erase) and markers/chalk | get non-disposable name tags; follow up on A/V requests; put someone local in charge of misc logistics | assemble registration packets; organize registration table (forms; laptop; etc.); bring materials from SEAC office for SEAC lit table; map out where workshops will be | make sure registration info gets entered into regional and national databases
On-Campus Outreach | [5 empty] | HOLIDAY BREAK | HOLIDAY BREAK | HOLIDAY BREAK |  |  |  | ask cool teachers to offer credit for going to conf. |  | make sure event is listed in campus newspaper calendar | get flyers up on campus; get the campus and community newspapers to run an article leading up to the conference (and printing the agenda or conference website, if possible) | chalk boards of classrooms; do raps at the beginning of classes of cool profs.