## Hárok1
Action plan "Market research" Attachment No.4
2002
| June | July |  | August |  | September |  | October
Activity | 3-4.week | 1-2.week | 3-4.week | 1-2.week | 3-4.week | 1-2.week | 3-4.week | 1- 2.week | 3-4.week
preparation of the project | x
preparation of questionnaire in printed form | x
preparation of questionnaire in e-form | x
preparation of questions for phone research |  | x
proposal of software for database of firms |  |  | x | x
pre-reasearch |  | x
distribution of questionnaires into the regions |  | x
distribution to respondents |  | x
handing back of quiesionnaires |  |  |  |  | x
elaboration of results | [5 empty] | x | x
phone research | [6 empty] | x
filling of database of firms | [5 empty] | x | x
testing of database | [7 empty] | x
formation of the final report | [7 empty] | x
graphic elaboration of the final report | [7 empty] | x
finance accounting | [8 empty] | x
proposal of recommendations to the end of 2002 | [8 empty] | x
proposal of recommendations for 2003 | [8 empty] | x