## Planning
UHS Release Planning - PeopleSoft Production Environment
[5 empty] | Current Environment |  |  |  | Future Changes
UHS Release | Tech Category | Vendor / Product | Owner | Exhibit | Version # | Service Packs | Patches | Last Change | UHS Release | Description of Change | Version # | Service Packs | Patches | Estimated Release Date
1.2 | 3rd Party Tools | Ad Astra Room Scheduling | Sosa,Lupe |  | 5.0
1.2 | 3rd Party Tools | CyberSource Web Credit Card Processor | Sosa,Lupe |  | 3.2.4.2
1.2 | 3rd Party Tools | Encore Service Mgr (IVR) | Sosa,Lupe |  | 6.2
1.2 | 3rd Party Tools | First Logic Postal Soft | Webb,Steve |  | 1.22a
1.2 | 3rd Party Tools | FirstQuery (IVR) | Sosa,Lupe |  | 6.2
1.2 | 3rd Party Tools | MicroFocus COBOL Net Express | Sosa,Lupe |  | 3.0
1.2 | 3rd Party Tools | PeopleLink (IVR) | Sosa,Lupe |  | 7.6
1.2 | 3rd Party Tools | PS Interface IVR software | Sosa,Lupe |  | 1.3.1
1.2 | 3rd Party Tools | ASG Report.Web | Martin,Keith |  | 1.2 |  |  | 2001-11-04
1.2 | 3rd Party Tools | ROAM (IVR) | Sosa,Lupe |  | 6.2
1.2 | 3rd Party Tools | Sterling Commerce GenTrans | Sosa,Lupe |  | 3.1
------ | 3rd Party Tools | Sun Instant Image | Moroney,Dennis | [5 empty] | TBA | Implement Instant Image | 2.0 |  |  | TBA
1.2 | 3rd Party Tools | Veritas File System | Moroney,Dennis |  | 3.3.3
1.2 | 3rd Party Tools | Veritas NetBackup | Moroney,Dennis |  | 3.2 |  | 108261-01 03/28/01
1.2 | 3rd Party Tools | Veritas Volume Mgr | Moroney,Dennis |  | 3.0.4
1.2 | 3rd Party Tools | WebAuthorize | Sosa,Lupe |  | 1.3.1
1.2 | Application Tools | BEA System Tuxedo | Sosa,Lupe |  | 6.5
1.2 | Application Tools | PeopleTools FS | Sosa,Lupe |  | 7.6 |  |  |  | 1.3 | Upgrade on FS | 7.61.09 |  |  | 2001-11-24
1.2 | Application Tools | PeopleTools SA | Sosa,Lupe |  | 7.61.09 |  |  | 2001-10-21
1.2 | Application Tools | PS Folio | Chern,Jonathan |  | 4.1
1.2 | Application Tools | PS Launcher | Chern,Jonathan |  | 1.52 |  |  | 2001-10-21
1.2 | Application Tools | PS n/Vision | Sosa,Lupe |  | 7.6
1.2 | Application Tools | Seagate Crystal Reports | Chern,Jonathan |  | 6.0.1
1.2 | Application Tools | SQA Robot | Sosa,Lupe |  | 7.5
1.2 | Application Tools | SQR | Sosa,Lupe |  | 4.3.4
1.2 | Database | Embarcadero Change Manager | Kumar,Jitender |  | 1.3
1.2 | Database | Embarcadero DBArtisian | Kumar,Jitender |  | 5.4
1.2 | Database | Embarcadero ER Modeler | Kumar,Jitender |  | 4.2.2
1.2 | Database | Oracle | Kumar,Jitender |  | 8.1.6.0 |  |  |  | TBA | Database Upgrade | 8.1.7.0 |  |  | TBA
1.2 | Financials | FAST mods library | Ness,Craig |  | 1.0
1.2 | Financials | ES mods library | Martin,Keith |  | N/A
1.2 | Financials | PeopleSoft | Ness,Craig |  | 7.51 | 1 | 2001-02-28 |  | 1.3 | Service Pack 2 | 7.52 | 2 |  | 2001-11-24
1.2 | Hardware | Compaq | Chern,Jonathan | H-2 | 1.0
1.2 | Hardware | Sun | Moroney,Dennis | H-1 | 1.0
1.2 | HRMS | FAST mods library | Bogrand,Jenine |  | 1.0
1.2 | HRMS | ES mods library | Lovelady,Mike |  | N/A
1.2 | HRMS | PeopleSoft | Bogrand,Jenine |  | 7.6 |  | 2001-08-15 | 2001-10-21 | 1.4 | Patch Migration | 7.6 |  | 2001-10-15 | 2001-12-09
1.2 | Servers - OS | MicroSoft Windows | Chern,Jonathan |  | 2000 | ???
1.2 | Servers - OS | Sun - Cluster | Moroney,Dennis |  | 2.2
1.2 | Servers - OS | Sun - Raid Manager | Moroney,Dennis |  | 6.22
1.2 | Servers - OS | Sun - Remote Services | Moroney,Dennis |  | 2.1
1.2 | Servers - OS | Sun - Solaris UNIX | Moroney,Dennis |  | 2.6 |  | 2001-06-01
1.2 | Servers - OS | Sun - Workshop | Moroney,Dennis |  | 5.0
1.2 | Student Admin | FAST mods library | Banks,Darella |  | 1.0
1.2 | Student Admin | ES mods library | Webb,Steve |  | N/A
1.2 | Student Admin | PeopleSoft | Banks,Darella |  | 7.6 |  | 2001-08-15 | 2001-10-21 | 1.4 | Patch Migration | 7.6 |  | 2001-10-15 | 2001-12-09
1.2 | UH LAN/WAN | UH | DeWees,Robert | N-H | 1.0
1.2 | UHCL LAN/WAN | UHCL | DeWees,Robert | N-C | 1.0
1.2 | UHD LAN/WAN | UHD | DeWees,Robert | N-D | 1.0
1.2 | UHV LAN/WAN | UHV | DeWees,Robert | N-V | 1.0
------ | VPN | TBA | DeWees,Robert | [5 empty] | TBA | Implement VPN | TBA |  |  | TBA
|  |  | History: | 1.2 | 2001-11-04 |  |  |  |  | Last updated: | 2001-11-06
|  |  |  | 1.1 | 2001-10-21 |  |  |  |  | by the Change Management Committee
|  |  |  | 1.0 | 2001-09-01