## Sheet1
World Bank/OECD/CDE Joint Project on Statistical Capacity Building at Subnational Level
|  |  | 1 month | 2 month | 3 month | 4 month | 5 month | 6 month | 7 month | 8 month | 9 month | 10 month | 11 month | 12 month | 13 month | 14 month | 15 month | 16 month | 17 month | 18 month
Activity
Stage 1. Start-up Activities
Creating a Working Group with the task of coordinating and implementing the Action Plan
Determine the members of the Working Group
Sending invitations to be a member of the Working Group
Developing and approving regulations of the Working Group
Creating the Subnational Information Consulting Center on the basis of ICPS with the task of supporting Action Plan implementation
Планування робіт. Навчання |  | Determining and approving criteria for selecting pilot oblasts, rayons and cities
Планування робіт. Навчання |  | Selecting pilot oblasts and pilot rayons and cities within these oblasts
Preparing a stage report for the Working Group
Stage 2. Trainings and joint seminars for data users and producers
Joint seminar for key users and producers of subnational data to present the Action Plan on Subnational Statistics Development and polling program
Trainings for the staff of regional and local government agencies
Development and elaboration of a training program for regional and local data users
Forming a group of lecturers for the trainings
Conducting “trainings for trainers” seminars
Forming groups of students consisting from the staff of regional and local government agencies (pilot oblasts, rayons and cities)
Conducting a series of seminars for users of regional and local data
Trainings for data producers
Development and elaboration of a data producing methodology training program for data producers
Forming a group of lecturers for the trainings
Conducting “trainings for trainers”
Forming groups of students consisting from the staff of the State Statistics Committee and producers of administrative information
Conducting a series of seminars for producers of regional and local data on the methodology of producing indicators determined after the polling of users of regional and local data
Joint seminars for users and producers of regional and local data
| Групи | Determining the topics for joint seminars
Conducting joint seminars
Conducting independent research
Preparing a stage report for the Working Group
Stage 3. Data inventory and determining the needs of data users
Inventory of available data
Approving the final list of institutions and organizations producing administrative data that are subject to inventory
Preparing and sending requests about data produced by organizations and institutions
| Групи | Processing of responses and preparing a register of available data
Polling
Preparing the questionnaire
Sending the questionnaires
Processing of questionnaires and setting priorities
Preparing a stage report for the Working Group
Stage 4. Creating a subnational statistics database
Determining the list of data required by key users
| Групи | Determining available resources of the State Statistics Committee with the view of satisfying the users’ needs
Developing a methodology for gathering the data that is required by key users but is not produced by statistical bodies or appropriate agencies
Stopping producing indicators that are in little demand
Reorienting freed resources to producing indicators that are required
Determining other sources of information
Defining mechanisms of providing this information to users
Creating a regional information database on the basis of economic departments of oblast state administrations
Preparing a stage report for the Working Group
Групи
Stage 5. Adopting and approval
Develop a procedure for presenting information on the basis of three pilot oblasts, rayons and cities
Preparing a legislative approval of the information exchange procedure
Aprobation of adopted regulaiton of data producing and exchange
Preparing a stage report for the Working Group
Групи
Супроводжує роботу груп,
надає консультації правового характеру