## Goal A
A. Develop innovative measures to reduce costs and redirect resources for the best results.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Administration
Have purchase of service (POS) agencies comply with 15% admin ceiling | The department established a 15% administrative cost ceiling. 2002 was a phase in period to allow agencies some latitude in bringing the exceptionally high costs down. | To bring down the administrative costs per program per provider to the 15% admin ceiling | •Develop contract compliance database •Send out reports, notifications, and letters to all POS agencies notifying them of admin ceiling status •Identify exemptions to admin ceiling •Administer review process •Have quality improvement (QI) group meet monthly to assess issues and track progress | 90% of purchase of service agencies at or below the 15% administrative ceiling | Edjuana Ogden, QI Group, G.P. Foster

## Goal B
B. Assess performance and cost-effectiveness of services; and improve quality in those areas where quality measures are established.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Administration
Provide timely, accurate, integrated fiscal information to DCDHS Administration, Program Management, Accounting and Budget of the developmental disabilities SDS System. | Various systems have been functioning independently and without coordination. A review of the systems is being performed to determine how they are interrelated and to verify their effectiveness. | Integrated financial systems (program allocation, accounting, auditing and budget) to provide timely and accurate budget control. | •Document the current service, financial, and budget management operating systems. •Test the operating system for compliance with management assumptions •Develop a set of recommended changes to current system. •Gain approval for proposed modifications. •Design new and/or modifications to existing systems and supporting materials. •Train staff in use of system changes and materials •Implement changes •Monitor system as modified for compliance. | •System documentation is completed •Administration/program management receives consistent and accurate financial reports. •Budget variances are eliminated. •Collect baseline data on number of days required for client enrollment and payment system entry. | Fiscal Services Manager, Sandy Bennett
Health Insurance Portability and Accountability Act (HIPAA) | Oversight Committee that includes staff from all divisions has been formed. Basic information has been shared with staff. Detailed impact of this law on each system is not known at this time. This law impacts not only DCDHS but other County departments as well. | 100% compliance with the privacy rule by established effective date: April 14, 2003. 100% compliance with Transaction by established effective date: October 16, 2003. | •Maintain contact with State DHFS to obtain updated information on systems affected by this law. •Modify intake processes to incorporate HIPAA compliant forms. •Create a plan to capture HIPAA compliant information for all existing consumers. •Complete gap analysis for the privacy rule. •Complete a systems gap analysis for our electronic data-bases and reprogram where necessary. •Submit a request for extension for the transaction rule by October 15, 2002. •Establish a privacy officer. | •Systems in compliance with the privacy rule by April 14, 2003. •Systems in compliance with the transaction rule by October 16, 2003 | Oversight Committee
Fiscal and Management Services (FMS) division reorganization | The reorganization of the FMS division has been approved by the Department of Administration (DOA). Two key positions approved in the reorganization are vacant. The redirecting of staff time and workflow have not yet occurred. | Complete the approved reorganization and fill vacancies. We will reduce the three accountants time (two to 0.75 FTE and one to 0.50 FTE) | •Hire vacant positions as soon as the freeze is lifted and to develop workflow analysis to equitably distribute work capacity. | •Have new full-time staff on board and functioning in key positions. implementation of new workflow process that incorporates reduced accountants’ time. | G.P. Foster, Fiscal Services Manager & FMS Staff
Intranet Development (DCINet) | We are in early development, not much done from HSD vantagepoint | •To have a clearly developed Intranet strategy. •50% of the documents that have department-wide appeal on the DCInet by year’s end. •Have each division identify documents that could be deployed via DCInet and post 30% to DCInet by year’s end | •Develop intra-departmental DCInet team. • Identify business process or products for Intranet deployment. •Create Intranet policies and procedures. •Develop business process | •Business processes developed •50% of documents that have department-wide appeal on DCInet. •30% of documents identified by divisions on DCInet | FMS staff and David Carlson
Contract compliance database development | The department collects data from the POS agencies in a primarily paper format. The data is stored in folders in file cabinets. There is no central repository of the data. | To develop a contract compliance database that will capture expense summary report data, personnel schedules, and budget reports data. | •Identify needs to be met by the system (project scope) •Identify reports to be generated by the database •Identify users of the system •Build structure with DOA to meet electronic reporting needs | •Contract compliance data housed electronically in a single database •All financial data captured in a single database | Edjuana Ogden
Electronic Reporting by POS Providers | The Purchase of Service (POS) agencies report to the county primarily on paper. This reporting includes financial data, output data, outcome measures or performance indicators, along with data to be reported to the State. | To develop the internal capabilities to receive electronic reports from POS agencies. | •Develop business rules •Modify or develop software to capture data •Test for accuracy of data and ease of reporting •Phase-in modules - target financial data to roll out first | •Electronic reporting capability in place by December 31, 2003 •Electronic reporting of financial data by POS. | Edjuana Ogden & Ken Baun
Develop a POS audit plan and implement the audit plan (desk or field) | POS agencies are required by contract to have an external financial audit done annually. Departmental audit still needed. Departmental audits/reviews of purchase of service agencies are rarely conducted. | To develop a departmental audit plan and annually perform financial compliance audits on 7% of the purchase of service agencies | Collaborate with internal staff, State, and external auditors on development of plan to include the following •Determine most appropriate tests to be performed •Focus efforts in right areas as not to duplicate work performed by external auditors •Determine what services can be done by internal staff verses those that can be done by external staff •Develop working document for staff use when completing monitoring process. Explore other resources to bridge the gap | •Audit plan developed – October 2002 •Audits performed on 7% of POS contracts or contracted programs | Edjuana Ogden
Budget database development | The department develops several financial documents to prepare, monitor, and analyze the annual budget. These documents are paper stand-alone documents. They are compiled and entered into a series of spreadsheets that have to be linked together to produce a budget document. | To complete the budget database that will provide a common repository for key staff to enter budget data and to discontinue the use of multiple spreadsheets. | •Complete the current database project in Access database •Lay out plans to roll the budget database into the information system | •Database deployed •Staff trained on the system | Ken Baun, Edjuana Ogden, G.P. Foster
Outome Measures | •CYF - four broad outcomes have been identified across most services - AODA programs have State established outcome measures •EA - performance based contracting with State •ACS - identified 2 primary outcome measures, performance measures currently in development. State has identified a consumer data set in the Mental Health area that has some outcome measures and is to be utilized by all counties. | Short-term: In 2003, in the AODA and Mental Health areas produce baseline reports. Long-term: Have performance measures be one tool to use in evaluating the performance of the Department and associated providers in delivering consumer services. | •Develop a phased (multi-year) approach to implementing performance based contracting for purchased services. •Establish an oversight committee to assure an integrated approach across the Department; •Provide training in outcome measures to all stakeholders; •Develop a repository for the data collection; •Identify resources for the analysis of the data; •Collect baseline data and refine acceptable performance levels and review processes. •Centralize consumer satisfaction surveys within the Department •Department must continue to make substantial investments in infrastructure necessary to monitor and track the fiscal and outcome data. | •Report baseline data for AODA and Mental Health programs, 2003. •When the Department is able to annually produce reports on outcomes across the identified service areas (long-term). | Jean Kuehn, 2003

## Goal C
C. Become a more culturally competent agency to meet the needs of diverse consumer populations.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Administration
Limited English Proficiency | The department currently has a number of bi-lingual/bicultural positions. We are aware however, that the best way to meet our LEP requirements is to expand the number of bi-lingual/bicultural staff in each division that work directly with customers or with the public. | Expand the number of bi-lingual/bicultural positions within the department. | Identify the number of additional bi-lingual/bicultural staff needed to meet existing needs. Redeploy vacancies in specific classifications to bi-lingual/bicultural classification and recruit to fill. Develop specialized recruitment plans to fill positions. | When the identified number of needed bi-lingual/bicultural positions has been filled. | Brenda Brown and division managers
Cultural Competency | CYF Division currently consists of 14 minority social workers out of 111 SW FTE. Current recruitment efforts typically yield few or no minority candidates. Need to develop specific recruitment strategies to improve minority recruitment. The ACS division has very little turnover in staff ACS positions are terminal positions and are highly sought after in the market. This has greatly impeded minority recruitment. | Develop improve minority recruitment strategy. Develop a Grow Your Own Minority Program in ACS and create minority internship program in the DD program or other ACS area. | Initiate/strengthen contacts with UW System and historically minority institutions and identify potential candidates. Involve current staff and staff from other agencies to develop improved recruitment strategies. Work with Human Resources and Office of Equal Opportunity to develop plan. Conduct specialized recruitments. Develop a Grown Your Own Model Program and request LTE dollars in the 2003 budget earmarked for minority intern program. | Minority recruitment has yielded at least a 5% increase in the number of minority staff in the CYF Division. An increase in the number of minority professionals in the ACS division. | Brenda Brown, Lynn Green, OEO Brenda Brown and Fran Genter

## Goal D
D. Promote with other community partners effective state of the art prevention and early intervention strategies for individuals and families.
Develop strategies to, wherever possible, leverage private funding to support these strategies.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)

## Goal E
E. Develop targeted legislative initiatives to increase sustainable funding streams.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Administration
Increase department participation in legislative affairs. | Divisions and individuals are involved in the legislative process on an issue by issue basis. | Legislative affairs will take on a greater emphasis with a department-wide review of legislative strategies and priorities. | Form a DCDHS legislative committee which will: 1. develop a legislative outreach plan, 2. be responsible for assisting development of the department legislative agenda and 3. review legislative proposals/rules that are introduced or proposed. | •Committee will develop an outreach plan with specific activities and initiatives to raise awareness with key legislators of key funding streams and programs. Committee will help develop department legislative agenda. •Legislative tracking system will be developed. | DCDHS Communications Manager will develop the legislative tracking system and will chair the legislative committee, which should be selected by July 1, 2002.
Development of strategic legislative partnerships with other human services groups to secure increases in Birth to Three, Youth Aids, IGT, Community Aids and Economic Assistance funding. | We regularly work with a variety of groups on issues of mutual interest. | Join with these groups to develop a shared legislative agenda that could be presented in a unified manner to raise the visibility and impact of the agenda with legislators and the governor. | Facilitate gathering(s) of key human services advocacy groups and associations as well as officials from other counties to identify common issues of concern and opportunities for cooperation. | Meetings will result in development of a shared human services agenda for action in the 2003-2005 biennial budget and other legislative action that will result in increases in these key funding areas. | DCDHS Communications Manager and Dane County lobbyist will organize and arrange for facilitation of the meeting(s). Initial meetings have already taken place. Other meetings will continue through the completion of the 2003-2005 state biennial budget process.
MA-Waiver funding. | State proposals for MA Waiver rate increases do not address significant local efforts in overmatch and locally funded slots in the CIP 1B program. | Future proposals for MA-Waiver funding increases should include a method of allocating funds which takes into account local efforts. | Work with DHFS, other counties, associations and advocacy groups to develop a proposal that makes desired changes in the MA Waiver funding system. | The plan will be proposed by DHFS and will be included in the Governor’s proposed 2003-2005 biennial budget. | Informal work group has been formed and meetings have begun. Work will continue through the completion of the 2003-2005 state biennial budget process.

## Goal F
F. Attract, develop and retain effective, committed and competent staff at all levels of the department.
Initiative Area | Current Status | Chosen Target | Tactics to Close the Gap | Measures of Success | Lead Staff Responsible
| (Where are we now?) | (Where do we want to be?) | (How do we get there?) | (How will we know we're there?) | (Who? By when?)
Administration
Attract, develop and retain effective, committed and competent staff at all levels of the department. - | For many years, the Department has employed numerous recruitment strategies to attract qualified and competent professionals and to expand the diversity of the department. These efforts have been successful.Diversity has expanded from 4% in 1990 to over 13.5% in 2002. The department would like to expand in these areas and to address emerging employment trends. Divisions have developed individual training plans to increase staff core competencies but this effort is in grave jeopardy due to a 60% reduction in training lines. | Retain and or expand professional development opportunities in the department. | Develop/retain and also expand professional development in the department. Many require train the trainer models or the use of in-house professionals to serve as trainers | •No decline in professional development opportunities. Expand opportunities where possible. •Develop 3-5 professional development strategies through innovative and cost effective measures to provide training in best practices. | Department team appointed by the Director.
| Retention is good to excellent for most of our classifications. However, with a changing global and local economy, a changing client base and a predicted future of significant turnover in personnel due to babyboomer retirements this may change in the near future. Presently 245 or 40.36% of department staff are 49 years of age or older | Department Head Position - Although the County has been successful in recruiting competent Human Services Department Heads retention has been very poor. This has had a negative impact on the department. The department is in need of consistent leadership Given the number of upcoming retirements, the department needs to plan for its future workforce, moving from a babyboomer workforce to a new millenium workforce. | Request County Executive and Employee Relations to do a job analysis of the Human Services Department Head position to improve the retention rate and provide consistency and leadership for the department staff and the human services system. Review and analyze retirement trends and develop a department recruitment plan for new a worker that has a special emphasis on minority recruitment. Research information on the new millenium worker and provide training for managers. Focus on best practices for supervisory and middle managers on how to develop and retain a competent work force. | Job analysis completed and changes implemented. Recruitment plan has been completed and managers have been trained on aspects of working with new millennium workers | Susan Crowley Brenda Brown
| In the recent past, government employment was a desirable profession but this is being eroded. Government employees are under attack, viewed as non-productive and over-paid, which has lead to low morale. Good benefit and wage packages were previously a draw for professionals but due to funding cuts benefit packages will start to erode which will make government a less attractive place to work. Current budget cutting mechanisms seem to all focus on employees, which decrease morale and commitment. | Nurture positive morale among county staff. Recognize outstanding employee contributions; publicly acknowledge county staff role in providing critical services to our community. Reward excellent employee performance. Public communication. | Review, analyze and develop employee performance and reward program. Develop monthly press success stories and share with the press and the County Board. | Program has been developed and implemented. Monthly press success stories shared with press and with the County Board. | Brenda Brown and department team. August 15, 2002. David Carlson and Department Management Team
| Also need to address the lack of promotional opportunities in the department. Traditionally workers have felt uninformed and powerless related to their position and work. Department workers have consistently requested to be kept better informed about the “state of the state”. | Provide incentives for career advancement, particularly at the top management level. Reexamine the fiscal disincentives for staff to convert to contract positions. Improve communication to Department staff. | Look at recruitment strategies for middle to top-level management positions and create internal advancement opportunities. Department head will write a monthly news report to staff explaining the “state of the state.” | Develop recruitment strategy to earmark positions that will only be open for internal promotion. Look at contract management positions and remove disincentives to apply. Monthly “state of the state” newsletters are issued consistently on a monthly | Susan Crowley and Brenda Brown Susan Crowley
| Human Services New Employee Orientation Program was instituted in 1992. It has run successfully as a half-day program for 5 of the 10 years that it has been operational. The program needs to be reviewed from a quality improvement standpoint to provide new workers with a top quality program that communicates policy and program content in a consistent and professional manner | New Employee Orientation Program Held quarterly at the Northport Office | The Training Officer in the Economic Assistance and Work Services Division will review and analyze ever aspect of the Department’s NEOP program from set-up to evaluations and will make recommendations for improvement to the Associate Director for Administration. The Training Officer will meet with all presenters and look at what is presented what additional information needs to be included and the overall flow of the program. She will also review the last 4 quarterly NEOP evaluation summaries are part of her review | Approved and revised NEOP program. | Margaret Romens, Training Officer and Brenda Brown December 31, 2002.
BPHCC
Assess the Organizational Functioning of the Facility | Identify areas whereby better communication can occur along with collaborative problem solving | Improve horizontal and vertical communication and problem solving | •Use the information from focused interviews to guide the team. •Create a strategic planning committee. •Look at past drafts of task force vision of organizational structure. •Look at Eden Alternatives. •More funds in our training accounts. | •Improvement in team functioning •More effective decision-making. •Better clinical outcomes for residents. •Higher retention rates. | Jack Nelson and BPHCC Management Team. Began in 2001. Will continue through 2002.
Improve CNA Orientation Program | New employees are not always well prepared for unit demands | Improve the assimilation of new staff to the clinical units--develop the concept of a mentoring program | CNA task force will meet 2 times per month to make recommendations to the nursing management team | Positive feedback from new employees and high senior staff. | Melody, Inservice Coordinator, will chair the task force
Improve mechanism for evaluating probationary employees | Some probationary employees fall through the probationary net and become long-term marginal employees | Facility wants to retain healthy, productive employees | •Identify performance gaps. •Initiate the coaching process early after hire. •Develop specific employee work plans. •Scheduling nursing supervisors to work on the units for closer observation and assessment. | •Do not maintain or sustain marginal employees. •Improved team functioning. •Improved staff morale. •Improved clinical outcomes. | Continuous dialogue with DOA and BPHCC management team. Review excessive absenteeism/FMLA utilization.