## Sheet1
Item no. | RSS comm. no. | RSS para. no. | Commitment | Lead branch, dept or agency | Lead official | Other parties | Progress to date | Next steps | Target date for next steps | Target date for all action | RSS time-scale
1 | 1.01 | 1.13 | Set up Road Safety Advisory Panel. | RS5 | Bill Hills | Many | RSAP seventh meeting held in January 2003. | Next RSAP meeting 30 October 2003. | 2003-10-01 | On-going | a
2 | 1.02 | 1.13 | Evaluate progress with the strategy and towards the targets formally every three years. | RS4 | Mark Magee | RSAP, RS5, TRL, TSR | Contractor commissioned to assist. First review underway. | Update RSAP at next meeting. | 2003-10-01 | On-going | b/c
3 | 2.01 | 2.1 | Local authorities to carry out child road safety audits, which will be monitored (with the Road Safety Advisory Panel advising on appropriate measures). | RS3 | David Padfield | RS4 | Data requirement included in guidance on Local Transport Plan annual progress reports.Guidance issued to local authorities on child road safety audit. | Analyse revised data annually. | Ongoing | Ongoing | a
4 | 2.02a | 2.10 and 6.28 | Local authorities must consider using their powers to create more 20mph zones (with suitable traffic calming and parking restrictions around schools and in residential areas where most child accidents occur). | RS4 | Andrew Rhind | RS3, CLT, LAs, GOs | Powers to create 20mph zones have been delegated to local authorities. Latest LTP annual progress reports were received July 2003 | Annual monitoring of local authorities' implementation as part of LTP progress reports. | Ongoing | On-going | a
5 | 2.02b | 2.1 | Local authorities must consider providing safe crossing facilities (on busy through roads where traffic calming is not appropriate). | RS4 | Ian Drummond | RS3, GOs, LAs | Covered in local transport plan guidance. | Action completed. |  |  | a
6 | 2.02c | 2.1 | Local authorities must consider making enforcement more effective (especially by the use of cameras on busy roads where many accidents happen). | RS2 | Adrian Waddams | LAs | See item 75 onwards. |  |  |  | a
7 | 2.03 |  | Highways Agency to develop and implement child friendly areas on trunk roads near schools and in residential areas. | HA | John Smart | RS3 | Highways Agency regional offices continue to support delivery of the child casualty reduction target through the identification and implementation of their safety scheme programme. | Highways Agency regional offices to investigate latest accident statistics for 2002 and identify potential sites or sections of routes for accident remedial measures. | Ongoing | Ongoing | a
8 | 2.04 | 2.1 | Supporting local authorities putting in place Home Zone schemes (to slow vehicles down and to give more priority for walking and cycling). | CLT | Wayne Duerden |  | 61 schemes selected for funding in 11 January 2002. Inaugural meeting held with authorities involved in the Home Zone Challenge. Authorities working with local communities to develop the schemes. Website to allow rapid dissemination of information on the Challenge Schemes established (www.homezoneschallenge.com). Design Guidelines for Home Zones published by IHIE, working in close collaboration with DfT, and launched by David Jamieson in June 2002. Traffic Advisory Leaflet on Public Participation published by DfT in January 2003. | Successful local authorities to implement home zone challenge schemes. | 2005-03-01 | On-going | a
9 | 2.05 | 2.1 | In-car design to take special account of children e.g. use of air bags. | VSE6 | Peter O'Reilly | DTI | One research project investigating airbag deployments has been completed. A second research project investigating airbag interactions started in March 2002. | Final report from second research project due by April 2004. | Apr-04 |  | c
10 | 2.06 | 2.14-15 | Standardising child restraint fittings. | VSE6 | Peter O'Reilly | DTI | Development of ISOFIX system and inclusion in ECE Regulations almost complete. Research into associated issues continuing. | Entry into force expected by the end of 2004. | Dec-04 | 2004 | b
11 | 2.07 |  | Issue (with RoSPA) national guidelines on roadside pedestrian training. | RS3 | David Padfield |  | Published. | Action completed. |  |  | a
12 | 2.08 |  | Continue to encourage schools to teach road safety in PSHE at key stages 1, 2 and 3. | RS3 | David Padfield | DfES, CD, RS4 | Both primary and secondary school lesson plans developed and placed on DfT website for schools. More primary and secondary plans being considered. DfES guidance on teaching safety published on website February 2002. Literacy plans have been added to the primary site. | (a) Lesson plans in various subjects continuing to be developed. (b) DfT's THINK website to include teachers' area. | Ongoing (a) Dec-03 (b) | Ongoing | a
13 | 2.09 |  | Work with road safety professionals to ensure road safety resources are used in schools. | RS3 | David Padfield | RS, CD, LARSOA | On-going contact with Road Safety Officers. New and existing research and materials promoted at RoSPA Congress and Education Show. | Continue to develop and promote existing resources, for example, at Education Show each year. | On-going | On-going | a
14 | 2.1 |  | From September 2000 a new road safety aid will be made available for classrooms. | CD | Tony Allsworth | RS3 | Arrive Alive available to schools from August 2000. Primary schools lesson plans available since September 2001. Secondary school lesson plans since June 2002. See www.databases.dft.gov.uk/lessonplans/ | Initial action completed - but materials will continue to be tested, developed and promoted. |  |  | a
15 | 2.11 | 2.43 | Produce road safety education guidelines for schools and professionals. | RS3 | David Padfield | CD, RS4 | "On the safe side" circulated to local authorities and published on the website in July 2002. | Action completed. |  |  | a
16 | 2.12 | 2.16 | In association with the Scottish Road Safety Campaign devise and implement a strategy for promoting road safety education in Scottish schools. | Scottish Exec | Alan Brown | SRSC | Progress on Scotland only topics is not covered in this DfT report.
17 | 2.13a | 2.12-13 | Encourage parents to get involved through "One Step Ahead" for new parents. | RS3 | David Padfield | OGDs, TRL, CAPT | Revised Book 1 distributed by Tesco. | Seeking private funding for revised Book 2. | Dec - 03 | Annual reviews | a
18 | 2.13b | 2.22 | Encourage parents to get involved through resources for the transition from primary to secondary school. | RS3 | David Padfield | CD, RS4 | Transition materials - Making Choices - published September 2001 and copies sent to local authorities. | Action completed. |  |  | b
19 | 2.14 | 2.2 | Explore potential for practical road safety training in play schemes and homework clubs. | RS3 | David Padfield | RS4, CAPT, CD | Out of school care activity pack published 18 June 2003. | Action completed. |  |  | a
20 | 2.15 |  | Increase access to road safety materials via the Internet. | CD | Tony Allsworth | RS3, RS4 | All DfT materials are now available on our website at: http://www.think.dft.gov.uk, www.databases.dft.gov.uk/lessonplans/ or www.hedgehogs.gov.uk | Action completed but we shall continue to review and develop the website. |  | On-going | a
21 |  | 2.19 | Make "Rosalind" more user-friendly (database of road safety education linked materials). | RS4 | Deirdre O'Reilly | CD, RS3, CLT | Put out to competitive tender. | Select contractor. | 2003-11-01 | 2004
22 | 2.16 | 2.2 | Discuss with road safety professionals and community groups how to encourage people to start up and run training schemes. | RS3 | David Padfield | RS4 |  | Will be one of the actions for co-ordinators under item 23. | On-going | 2007 | a
23 | 2.17 | 2.2 | Develop a programme promoting child pedestrian training schemes in deprived areas. | RS3 | David Padfield | RS4 | Successful local authorities in first tranche notified September 2001. Successful local authorities in second tranche notified September 2002.Successful LAs in the third and final tranche notified July 03. | 1st tranche: monitor child training. (a) 2nd tranche: monitor child training. (b) 3rd tranche: co-ordinators should be in place by Jan - 04 (c) | Apr-04 (a) Apr-04 (b) Jan - 04 (c) | 2007 | b
24 | 2.18 | 2.46 | Monitor high risk groups and explore ways of improving their safety. | RS4 | Deirdre O'Reilly | RS3, CD | Ensure high risk groups are included in the evaluation of the Kerbcraft pilot. Met with RSOs working with ethnic minorities. | Develop a research proposal in response to meeting with RSOs. | 2003-12-01 | On-going | b
25 | 2.19 | 2.35 (box) | Support school travel plans. | CLT(TA) | Margaret Longes | RS3, DfES, DH | Local authority travel plan co-ordinator bursaries awarded February 2001. Extended programme of free site-specific advice available from May 2001. Second phase of second series of school travel seminars commenced in September 2002 and finished October 2002. | Publish "Making School Travel Plans Work" a new best practice guide. | 2004-05-01 | On-going | a
26 | 2.2 | 2.35 (box) | Raise the profile of school travel issues and spread best practice through the School Travel Advisory Group. | CLT(TA) | Margaret Longes | RS3, DfES, DH | STAG has overseen preparation of a best practice guide to school travel strategies and plans for local authorities, a guide to school travel plans and a school travel resource pack and a guide on best practice in increasing bus use for journeys to school. | STAG overseeing work on the 11 recommendations set out in its report to Ministers as published in January 2000. | On-going | On-going | a
27 | 2.21 | Page 19 (box) | Change legislation on school crossing patrols. | RS3 | David Padfield |  | Changes made in s270 of Transport Act 2000. LA circular issued. Leaflet published. | Action completed. |  |  | a/b
28 | 2.22 | 2.32 | Work with voluntary groups to encourage more children to wear cycle helmets. | RS3 | David Padfield |  | Grant to Bicycle Helmet Initiative Trust. Project completed August 2001. Guidelines for local highway and health authorities published May 2002. Grant provided for BHIT to produce guidelines for schools, published June 2003. | Action completed. |  | On-going | a
29 |  | 2.24- 28 | Promote cycle training. | RS3 | David Padfield | RS4, CLT | Revised RoSPA guidelines on cycle training published. | Action completed. |  |  | b
30 | 2.23 | 2.28 | Promote the use of the Scottish cycle training scheme in all Scottish schools. | Scottish Exec | Alan Brown | SRSC, RS3 | Progress on Scotland only topics is not covered in this DfT report.
31 |  | 2.45 | Support professional development of those who deliver road safety education, publicity and training through NVQ in road safety. | RS3 | David Padfield |  | DfT has supported the development and trials of NVQs in road safety, and given a small grant to promote their take-up. | Further promotion of road safety NVQ as appropriate. | On-going | On-going | c
32 |  | 2.46 | Further research into child-related issues to help understand problems and develop counter-measures. | RS4 | Deirdre O'Reilly | RS3, TSR, CLT, CD | 2 out of 4 projects on adolescent road safety have been completed. | Disseminate research reports on adolescent road safety (a). Agree final report on the survey of child road safety in OECD countries and disseminate the results (b). | Nov-03 (a) Dec-03 - June-04 (b) | On-going
33 | 3.01 | 3.09 | Boost road safety education in schools (through expanded DSA Schools Programme in partnership with the police and road safety officers). | DSA | Paul Butler | RS | Funds secured for increasing programme until end of 2003/04. Arrive Alive Programme received Prince Michael International Road Safety Award in August 2002. 2800 presentations made in 2001/02. 4,250 presentations made 2002/03. 1588 presentations made April - September 2003. | 6000 presentations planned for 2003/04. Aim to send "Arrive Alive" folder to every school in Autumn 2003. | Dec - 03 | On-going | a
34 | 3.02 | 3.2 | Develop logbook scheme for car drivers - voluntary. | DSA | Paul Butler | RS6, RS4, DVLA | One million logbooks printed and distributed to date within pilot scheme. Revised version of the logbook (renamed drivers record) issued June 2003 (see items 35 and 36) - now sent to all new provisional licence holders by DVLA. | Action completed. |  | 2003 | a
35 | 3.03 | 3.20 - 21 | Consult on introducing mandatory logbooks for learner drivers (to include night-time driving). | DSA | Paul Butler | RS6, RS4, DVLA | Regulation-making powers to introduce training schemes supported by logbooks obtained in Transport Act 2000. Further consultation on principle of mandatory logbooks, and who should sign them, undertaken in "More structured approach to learning to drive". (Consultation closed June 2002.) | Responses to consultation under consideration. | 2003-12-01 | 2004 | a
36 | 3.04 | 3.22 | Develop logbook schemes for drivers of other vehicles (lorries, buses and motorcycles). | DSA | Paul Butler | RS6, RS4, RS3, DVLA | New occupational standards adopted for road haulage and passenger transport industries. | Lorries and buses - Link with new European requirements for professional competence for drivers (see item 47). | Dec - 03 | 2004 | b
37 | 3.05 | 3.15 | Consult on measures to achieve necessary driving experience. | RS6 | Sue Faulkner | DSA, DVLA, RS4 | Consultation document issued 1 March 2002. | Responses to consultation under consideration. | 2003-12-01 | 2004 | a
38 | 3.06 | 3.25-3.26 | Raise standards of driving instructors. | DSA | Paul Butler | Legal, RS4 | Workshops have been held and industry have produced report (see also items 34, 40). Theory test in qualifying exam improved in February 2002 - question bank expanded and third distracter added. Question bank published. Hazard perception testing introduced into ADI qualifying examination in line with main programme of implementation 14 November 2002 (see item 43). | Next set of 12-monthly data to be sent to ADIs October 2003 (see item 40). | 2003-10-01 | 2004 | a/b
39 | 3.07 | 3.27 | Rationalise driving instructor regulation, with detailed provisions for different sectors. | DSA | Paul Butler | RS6, Legal, RS1 | Instructions for registering different types of instructor prepared for future Bill | Link with instructor provisions flowing from item 47. | 2003-12-01 | 2005 | b
40 | 3.08 | 3.28 | Publish information on driver instructor performance. | DSA | Paul Butler | Legal, RS4, RS6 | Three rounds of data analyses shared with individual instructors (latest data for 12 months to end March 2002 sent to ADIs in September 2002). Instructions for information disclosure powers prepared for future Bill. Workshops have been completed and industry groups have produced report (see also items 34, 38). | DSA's Road Safety Information System will enhance the quality of data about instructors and candidates - currently in development and due to be in place late 2003. Next set of 12-monthly data to be sent to ADIs in October 2003. | 2003-10-01 | 2004 | b
41 |  | 3.29 | Consult on proposals to suspend instructors where there is a risk to public safety, and introduce new appeals arrangements. | DSA | Paul Butler | Legal, RS4, RS6 | Enabling powers for better enforcement and transfer of appeals to Transport Tribunal, obtained in Transport Act 2000. Commencement Order made and in force April 2002. | Action completed.
42 | 3.09 | 3.32 | Development of current theory test (to promote the responsible driving agenda). | DSA | Paul Butler | RS4, RS6 | Changes to LGV/PCV theory tests implemented 1 April 2003. ADI multiple choice questions enhanced and improved feedback given to candidates on HPT from September 2003. Continuous trialling of new multi-choice questions and HPT clips has also started. | Next changes to lorry and bus questions planned for 1 April 2004 and for cars and motorcycles 1 July 2004. | 2004-04-01 | On-going | a
43 | 3.1 | 3.34 | Add hazard perception to theory test (by 2002). | DSA | Paul Butler | RS4, RS6, TRL | Hazard Perception Testing implemented 14 November 2002. Training package distributed to 55,000 driving instructors and made available to general public. Information video sent to candidates for the first 3 months. | Action completed. |  |  | b
44 | 3.11 | 3.36 - 37 | Consider further changes to car practical test. | DSA | Paul Butler | RS4, RS6, TRL | Research undertaken on practical driving test. Effects of longer test on amount of training and pass rates being monitored. Decisions on new EU standards announced. | EU undertaking TEST project into location and duration of driving test throughout Europe. Due to report 2005. | 2005-09-01 | 2005 | b
45 | 3.12 | 3.39 | Consult on introduction of compulsory P plates (and encourage greater voluntary use in the meantime). | RS6 | Sue Faulkner | DSA, RS4, CD | Included in consultation document mentioned in item 37. | Responses to consultation being considered. Trial of voluntary use underway. | 2003-12-01 | 2004 | a
46 | 3.13 | 3.52 | Introduce instructor registration for fleet car (and other specialist) drivers. | DSA | Paul Butler | RS6, HSE | Voluntary registration scheme for fleet-driver trainers introduced in April 2002. Some 355 are now on the register. | Action completed. |  |  | a
47 | 3.14 | 3.45, 3.47 | Raising standards of LGV and PCV driver training: Stage 1: theory test, supervising driver. Stage 2: statutory scheme (prescribing training course, approved providers and register of instructors). | DSA | Paul Butler | Legal, RS6, RS1 | Stage 1: Completed. Stage 2: Enabling powers obtained in Transport Act 2000. Links with consultation undertaken on EU proposals for professional lorry and bus driver competence Directive. Directive entered into force 10 Sept 2003. GB has until 2008 to establish a regulatory training scheme for PCV drivers - DSA will look to introducing earlier as part of phase-in of Directive's proposals. | Stage 2: Legal transposition by 10 September 2006. Will consult again on those matters where Directive gives Member States alternatives Dec 2003. Establishing a voluntary PCV registration scheme overtaken by Directive. DSA now looking to introduce regulatory scheme - pre-test training for PCV licence acquisition as part of phase-in of Directive's requirements. | 2003-12-01 | 2005 | a/b
48 | 3.15 | 3.4 | Set national standards for advanced driver training and instructor registration. | DSA | Paul Butler | RS6 | 1. Agreement reached between DSA, IAM, RoSPA & DIA on national standards for advanced driver testing. DSA has conducted supervising visits since June 2002. 2. Expectations Document for competencies required by "blue light" drivers agreed with MOD, police, fire and ambulance services. Sent to wider constituency of users. | 1. Action on-going. 2. Ongoing discussions with individual services cascading of Expectations Document within their training programmes. | 2004-03-01 | 2004 | b
49 | 3.16 | 3.43 | Develop schemes for better information and advice for older drivers and older driver assessment - and issue revised leaflet. | RS1 | Robert Davies | RS4, CD, DSA | New leaflet was issued in July 2002 and Road Safety Research Report no. 29, "The Ageing Driver - A Programme Of Research" published in November 2002. | Keep under review possibilities for providing better advice on medical fitness to drive. | On-going | On-going | a
50 | 3.17 | 3.49-3.51 | Set up inter-agency group on work-related road risk. | HSE | Sharan Bains | RS6, RS4, DSA | Ministers have agreed a programme of work staged over a 3-5 year period, focused on: working with industry to develop and promote best practice; raising awareness; intelligence and data collection; clarifying investigation / enforcement arrangements between the Police, HSE and Local Authorities; research and guidance. Generic guidance for employers was published inSeptember 2003. | HSE, in partnership with DfT, continues to progress the programme and is currently working with the police to develop investigation criteria to enable them to identify where serious management failings have been a significant contributory factor in a traffic accident. | 2004-10-01 | On-going | a
51 | 3.18 | 3.54 | Continue to publicise the dangers of driving whilst using a mobile phone. | RS6 | Sue Faulkner | CD, RS4 | Announced on 24 June that drivers to be banned from using hand-held mobile phones from 1/12/03. | Lay regulations before Parliament | Oct-03 | 2003 | a
52 | 4.01 | 4.1 | Home Office review to consider whole range of penalties for drink drive offenders. | RS1 | Robert Davies | Home Office, LCD | Report on review of penalties published on 24 July 2002. | Increase in maximum penalty to 14 years imprisonment for causing death by dangerous driving when under the influence of drink or drugs being implemented through Criminal Justice Bill | 2003-10-01 | 2004 | a/b
53 | 4.02 | 4.11 | High risk offenders scheme to be reviewed. | RS1 | Robert Davies | Home Office , RS4, DVLA | Research report published January 2003. | Further discussions planned with DVLA. | 2003-10-01 | 2003 | b
54 | 4.03 | 4.12 | Home Office review will cover minimum ban for first-time high risk offenders. | RS1 | Robert Davies | Home Office, RS4, DVLA | See item 52 | See item 52. | On-going | 2004 | a/b
55 | 4.04 | 4.13 | Roll out rehabilitation nation-wide. | RS1 | Robert Davies | RS4, Magis. Courts, course providers |  | Action completed. |  |  | a
56 | 4.05 | 4.15 | Improve drink-drive publicity campaigns. | CD | Tony Allsworth | RS1 | THINK! drink-drive campaign launched November 2000. Year round advertising launched October 2002. Pub TV and association with Rugby football league 2002/3 helped to get message across. | Continue to develop year-round advertising keeping in touch with the target audience through market research. | 2004-03-01 | On-going | a
57 | 4.06 | 4.16-4.17 and 4.29 | Strengthen police powers for roadside testing (drink and drugs). | RS1 | Robert Davies | Home Office, Police, RS4 | Powers for roadside tests introduced/improved through the Railways and Transport Safety Bill (enacted July 2003). | Uses of powers relies on items 60 and 61 for drugs. Drink drive powers will be completed by work under item 58. | On-going | 2004 | b
58 | 4.07 |  | Introduce evidential roadside breath testing (subject to further investigation). | RS1 | Robert Davies | Home Office, Police | Home Office and police examining procedural and legislative implications. | Await suitable legislative opportunity. | On-going | 2004 | b
59 | 4.08 | 4.19 - 4.20 | Consider changes in the drink-drive limit in a European context. | RS1 | Robert Davies | Home Office, OGDs | EC Recommendation on harmonised limit adopted by Council. Government decision not to reduce BAC limit announced on 20 March 2002. | No further action currently planned. |  |  | a/b
60 | 4.09 | 4.27 | Continue support for development of drug screening devices. | RS1 | Robert Davies | Police, Home Office, RS4 | Specification for roadside screening device issued by ACPO, January 2003. Home Office Police Scientific Development Branch continue to explore technological opportunities to identify independently i) impairment and ii) the presence of drugs. | Further progress depends on scientific developments. Legislation now in place and implementation of that will encourage rapid development. | On-going | On-going | a/c
61 | 4.1 | 4.28 | Support police training in drug recognition and impairment testing techniques. | RS1 | Robert Davies | Home Office, RS4 | Drug Recognition Techniques Field Impairment Testing (DRTFIT) launched in August 2000. Contract awarded for 2 year project to monitor and evaluate effectiveness of techniques used by police. | Evaluation report to be submitted. | 2003-11-01 | On-going | a
62 | 4.11 | 4.3 | Continue research into drug-driving. | RS4 | Robert Davies | Home Office, DVLA, RS1 | Report on cannabis and driving published Dec 2000. Report on 3 year study on incidence of drugs and alcohol in fatal victims published June 2001. Report on cannabis and alcohol on driving published September 2002. EU funded project ‘Impaired Motorists: Methods of Roadside Testing and assessment for Licensing” study to examine the prevalence of illegal drugs in casualties. | Await outcome of IMMORTAL project research. Consider further projects | Dec-04 On-going | On-going | a
63 | 4.12 | 4.33 | Consider how to target publicity on the risks of drug-driving. | RS1 | Robert Davies | RS4, CD, Home Office, ADCU, MCA | Targeted publicity now underway - see www.drugdrive.co.uk Report on labelling of medicines published May-03. | Further targeted publicity to be developed on back of current research. | On-going | On-going | b
64 | 4.13 | 4.42 | Consultation on the possible repeal of the UK drivers' hours in favour of the EU rules. | RH | Peter Dean | RFOP1 | Originally delayed because of discussions on Working Time Directive but now on hold because of proposal to amend EU drivers' hours. Revised Commission proposal to amend EU drivers' hours rules published in August 2003. | Ministers have agreed to defer review of UK rules until the fate of this proposal is known. | 2004-06-01 | On-going | b
65 | 4.14 | 4.43 | Continue research into the accident risk of business and commercial drivers and effective counter-measures. | RS4 | Sofia Marcal | RS6, HSE | Research on organisational safety culture and accidents underway. Final report on company vehicle incident reporting and recording published April 03. | Report on research on organisational safety culture and accidents in Dec 03. | 2003-12-01 | On-going | a
66 | 4.15 | 4.38 | Continue to research driver fatigue as a road safety issue. | RS6 | Sue Faulkner | RH, HSE, RS4 | Three-year research project completed and report published. New contract on effectiveness of motorway service areas let December 2002. | MSA research to be completed by December 2003. | 2003-12-01 | On-going | a/c
67 | 4.16 | 4.44 | Improve publicity on fatigue. | CD | Tony Allsworth | RH, HSE, RS6, RS4, CD | Radio and poster campaign began in August 2000. New TV advert launched 27 March 2002, plus Don't Drive Tired VMS signs on motorways and co-operation from service areas. TV and radio reminders through summer 2002. Truckback advertising from Spring 2003. | Messages on planning journeys and taking breaks to be developed for use in 2004. | Mar - 04 | On-going | a/c
68 | 5.01 |  | Production of provisional local transport plans for 2000/2001 including the local casualty reduction target and local road safety strategy. | RS4 | Ian Drummond | RS3, LTP, GOs, LAs |  | Action completed. |  |  | a
69 | 5.02 |  | Production of full five-year local transport plans. | LTP1 | Jenny Sewell |  | Revised guidance on LTP APRs published March 2003. | Action completed. |  |  | a
70 | 5.03 | 5.32 | (Local authorities to) monitor accidents and address problem sites. | RS4 | Ian Drummond | RS3, GOs | DfT guidance requires LAs to report on local casualty rates and their plans to address them in LTP annual progress reports | Next LTP annual progress reports due end July 2004 | 2004-07-01 | On-going | a
71 | 5.04 |  | Maintain roads and road signs to a high standard. | RP | Ian Holmes | LTP, TMT, LGA, CSS, HA | Further increase in resources for local highway maintenance secured in December 2002 LTP settlement. | Code of Good Practice for Roads to be revised in 2004. Revised Code for Street Lighting, taking into account risk management, in preparation. New Code of Good Practice to be prepared for bridges by July 2004. | 2004-05-01 | On-going | a
72 |  | 5.08 | Work with professionals to support guidance on road safety best practice. | RS4 | Ian Drummond | RS3 | Good practice guide launched at the national road safety good practice conference in Bristol in June 2001. | User survey of Guide undertaken in early 2003. Revised Guide will need to account for results of Local Authority performance study, due to report in January 2004 | 2004-01-01 | On-going | a
73 | 5.05 | 5.08 | Cascade good practice from the Gloucester Safe City project. | RS4 | Ian Drummond | RS3 | Full report and new Urban safety management Guidelines launched September 2003. | Action completed. |  |  | a
74 | 5.06 | 5.18 | Implement the actions outlined in the Highways Agency safety plan. | HA | John Smart | RS | Highways Agency regional offices completed a programme of 162 schemes in 2002/03 | Complete review of accident data and prepare scheme programme for 2003/04. | 2003-12-01 | On-going | b
75 | 6.01 | 6.17, 6.32-3 | Advise on more efficient speed limit signing and additional signing for speed cameras. | RS2 | Adrian Waddams | RS4, TMT, CSS, LGA, ACPO | Research commissioned, May 2001. (Other signing requirements to be covered by item 76.) Camera signing covered in revised Traffic Signs Regulations and General Directions published in January 2003. | Action completed. |  |  | a
76 | 6.02 | 6.16 | Revise guidance on setting speed limits. | RS2 | Adrian Waddams | RS3, HETA, CLT, TMT, Legal, HA, ACPO, CSS, LGA | Research into assessment frameworks and speed data evaluation for rural roads has been commissioned. | Outcome of research and further dialogue with practitioners during 2003 expected to produce initial proposals early in 2004 | 2004-01-01 | 2004 | b
77 | 6.03 | 6.27 | Developing solutions to improve safety on urban high streets and other "mixed priority" routes. | RS4 | Andrew Rhind | RS2, RS3, CSS, LGA, IHT, CLT, GOs | Mixed priority route demonstration projects (5 schemes) announced in December 2001. Second round of projects (5 further schemes) announced in December 2002. Birmingham City Council announced as Inner City Demonstration Project authority in June 03 | Construction of Norwich and Manchester schemes due to start Spring 04. Interim report to be published summer 04. | 2004-07-01 | On-going | a
78 | 6.04 | 6.17 6.32 | Type approve and issue guidance on speed-activated signs to warn drivers of hazards. | RS2 | Adrian Waddams | CLT, HA, CSS, LGA, IHT | Traffic Signs Regulations and General Directions 2002 changes covered vehicle activated signs. Traffic Advisory leaflet issued to LAs end March 2003. | Action completed |  |  | a
79 | 6.05 | 6.24 | Rural accident prevention through targeting accident sites with engineering measures or new technology. | RS2 | Adrian Waddams | CLT, HA, CSS, LGA, IHT | Initial research completed and published. | Advice on safety measures to be developed in support of guidance on rural speed limits at a later stage. (see item 76). | On-going | 2004 | a
80 | 6.06 | 6.17 6.32 | New technology for accident prevention in rural areas. | RS2 | Adrian Waddams | CLT, HA, CSS, LGA, IHT | See item 78. | Action completed |  |  | b
81 | 6.07 | 6.24 | Continued trials of sympathetic traffic calming in villages to develop good practice guidance. | CLT | Catherine Lovell | CLT, HA, CSS, LGA, IHT | Trials have been completed. Reports published in October 2001. New research project "Drivers and Traffic Calming" started October 2001. | Schemes and techniques to be identified and monitored over a 3 year period. | 2004-10-01 | 2004 | a
82 | 6.08 | 6.37 | Pilot schemes for development of a speed camera funding mechanism. | RS2 | Adrian Waddams | Home Office, ACPO | Pilot schemes finished in March 2002. First year summary published on 13 August 2001. Report on final outcome of pilot schemes published in February 2003. | Action completed. |  |  | a
83 | 6.09 | 6.37 | Country-wide roll out of camera funding. | RS2 | Adrian Waddams | Home Office, LCD, HMT, CPS, RS1, ACPO, CSS, LGA | Powers obtained via Vehicles (Crime) Act 2001 allowing police/local authorities/courts to cover safety camera operation costs from fixed penalty speeding fine revenue. National roll-out announced on 13 August 2001. 42 partnerships covering 46 of 51 police areas in Great Britain in place from 1 April 2003. | Complete national roll-out. | 2004-03-01 | 2004 | b
84 | 6.1 | 6.37 | Evaluation of new enforcement technologies. | RS2 | Adrian Waddams | Home Office, ACPO | Included in pilots under item 82. | See item 82. |  |  | a
85 | 6.11 | 6.37 | Subject to Home Office review of penalties, give the courts power to impose heavier fines and additional penalty points for speeding. | RS1 | Robert Davies | RS2, RS3 | See item 52 | See item 52. |  | 2004 | a
86 | 6.12 | 6.37 | Consider how best to deal with the very worst cases of speeding, possibly with tougher penalties. | RS1 | Robert Davies | RS1, RS2, Home Office | See item 52 | See item 52. |  | 2004 | a
87 | 6.13 | 6.37 | Research into benefits of rehabilitation courses for speeding offenders. | RS2 | Adrian Waddams | RS1, RS4, Home Office, ACPO | Related research into driver improvement courses underway. Evaluation of speed awareness courses has also started. | Awaiting input on related research from RS4. | 2004-04-01 | 2004 | a
88 | 2003 | 6.18 | Extend use of the controlled motorway system where congestion or network management problems exist. | HA | Hugh Maxwell | RS2 | The work to extend Motorway control from M25 J15 to J16 was completed on time (December 2001). Motorway control now operates between J10 and J16 on M25. New monitoring to re-assess benefits to justify wider application started in January 2002. | A copy of the Controlled Motorways business case will be placed in the House of Commons Library by late 2003. | 2003-12-01 | 2003 | b
89 | 6.15 |  | Continue publicity campaigns to inform motorists of both the dangers of speed and that enforcement will be given a higher profile. | CD | Tony Allsworth | RS1, RS2 | Radio advertising running since August 2000. "Think! slow down" TV, and radio advertising launched June 2001 and continues. | Continue work with safety camera partnerships. Research in hand to inform the most effective way of taking forward publicity. | Mar - 04 | On-going | a
90 | 6.16 | 6.13 | New publicity campaigns informed by behavioural studies. | CD | Tony Allsworth | RS2, TMT, CLT, RS1 | On-going development of Think! campaign. Research into speed and drink driving campaigns is imminent. | Ideas to be developed further in consultation between CD, RS and others. | Mar - 04 | 2004 | b
91 | 6.17 | 6.33, 6.17 | Research into drivers' understanding of national speed limits. | RS2 | Adrian Waddams | CLT, TMT, CSS, LGA, IHT, ACPO | Being carried out as part of publicity work under item 90 | See item 90. | Mar - 04 | 2004 | a
92 | 6.18 | 6.21 | Creation of hierarchy of roads by road usage. | RS2 | Adrian Waddams | HETA, Legal, CLT, TMT, HA etc | Requires progress on items 76 and 96 to inform requirements. Report to Parliament in November 2001 delivered on time. | Consider how to use recommendations of report. Recommendations to inform other work on speed management under this heading. | On-going | 2004 | b
93 | 6.19 | 6.31 | Issue guidance on creating self-explaining roads. | RS2 | Adrian Waddams | CLT, TMT, HA and others | Research on rural speed management (project S240B) is already studying this topic. | Trials of the concept may form part of the proposed rural area safety management demonstration project starting in 2004. Overall objective will take until 2005 to deliver and is dependent on success of trials, as yet not commissioned. | 2004-12-01 | 2005 | c
94 | 6.2 | 6.21-22 | Review policies based on results of research into the effect of and justification for lower speed limits in rural and urban areas. | RS2 | Adrian Waddams | Legal, CLT, TMT, HA and others | Needs to be linked with work on hierarchies and speed limit setting framework and traffic calming. | Urban research will indicate scope for further practical trials. Need to consider scope of work for rural areas. May not be able to start rural work until 2004 but should still be possible to deliver overall objectives by 2005. | On-going | 2005 | b
95 | 6.21 | 6.22, 6.35 | Review policies based on results of research into alternative signing conventions, including the viability of 'unsigned' limits. | RS2 | Adrian Waddams | Legal, CLT, TMT, HA, CSS, LGA, ACPO | Guidance on village speed limits, including signing, to be issued end 2003. | Action completed. |  |  | b
96 | 6.22 | 6.23 | Development of a simpler method of making speed limits by reference to the speed management strategy. | RS2 | Adrian Waddams | RS3, Legal, CSS, LGA | Linked to items 75, 76, 91and 92. Contract awarded to consultants in May 2001. First stage completed. No legislative changes required. | Future development will feed into item 76 and associated discussions with practitioners. | 2004-01-01 | 2004 | b
97 | 7.01a | 7.19 | Euro NCAP (support expansion to cover primary safety features). | VSE4/ VSE6 | Ian Yarnold/ Peter O'Reilly |  | Initial scoping research completed. Main project started in 2000 to run until 2004. EuroNCAP recently established a technical working group to develop test protocols and assessment criteria based upon UK research. Braking and visibility tests likely to precede ergonomics, lighting and handling. | Complete research. Take active role in EuroNCAP process. | 2004-06-01 | 2006 | a
98 | 7.01b | 7.2 | Euro NCAP (consider expanding to cover other vehicle categories). | VSE5 | Geoff Harvey |  | No progress due to low priority | Review priority | 2004-01-01 | 2006 | c
99 | 7.02 | 7.14 | Side impact protection. | VSE6 | Peter O'Reilly | DTI | Directive implemented for new car models from 1 October 1998 and all new cars from 1 October 2003. | Action completed but see items 101 and 102. |  |  | a
100 | 7.03 | 7.14 | Front impact protection. | VSE6 | Peter O'Reilly | DTI | Directive implemented for new car models from 1 October 1998 and all new cars from 1 October 2003. | Action completed but see items 101 and 102. |  |  | a
101 | 7.02 and 7.03 | 7.14 | Improved front and side impact capability. | VSE6 | Peter O'Reilly | DTI | Contractor has carried out research to evaluate existing directives. Final report available. Results incorporated within EEVC report submitted to Commission in January 2000. Commission proposal overdue. Following collaborative research, agreement within UNECE on revised side impact barrier and dummy secured. | Commission to report to Council and EP on potential improvements to directives. | 2003-12-01 | 2004 & 2005 resp for new car models; 2005 & 2008 resp for all new cars. | c
102 | 7.04 | 7.29 | Improved front and side impact compatibility. | VSE6 | Peter O'Reilly | DTI | First and second phase of research completed. Discussions progressing in EEVC and IHRA. Commission and Member States funding further collaborative research as part of third phase. | Complete collaborative research programme and select test procedures. Commence subsequent final fourth stage to validate selected procedures. | 2005-06-01 | 2010 new car models; 2015 for all new cars. | c
103 | 7.05 | 7.17 | Front under-run guards for HGVs. | VCA | Gus Gander | VSE5, Legal | New directive agreed (2000/40/EC). New GB regulations implemented from 10 August 2003 for vehicles >3.5ft. | Action Completed |  |  | b
104 | 7.06 | 7.28 | Intelligent seat belts (and airbags). | VSE6 | Peter O'Reilly |  | Advanced technology issues. Initial research now complete. New contract on advanced restraint systems awarded February 2002. | Await further research results. | Apr-04 | on-going | b/c
105 | 7.07 | 7.12 | Improve seat belt wearing rates. | CD | Tony Allsworth | RS1 | Publicity to promote greater use of rear seat belts continues to be run. Higher wearing rates maintained. TV and radio advertising continue. A new TV ad and online advice launched Sept 2003. | On-going development of advertising about front and rear seatbelts and child restraints. Further PR to accompany any regulation change on delivery drivers. | Mar - 04 | On-going | c
106 | 7.08 | 7.12 | Seek legislative opportunity to tighten the seat belt exemption for people on 'local rounds of deliveries". | RS1 | Robert Davies | Legal | The Railways and Transport Safety Act 2003 allows a change to the exemption from wearing seat belts. | Consult on revised exemption. | 2003-10-01 |  | a
107 | 7.09 | 7.13 | Subject to consultation, make the fitting of seat belts compulsory in new buses, coaches and minibuses and in new goods vehicles over 3.5 tonnes. | VSE6 | Peter O'Reilly | VSE5, RS, Legal, BT | Regulations made March 2001. Came into effect in October 2001. | Action completed. |  |  | b
108 | 7.1 | 7.1 | Improved vehicle lighting including daytime running lights. | VSE4 | Ian Yarnold | VSE6, DTI | The commitment to fit daytime running lamps as part of the Pedestrian Protection agreement has been deferred for further consideration. Further UK research into the effectiveness of daytime running lamps was proposed but may not proceed as EU research has begun. | Await results of EU research. | 2004-02-01 | On-going | c
109 | 7.11 | 7.16 | Pedestrian protection directive (safer car fronts). | VSE6 | Peter O'Reilly | DTI | Research on-going. Commission made proposal in February 2003 for Pedestrian Protection to apply to new car types from 2005 (Phase 1) and 2010 (Phase 2). | Proposal currently under discussion in European Council and Parliament. | 2003-12-01 | On-going | c
110 | 7.12 | 7.09 | Improved braking and compulsory ABS (for large vehicles). | VSE4 | Ian Yarnold | Legal, DTI, DSA | Regulations implemented September 2001. Main elements came into force on 1 May 2002. Research into Brake Limiting Factors was started in January 2001 and has been completed - final report being reviewed. Reserach investigating Driver Perception of Secondary Brake Performance was started in September 2001 and has been completed - final report awaiting publication. | Complete review of final report on Brake Limiting Factors. Publish report on Driver Perception. | Nov-03 | 2005 | b/c
111 |  | 7.21 | Quality control and safety recalls. | LRI2 | David Briggs | VSE, VI, VCA, DVLA | Following discussions with industry and VI/DVLA, safety recall notifications to vehicle keepers now significantly quicker (reduced from maximum of 16 weeks to minimum of 24 hours). | Action completed.
112 |  | 7.30-7.33 | Vehicle radar. | VSE4 | Ian Yarnold | RS, DTI, VCA | Preliminary systems being fitted to certain luxury car models and more in pipeline. VSE involved in negotiating international standards via BSI/ISO. | Continue to monitor developments. | On-going | On-going
113 |  | 7.34 | Intelligent Speed limiters. | VSE4 | Ian Yarnold | RS, DTI, VCA, TMT, DSA, HA | Phase 1 of new ISA research project completed. On road vehicle trials begun August 2003. | Continue to monitor research progress. | On-going | On-going
114 | 8.01 | 8.09 | Advisory group initiatives. | RS3 | David Padfield | AGM, RS4, VSE, TMT, TSR, LRI | Advisory Group on Motorcycling set up in May 1999 and has five task force groups. Interim report published April 2001. | Task force groups to continue work. Next full meeting is arranged for January 2004 when draft final report to be tabled. | 2004-01-01 | 2004 | b
115 | 8.02 | 8.12 | New licensing rules for learner riders. | DSA | Paul Butler | RS3 | Regulations amended to abolish two years on / one year off provisional licence rule from 1 February 2001. | Action completed. |  |  | a
116 | 8.03 | 8.13 | Improvements to pre-test training. | DSA | Paul Butler | RS3 | Meetings held with motorcycle training interests on training plans and logbooks. | Review syllabus and supporting logbook. | 2003-12-01 | 2003 | a
117 | 8.04 | 8.16 | Develop guidance for those returning to motorcycling after a break. | DSA | Paul Butler | RS3, RS4 | 1. DSA has re-written and updated its handbook, "Motorcycle Riding - The Essential Skills" and has produced a free leaflet for distribution via trainers and retailers. 2. Statements of core competencies developed for those who ride in the context of their work. Discussions held with motorcycle industry about DSA involvement in developing national standards for rider development training. | 1. Action completed. 2. Agree appropriate training solutions in partnership with industry. National standards in the process of being agreed between fast-food delivery companies and trainers. Links with work on rider development training (see 118). | 2004-01-01 | 2003 | a
118 | 8.05 | 8.16 | Develop voluntary register of accredited motorcycle trainers. | DSA | Paul Butler | RS3 | Discussions held with trainers and representatives of industry over accreditation arrangements. Set of competencies identified for instructors and trainees. | Issue discussion paper on proposals to motorcycling interests | 2003-12-01 | 2003 | a
119 | 8.06 | 8.14 | Introduce training requirement for newly qualified drivers wishing to ride a moped. | DSA | Paul Butler | RS3 | Regulations amended to require this from 1 February 2001. | Action completed. |  |  | a
120 | 8.07 | 8.15 | End exemption from motorcycle theory test for those holding full car licence. | DSA | Paul Butler | RS3 | Regulations amended to end this from 1 February 2001. | Action completed. |  |  | a
121 | 8.08 | 8.18 | Include awareness of vulnerable road users in training logbooks for learner drivers. | DSA | Paul Butler | RS6 | Included in voluntary log book for learner car drivers. | Include in log books for lorry, bus drivers, etc. They will be promoted starting with a voluntary scheme (links with developments on European Directive on LGV / PCV driver training - item 47). | 2003-12-01 | 2004 | b
122 | 8.09 | 8.17 | Introduce statutory register of motorcycle trainers. | DSA | Paul Butler | RS3 | Enabling powers sought in instructions prepared for next Bill. Discussions held with training industry. | Develop detailed proposals with the training industry and undertake wider consultation in light of development of 118 above. | 2004-04-01 | 2004 | b
123 | 8.1 | 8.28 | Work with OECD to standardise world-wide accident investigation. | VSE4 | Ian Yarnold | RS3, STP | Research has set up a world-wide methodology for accruing information on motorcycles accidents. Little support from OECD for new study, but possible bi-lateral approach with other Member states being considered. | Consider in more detail potential bilateral configuration. | 2003-12-01 | On-going | c
124 | 8.11 |  | Work with EC to examine scope for including secondary safety features in construction requirements for motorcycles. | VSE4/ VSE6 | Ian Yarnold/ Peter O'Reilly | RS3, DTI | The amended version of EWVTA framework directive will restate the Commission's intention to introduce secondary safety provisions for motor cycles. | Continue to await EC proposal. | On-going | On-going | c
125 | 8.12 | 8.27 | Work towards a new helmet standard. | VSE6 | Peter O'Reilly | RS3 | DfT lead European collaborative research and parallel domestic research, including work on new helmet technology demonstrator completed and reported. Calls invited by EU for integrated projects involving vulnerable road users. UK project - let to deliver next steps. | Intermediate discussions on next steps with stakeholders including new helmet standard for possible introduction by 2005. | 2003-11-01 | 2005 | c
126 | 9.01 | 9.05 | Local authorities to develop local transport plans which include measures to increase cycling and walking with a range of measures to improve safety. | GOs | GO road safety contacts | RS3, RS4, CLT | LTP guidance provides advice and requests details of local authority proposals. | RS4 will monitor LA road safety investment through new annual returns. 2003/04 data being collated as baseline for future comparisons. | 2004-06-01 | On-going | a
127 | 9.02 | 9.17 | Monitor and develop Home Zones. | CLT | Wayne Duerden | RS2, RS3, RS5 | Nine local authority schemes selected for "before and after" monitoring by contractor (for DfT). All "before" monitoring completed. Schemes in Leeds, Magor (Wales), Manchester, Plymouth and Sittingbourne completed, works in progress at Ealing, Peterborough and Nottingham but yet to start in Lambeth. Monitoring report for the scheme in Leeds published in July 2003. "After" monitoring and analysis underway in Magor, Manchester, Plymouth and Sittingbourne.Home Zones given new legal status in Transport Act 2000. Procedure regulations for designation and for Use and Speed orders being drafted following initial consultation on scope and content. | Local authorities to complete implementation of remaining pilot schemes. Contractor to carry out "after" monitoring once schemes are complete. Further consultation on draft statutory guidance and regulations. | Dec - 03 | On-going | b
128 | 9.03 | 9.13 | Consider setting rate-based targets for vulnerable road users. | TSR | Valerie Davies | RS3, RS4, RS5 | Matter was considered by RSAP Statistics sub-group. | Keep under review until detailed exposure data become available from NTS (expected to be available late 2003). | 2004-01-01 | On-going | a
129 | 9.04 | 9.23 | Work with the Cyclists' Touring Club (CTC) to develop adult training courses. | RS3 | David Padfield | RS4, CLT, DH | Small grant to CTC agreed to prepare adult cycle training guidelines. Grant matched by Department of Health. Project completed and guidelines published May 2003. | Action completed. |  |  | b
130 | 9.05 |  | Provide funding for RoSPA to revise their "Code of Good Practice on the Practical Aspects of Cyclist Training". | RS3 | David Padfield |  | Funding provided. Report published June 2000. | Action completed. |  |  | a
131 | 9.06 | 9.27 | Promote cycle helmet wearing. | RS3 | David Padfield | CLT | DfT publicity materials already recommend use of helmets. Developing new Teenage Cycle Safety campaign showing benefit of cycle helmets. Printed material and website launched May 2003.TV filler film shot. | Regularly review option of making helmets compulsory. (a) TV filler film will be available to TV stations early 2004. (b) | On-going (a) Feb 04 (b) | On-going (a) Feb-04 (b) | a
132 | 9.07 | 9.25 | Monitor helmet wearing rates. | RS4 | Deirdre O'Reilly | RS3, CLT | Wearing rates for 2002 have been published by TRL and results disseminated. | Review when next wearing rate survey should be undertaken. | 2003-10-01 | On-going | a
133 | 9.08 | 9.34 | Collect data from accident reports to get a clearer picture of horse-related accidents. | TSR | Valerie Davies | RS3 | Accident report form changed in January 1999. Data on horse rider casualties first published in "Road Casualties Great Britain 1999". | Monitor statistics. | On-going | On-going | a
134 | 9.09 | 9.37 (and 8.18) | Raise drivers' awareness of vulnerable road users through better training and testing. | DSA | Paul Butler | RS3, RS6 | Driving test for car drivers enhanced via more theory test questions and longer practical test. Car driver version of "What if..." video launched March 2001; motorcycle version in January 2002. Hazard Perception Testing introduced 14 November (see item 43). | Conducting increased numbers of Arrive Alive visits (see item 33). Include in logbooks for the various categories of driver (see item 121). TRL undertaking cohort study monitoring effects of changes to practical driving tests, including introduction of Hazard Perception Testing. Due to report 2005. | 2003-12-01 | On-going | a
135 | 9.1 | 9.38 | Improve victim support systems. | Home Office | Chrissie Daines | RS1 | Home Office-funded booklet by Brake available from police family liaison officers Home Office consultation paper on possible changes to Victims' Charter, issued in February 2001, asked if it should cover road accident victims.Recommendations put to Ministers and in-depth reviews to establish what works best in what context carried out in autumn 2002. Road Victims pilot group established to consider setting up projects. | Pilot projects announced in 3 areas to test different options on service delivery. Schemes will run for 18 months in Bedfordshire, Merseyside and areas within West Yorkshire. Schemes should be fully operational before the end of the year and will be independently evaluated. | 2003-11-01 | 2005 | b
136 | 10.01 | 10.08-09 | Implement the findings of the HMIC inspection report (for the police). | Home Office | Geoffrey Biddulph | Police, RS1, RS4 | HMIC report emphasised need for greater attention to road safety and road policing. | ACPO to monitor and evaluate implementation of its road policing strategy and traffic policies. | On-going | On-going | a/b
137 | 10.02 | 10.1 | Improve public understanding of the risks and penalties of road traffic offences. | RS1 | Robert Davies | Home Office, Police, Courts | Recognition that road traffic offences are not regarded by society with the same degree of condemnation as other crimes. | Aim for greater clarity in road traffic law. Use contacts with courts and others to spread appropriate messages. | On-going | On-going | b
138 | 10.03 | 10.14, 10.15 | Monitor the extent to which road safety issues are included in Crime and Disorder strategies. | Home Office | Geoffrey Biddulph | RS1, Police | Strategies of 98 (out of 376) CDRPs prioritised road safety, and 54 of them set road safety crime reduction-related targets. | Completed |  |  | a
139 | 10.04 | 10.16 | Home Office and DfT to review penalties for road traffic offences. | RS1 | Robert Davies | Home Office | See item 52 | See item 52. | On-going | 2004 | a
140 | 10.05 | 10.20-21 | Consult on obligatory retesting on conviction for wider range of offences. | RS1 | Robert Davies | DSA, DVLA | SI made in respect of offence of causing death by careless driving when unfit through drink or drugs. | Further use of obligatory retesting to be considered in context of penalties review. See item 52. | On-going | 2004 | b
141 | 10.06 |  | Complete research into dangerous and careless driving. | RS1 | Chris Gazzard | RS4, Home Office, LCD, CPS, Scot Exec | Main research report published February 2002. Draft reports of offenders and victims surveys received. | Approve final report of surveys for publication. | Oct-03 | 2003 | a
142 | 10.07 |  | Raise maximum penalty for careless driving. | RS1 | Robert Davies | Home Office | Penalties review consultation paper considered raising maximum penalty for careless driving from Level 4 to Level 5 fine. | See item 52. | On-going | 2004 | b
143 | 10.08 |  | Specific consideration of penalties for speeding offences. | RS2 | Adrian Waddams |  | Home Office review of penalties now complete. | Await suitable legislative opportunity. | On-going | 2004 | a
144 | 10.09 |  | Develop a new funding mechanism for speeding cameras. | RS2 | Adrian Waddams |  | Action complete but see also item 83. |  |  |  | b
145 | 10.1 | 10.20, 10.32-34 | DfT, Home Office and the police to refine the details of driver improvement schemes with a view to extending them nation-wide. | RS1 | Robert Davies | Home Office, Police, DSA, RS4 | DfT participating in meetings of course providers. | Further research needed on content of schemes and to monitor their effectiveness. | On-going | On-going | b
146 |  | 10.35 | Consider how the courts might be able to send convicted offenders on retraining courses as part of their sentence. | RS1 | Robert Davies | Home Office, LCD, DSA | Considered as part of Home Office review of penalties. | See item 52. | On-going | 2004
147 |  | 10.36 | Examine ways of extending retraining to other penalties involving retesting. | RS1 | Robert Davies | Home Office, LCD, DSA | Considered as part of Home Office review of penalties. | See item 52. | On-going | 2004
148 | 10.11 |  | Develop new technology which could help enforce the law more effectively e.g. digital breath-testing devices and drug-testing devices. | RS1 | Robert Davies | RS4, VSE, Home Office | Revised invitation for expressions of interest for a project published in the EC Official Journal in December 2002. Tenders received. | Tenders for alco-locks research under consideration. Let contract. | Oct-03 | On-going | b/c
149 |  | 11.12 | DfT will invite all major stakeholders to a conference to discuss emerging publicity plans. | CD | Tony Allsworth | RS | Conference held 1 May 2000. Attendees from local authorities, police forces and road safety organisations. Second THINK conference held on 27th June 2003. | Increased attendance at major fora. | 2004-04-01 | On-going
150 |  | 11.12 | DfT will hold regular campaign co-ordination meetings with representatives of the key organisations. | CD | Tony Allsworth | RS | Regular meetings held with road safety organisations and ACPO delegates. | Next meeting November 2003. | 2003-11-01 | On-going
151 |  | 11.12 | DfT will take full advantage of information technology to exchange ideas and keep stakeholders up to date with campaign news and good practice plans. | CD | Tony Allsworth | RS | Basic information available on website (www.think.dft.gov.uk). Since July 2003, use being made of LARSOA online newsletter. | Upgrading website for general information to public and campaign supporters. | On-going | On-going
152 |  | 11.12 | DfT will produce a campaign planning guide to help activists at local level to stimulate maximum news cover and business support. | CD | Tony Allsworth | RS | Campaign planning guide for supporters published and kept up-to-date on DfT website. Revised printed version issued at June 2003 THINK conference and subsequently distributed. | Continue to update website as necessary. | On-going | On-going
153 |  | 11.12 | DfT will involve the regions more closely with a programme of regional meetings. | RS3 | David Padfield | RS | A series of road safety roadshows was arranged during summer 2000. London roadshow held in March 2001. | Action completed.
154 |  | 11.12 | DfT will support the advertising regulators in cracking down on irresponsible speed-related advertising of cars and motorcycles. | CD | Tony Allsworth | RS | Market research carried out among drivers and potential drivers on what they take out from car advertising. Results presented to ITC, SMMT, Advertising Association and car advertising managers in 2000-02. Former DTLR commented on a proposed revised ITC advertising code in March 2002. ITC Code updated in August 2002 says "No advertisement may encourage or condone dangerous, inconsiderate or irresponsible driving". DfT has commented on the draft revised ASA/CAP code. Revision of ASA/CAP Code completed. | Action completed.