## calculator
Estimate Preparation Cost/Schedule Calculator
Only includes cost and time for the cost estimating function - does not include costs for the project team
or engineering to develop the deliverables that define the project scope and form the project estimate basis.
Est. Title:
Est. ID #:
Estimator:
General Form of Cost Estimating Relationship: Estimate Preparation Cost = C + K(project cost)^e
BASE PARAMETERS:
1) Enter best quess of total project costs for scope to be estimated (in US $): | 10000000
(Note: do not include project costs estimated by others) |  |  |  | C = | 640
2) Enter Estimate Classification (5,4,3,2, or 1): | 1 |  |  | K = | 1.6
(Refer to AACE International's cost estimate classification Recommended Practices: |  |  |  | e = | 0.6
-Level of Project Definition/Completion of Deliverables: Class 5=0-2%, 4=1-5%, 3=10-40%, 2=30-60%, 1=50-100%
-Typical names for class: Class 5=ROM, 4=Concept, 3=Budget/Authorization, 2=Definitive/Control, 1=Bid/Tender/Detail
3) Enter the number of estimate "sub-parts" that will more or less be
estimated as separate projects by separate individuals or sub-groups: | 5
(e.g. utilities + services + process1 + process2 +g&a/oh&p = 5)
(Note: this subdivides the estimating work into this many parts and estimates prep costs for each part
individually. Estimating work may be segregated by process "units, areas, or system", or by trade/discipline, but do not
count these as "sub-parts" unless the estimating team organization/procedure treats them as relatively distinct entities
with different estimators responsible for that part of the work.
ADJUSTMENT FACTORS (productivity, quality, complexity, etc.): |  |  |  |  | factor4 =
4) Enter Project/Process Technical Complexity (also state of R&D, QA, etc.) | 3 |  |  |  | 1
(1=bldgs, 2=repeat chem, 3=chem plant , 4=advanced chem, 5=pilot chem, 6=aero/nuc 7=advanced aero/nuclear) |  |  |  |  | factor5 =
5) Rate the quality of project team cooperation and input to the estimate: | 4 |  |  |  | 1
(Scale of 1 to 7: 1 = best, 4 = average-good practice, 7 = very poor,
assumes that improving the quality of input to the project basis improves the efficiency of the estimating process)
6) Enter Percentage (whole number) of costs for which a special parametric |  |  |  |  | factor6 =
modeling or automated estimated systems will be used: | 0 |  |  |  | 1
(assumes automated or custom tools improves the efficiency of the estimating process, excludes common software and digitizers,
applies mostly to Class 5,4, or 3 R.O.M. or conceptual estimates)
Rate the expected "estimating process" complexity level and availability of good reference
data or history relative to your normal expectations for this class of estimate and |  |  |  |  | factor7 =
type of project: | 4 |  |  |  | 1
(Scale of 1 to 7: 1 = no complexity/copy job, 4 = standard process-good data, 7 = very complex/little to no data) |  |  |  |  | cum factor
of above =
RESOURCING/SCHEDULE FACTORS: |  |  |  |  | 1
Enter equivalent no.# of full-time estimators involved: | 8
(effects the minimum schedule duration only....this value is generally = or > the number of estimate "sub-parts")
Estimating Labor Rate in $/hour: | 80
(all-in rate including burdens, benefits, overhead, and profit)
Range
|  | High | Low
RESULTS: | Point Estimate | 50% | -30%
Total Estimated Preparation Costs: | 48900 | 73350 | 34230
Estimate Preparation Costs as % of Total Project Costs: | 0.489% | 0.7335% | 0.3423%
Total Estimating Labor Hours: | 611 | 916.5 | 427.7 |  | time scaler
Theoretical Minumum Estimating Duration in Working Days @ 6hr/person-day: | 13 | 19.5 | 9.1 |  | used in equation
Predicted Estimating Duration in Calendar Days including delays, etc. | 43 | 64.5 | 30.1 |  | 0.8
(duration excludes project time to produce the deliverables that define the project scope and form the basis of estimate)
Note: this model is provided as an educational example of technology
developed and used by cost engineers. Use at your own risk.