## In Process
University Systems Maintenance Projects
Financial Information Services
Task | Task No. | Type | Group | Dev Name | Client Office | Client Contact | System | ECD | ACD | Status | Time Estimate (hours) | Time Actual (hours)
Addition of two fields to the HRMS parking deduction file for Parking use |  | M | FIS | Ayers | Parking | Valdez | HRMS | 20031208 | 20031212 | D | 4
Additional Personnel Retiree Database Enhancements |  | E | FIS | Ayers | PER | May | Retiree | 20031219 |  | S | 8
Provide reporting support for Pinnacle System |  | M | FIS | Ayers | ICT | Para | Pinnacle | 20031219 |  | S | 80
United Way Campaign Support |  | M | FIS | Ayers | ENGR | Creed | UW | 20040105 |  | P | 60
ERB reporting changes - FTE Fix |  | P | FIS | Bagwell | PAYR | Stuart | HRMS | 20031114 |  | P | 4
Modify Student Payroll Requistions Report - HRSZ0200 |  | D | FIS | Bagwell | SP | Aranda | SES | 20031114 |  | S | 8
Modify W2 print to accommodate 457(b) elective deferral plan |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031212 |  | P | 40
Implement money card payroll deduction feed |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031218 |  | P | 40
HRMS 2003 Year-End Phase I Release including EPCN for Texas Quarterly Reporting |  | M | FIS | Bagwell Wang | PAYR/PER | Stuart | HRMS | 20031219 | 20031219 | D | 25
HRMS 2002 Year-End Phase II Release |  | M | FIS | Bagwell Wang | PAYR/PER | Stuart | HRMS | 20040107 |  | W | 25
Route SAR reports to e~print (SARZ5035/036 |  | M | FIS | Hammersmith | UAR | Kienhe | SAR | 20031219 |  | A | 4
Develop Business requirements document for accepting credit cards via the Web for Housing, Dining Services, Parking, etc. |  | E | FIS | Jeffries | Housing | Giacomelli | Housing | 20031219 |  | P | 32
Review SEVIS reporting requirements for HRMS |  | M | FIS | Jeffries | CIP | Jasper | HRMS | 20031219 |  | P | 40
Develop Service Level Agreements (SLAs) for Production Systems within FIS |  | M | FIS | Jeffries | FIS | Wilson | HRMS EAF FRS | 20040123 |  | P | 40
Key:
Status Codes: |  |  | Types: |  |  | Group: |  | Dates:
W - Waiting resources/requirements |  |  | D - Development |  |  | FIS |  | ECD - estimated completion date
C - Cancelled |  |  | E - Enhancement |  |  | SIS |  | ACD - actual completion date
A - Analysis |  |  | M - Maintenance |  |  | DRS |  | (format - ccyymmdd)
P - Programming |  |  | P - Problem |  |  | SP
T - Developer testing |  |  | R - Report |  |  | US
S - Client testing/signoff |  |  | T- Training
D - Done |  |  | U- Urgent
H - Hold
I - Instruction

## Completed
University Systems Maintenance Projects
Financial Information Services
Project Description | Task No. | Type | Group | Dev Name | Client Office | Client Contact | System | ECD | ACD | Status | Time Estimate (hours)
Rejected EAF problem |  | P | FIS | Jeffries | PER | Quintana | HRMS | 20010115 | 20010102 | D | 4
Alter HRMS department table RI to accommodate deletion rules |  | M | FIS | Wang | IRP | Meyer | HRMS | 20011221 | 20010104 | D | 6
Employee History Date Problem |  | P | FIS | Wright Bagwell | PER | Quintana | HRMS | 20010215 | 20010220 | D | 6
Annual Leave Cutoff | 411 | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010227 | 20010227 | D | 6
Internet Explorer Error | 466 | P | FIS | Kelley | FSA | Rumford | EAF | 20010312 | 20010313 | D | 2
No. Checks for Term Code 8 & 9 | 233 | M | FIS | Bagwell Montoya | PAYR | Throneberry | HRMS | 20010302 | 20010316 | D | 16
HRMS New Release - Mid Yr/Yr-end Phase 1&2 |  | M | FIS | Montoya Bagwell | FSA | Baca | HRMS | 20010131 | 20010316 | D | 160
Sweep TA800 Field | 463 | U | FIS | Wright | FSA | Ross | FRS | 20010316 | 20010316 | D | 4
AQT Brownbag |  | T | FIS | Bagwell | ICT | N/A | HRMS | 20010322 | 20010322 | D | 40
Travel Authorization changes (analysis only) | 429 | M | FIS | Wright | FSA | Baca | FRS | 20010325 | 20010325 | D | 20
Apply TMN 289 programming changes | 471 | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010326 | 20010326 | C
EAF Reject Problem |  | M | FIS | Bagwell | PER | Quintana | HRMS | 20010328 | 20010326 | D | 6
Routing Template Display Problem | 470 | P | FIS | Kelley | FSA | Rumford | EAF | 20010328 | 20010330 | D | 25
EAF feed all data-FICA change related to Visa type | 426 | M | FIS | Bagwell | PAYR | Byford | HRMS | 20010307 | 20010406 | D | 8
EAF Feed all data - UI Eligibility Change | 472 | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20010326 | 20010406 | D | 10
Resolve URL length problem |  | P | FIS | Kelley | FSA | Baca | EAF | 20010410 | 20010409 | D | 7
User Login to EAF | 252 | M | FIS | Kelley | FSA | Baca | EAF | 20010405 | 20010410 | C
Problem - Requisition 19996643 | 31 | M | FIS | Kelley | FSA | Baca | EAF | 20010410 | 20010410 | C
Earnings Type Table Change |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010510 | 20010411 | D | 4
FRS GL Account marked for deletion | 479 | M | FIS | Wright | FSA | Rumford | FRS | 20010410 | 20010411 | D | 4
Change text on Purchase Order | 488 | U | FIS | Wright | FSA | Ross | FRS | 20010412 | 20010416 | D | 2
EAF Personnel Edit Capability (Analysis only) | 453 | E | FIS | Kelley | FSA | Rumford | EAF | 20010309 | 20010417 | D | 4
Do not process A/L accrual on RA transactions | 412 | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010316 | 20010419 | D | 6
Individual not listing as approver | 480 | P | FIS | Kelley | FSA | Rumford | EAF | 20010410 | 20010419 | D | 20
Sweep POA18 field |  | M | FIS | Wright | FSA | Ross | FRS | 20010423 | 20010423 | C
HRMS database error 181 application PR04 | 489 | M | FIS | Bagwell | FSA | Ross | HRMS | 20010425 | 20010424 | D | 5
Implement Travel Authorization Changes (option 1A) | 483 | E | FIS | Wright | FSA | Ross | FRS | 20010424 | 20010424 | D | 24
Modification to ICT Inventory File |  | M | FIS | Hammersmith | ICT | Quintana | FRS | 20010425 | 20010425 | D | 4
Posting Details | 391 | M | FIS | Kelley | FSA | Baca | EAF | 20010427 | 20010427 | D | 3
PSL Employee Feed | 392 | M | FIS | Kelley | FSA | Baca | EAF | 20010427 | 20010427 | D | 5
Initialize "PI" info when option to route to PI is 'NO' | 324 | M | FIS | Kelley | FSA | Baca | EAF | 20010429 | 20010427 | D | 6
Student Eligibility Check Prior to Routing | 319 | E | FIS | Kelley | FSA | Baca | EAF | 20010430 | 20010427 | D | 280
EAF Change Exec VP to Provost | 457 | M | FIS | Kelley | FSA | Rumford | EAF | 20010425 | 20010429 | C
EAF Add VP Research Routing Option | 458 | E | FIS | Kelley | FSA | Rumford | EAF | 20010429 | 20010429 | C
Modification to Screen 250 - POB04 field | 496 | M | FIS | Hammersmith | FSA | Ross | FRS | 20010501 | 20010501 | D | 2
Cancel Student Requistions | 503 | M | FIS | Kelley | FSA | Rumford | EAF | 20010502 | 20010501 | D | 4
Leave Accrual Plan Update | 347 | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010502 | 20010502 | C
Check Print ASCII Format (Analysis Only) | 495 | M | FIS | Bagwell | FSA | Baca | HRMS | 20010502 | 20010502 | D | 2
PROVOST Departmental Listing problem | 481 | P | FIS | Kelley | FSA | Rumford | EAF | 20010412 | 20010503 | D | 16
Registration Document Change |  | M | FIS | Ramirez | UAR | Kiehne | SAR | 20010504 | 20010504 | D | 3
FRS Account Load Program Fix |  | U | FIS | Bagwell | PAYR | Stuart | HRMS | 20010507 | 20010507 | D | 6
FFX Project Request | 502 | U | FIS | Hammersmith | FSA | Ross | FRS | 20010507 | 20010507 | D | 4
Down Payment Change for Fall 2001 |  | M | FIS | Montoya Ramirez | UAR | Kiehne | SAR | 20010501 | 20010516 | D | 32
CASHNET Check Writer Feed File Layout |  | M | FIS | Montoya | FSA | Rumford | FRS | 20010517 | 20010517 | D | 2
Investigate problem w/ Salary Letter Date |  | P | FIS | Wright | PER | Quintana | HRMS | 20010518 | 20010518 | D | 4
SARZ5025 FTP Modification |  | M | FIS | Ramirez | UAR | Kienhe | SAR | 20010521 | 20010521 | D | 4
Apply Wage Attachment Fix (TPF 010322.ZIP) |  | M | FIS | Bagwell | PAYR | Roggow | HRMS | 20010521 | 20010522 | D | 16
Investigate problem w/ Salary Report HRSZ2040 |  | P | FIS | Wright | PER | Alvarez | HRMS | 20010522 | 20010522 | D | 4
HRMS OS/390 Testing |  | M | FIS | Bagwell | ICT | Risinger | HRMS | 20010525 | 20010525 | D | 24
Quarterly Processing Change |  | M | FIS | Montoya | PAYR | Stuart | HRMS | 20010608 | 20010531 | D | 4
Tax Relief Act Reporting | 298 | E | DRS/FIS | Ramirez | UAR | Kiehne | SAR | 20010731 | 20010711 | D | 32
Meal Load Problem |  | P | FIS | Ramirez | HOUS | Giacomelli | SAR | 20010531 | 20010712 | D | 24
EFT of Financial Aid to Banks | 299 | E | FIS | Montoya | UAR | Kiehne | SAR | 20010731 | 20010713 | C
SARZ5021 FINAL Run control |  | M | FIS | Ramirez | UAR | Kiehne | SAR | 20010731 | 20010719 | D | 10
Create allowance pay differentials |  | M | FIS | Bagwell | ICT | Throneberry | HRMS | 20010723 | 20010723 | D | 4
FRS Year-End Support |  | M | FIS | Wright Montoya Hammersmith | FSA | Baca | FRS | 20010807 | 20010807 | D | 120
Building Useful Life Table for CHE Reporting | 501 | M | FIS | Hammersmith | FSA | Ross | FRS | 20010731 | 20010814 | D | 40
Add new column to CHE Report |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20010731 | 20010814 | D | 16
CHE Report Reconciliaton | 438 | M | FIS | Hammersmith | FSA | Baca | FRS | 20010810 | 20010814 | D | 16
Class Schedule/Fee Statement Change for Tribal Orgs |  | M | FIS | Ramirez | UAR | Kienhe | SAR | 20010815 | 20010814 | D | 32
Screen 045 Labor Expense Change |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010820 | 20010827 | D | 32
DBAZ0045 Revised Sort |  | M | FIS | Wright | FSA | Taylor | FRS | 20010828 | 20010829 | D | 2
Payroll M204 Data Archive Requirements | 511 | M | FIS | Wright | PAYR | Roggow | HRMS | 20010531 | 20010831 | D | 24
HRMS Fiscal Year End Support |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010831 | 20010901 | D | 48
EAF Requisitions not passing eligibility | 560 | P | FIS | Wang | FSA | O'Larey | EAF | 20010831 | 20010906 | D | 2
Student Titles |  | M | FIS | Wright | PER | Quintana | HRMS | 20010531 | 20010912 | D | 40
10/12 expense accrual | 394 | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010531 | 20010918 | D | 50
10/12 Expense Accrual |  | P | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010918 | 20010918 | D | 32
Feed to HRMS from SAR for grad payroll deductions |  | E | FIS | Montoya | UAR | Kiehne | SAR | 20010901 | 20010919 | D | 40
Problem with RCGOLD | 566 | P | FIS | Wang | FSA | O'Larey | EAF | 20010920 | 20010920 | D | 3
SARZ5035/6 FTP |  | M | FIS | Ramirez | UAR | Kiehne | SAR | 20010731 | 20010926 | D | 24
SAR Cross Training |  | T | FIS | Montoya Ramirez | UAR | Kienhe | SAR | 20011231 | 20011001 | D | 200
United Way Data Entry Operator Form change |  | M | FIS | Wang | EDUC | Moorehead | UW | 20010928 | 20011001 | D | 4
EAFs not feeding to HRMS | 563 | M | FIS | Wang | FSA | O'Larey | EAF | 20011005 | 20011007 | D | 2
Invalid Dates in FPR Backfeed data |  | P | FIS | Hammersmith | PPD | La Torra | FRS | 20011012 | 20011012 | D | 2
CHE Reporting Project changes |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20011115 | 20011015 | D | 24
New paycheck distribution code for EEO ADA on HRMS |  | M | FIS | Jeffries | IRP | Meyer | HRMS | 20011019 | 20011019 | D | 1
Modifications to HRSZ0160 - Library Interface |  | M | FIS | Ayers | LIB | Boyse | HRMS | 20011031 | 20011025 | D | 4
Benefits Base & Annual Salary |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010727 | 20011025 | D | 40
Summary Unit change for branches from CC to separate acronym |  | M | FIS | Wang | IRP | Meyer | HRMS | 20011031 | 20011106 | D | 10
Investigate incorrect HRMS LE Feed to FRS - Schedule 102 |  | P | FIS | Bagwell | PAYR | Throneberry | HRMS | 20011026 | 20011108 | D | 2
Resolve problem with salary roll |  | P | FIS | Wright | PER | Quintana | HRMS | 20010831 | 20011109 | D | 32
Additions to Parking Deduction Feed |  | M | FIS | Wright | PAYR | Stuart | HRMS | 20011203 | 20011112 | D | 10
EAF Templates 32K Space Problem | 559 | P | FIS | Wang | FSA | O'Larey | EAF | 20011031 | 20011117 | D | 32
Routing Templates not obtaining approval names on EAF | 577 | P | FIS | Wang | FSA | O'Larey | EAF | 20011031 | 20011117 | D | 4
Addendum to Routing Template w/ 32K Problem | 580 | P | FIS | Wang | FSA | O'Larey | EAF | 20011031 | 20011117 | D | 3
Add columns to FBX010EP/FBX011EP |  | M | FIS | Hammersmith | OFS | Puckett | FRS | 20011130 | 20011203 | D | 5
TX Transaction Errors |  | P | FIS | Wang | PAYR | Roggow | HRMS | 20011207 | 20011204 | D | 7
HRSZW220 Report Modifications |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20011212 | 20011207 | D | 2
Turn off the feed of the EAF Degree Information to HRMS | 595 | M | FIS | Wang | FSA | O'Larey | EAF | 20011221 | 20011209 | D | 24
Additions to Comments Report in EAF | 574 | M | FIS | Ayers | FSA | O'Larey | EAF | 20011031 | 20011210 | D | 5
Investigate problem with HRSZ0260 report |  | P | FIS | Ayers | PER | Macrorie | HRMS | 20011031 | 20011210 | D | 4
FBX001EP Modification |  | M | FIS | Hammersmith | FSA | Marten | FRS | 20011205 | 20011210 | D | 3
HRMS Year-end Phase I release install |  | M | FIS | Wang | PAYR | Throneberry | HRMS | 20011214 | 20011212 | D | 32
HRMS February/Mid-year 2001 release install |  | M | FIS | Wang Montoya | PAYR | Throneberry | HRMS | 20011015 | 20011212 | D | 40
HRMS Student Purge |  | E | FIS | Bagwell | PAYR | Roggow | HRMS | 20011214 | 20011213 | D | 48
Resolve problem with blank account lines on JAs |  | M | FIS | Bagwell | PAYR | Roggow | HRMS | 20011221 | 20011217 | D | 3
Federal Flag for Implied Maintenance |  | M | FIS | Bagwell Wang | PAYR | Roggow | HRMS | 20010927 | 20020104 | D | 6
HRMS Year-end Phase II release install |  | M | FIS | Wang | PAYR | Throneberry | HRMS | 20020115 | 20020107 | D | 16
United Way Campaign Support |  | M | FIS | Bagwell Wang Ayers | EDUC | Moorehead | UW | 20020105 | 20020110 | D | 120
Evaluate/Rewrite all United Way Crystal reports |  | M | FIS | Ayers | ICT | Jeffries | UW | 20011119 | 20020111 | D | 40
1099 Regulatory Updates |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20011221 | 20020111 | D | 20
Home Department Selection List | 619 | M | FIS | Wang | FSA | O'Larey | EAF | 20020123 | 20020114 | D | 2
Annual Leave Accrual Modification | 617 | M | FIS | Wang | FSA | O'Larey | EAF | 20020118 | 20020124 | D | 4
Allow blank in campus mail stop field |  | M | FIS | Wang | IRP | Meyer | HRMS | 20020215 | 20020124 | D | 4
Campus Directory Changes |  | M | FIS | Ayers | UC | Feldman | HRMS | 20020125 | 20020128 | D | 4
Problem with EAF Passwords | 579 | P | FIS | Wang | FSA | O'Larey | EAF | 20011031 | 20020128 | C
ERB Mandatory Reporting Changes |  | M | FIS | Bagwell Wang | PAYR | Throneberry | HRMS | 20020131 | 20020131 | D | 160
Format on Position Number & Pay Base Start/Stop Dates | 618 | M | FIS | Wang | FSA | O'Larey | EAF | 20020118 | 20020207 | D | 7
Feed to OFS of employee/department data |  | M | FIS | Ayers | OFS | Puckett | HRMS | 20011130 | 20020208 | D | 5
Apply ZSIBM287 |  | M | FIS | Hammersmith | ICT | Jeffries | FRS | 20020215 | 20020211 | D | 6
Company ID Coding Changes |  | M | FIS | Wang | FSA | Roggow | HRMS | 20020201 | 20020214 | D | 10
Modifications to HRSZ0710 & NMSU Department Table to accommodate long address |  | M | FIS | Hammersmith Wang | IRP/PER | Meyer Macrorie | HRMS | 20020329 | 20020325 | D | 7
HRMS February 2002 new release install |  | M | FIS | Wang | PAYR/PER | Throneberry Quintana | HRMS | 20020328 | 20020328 | D | 8
Modifications to Implied Maintenance |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20020403 | 20020403 | D | 12
Purchase Requisition changes for dual year processing | 646 | M | FIS | Hammersmith | FSA | Ross | FRS | 20020415 | 20020503 | D | 4
Automate changes to FBY005.01 file | 571 | M | FIS | Hammersmith | FSA | Ross | FRS | 20020401 | 20020509 | D | 5
Copy HRMS Prod to HRMS Dev for testing leave corrections |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20020529 | 20020520 | D | 3
FRS Batch Processing improvements including steps to eliminate day lag and automate feeds into FRS |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20020628 | 20020520 | D | 120
Make required changes to HRMS job streams which use CHKTHRD |  | M | FIS | Ayers | ICT | Jeffries | HRMS | 20020522 | 20020522 | D | 4
Resolve processing problems with SAR Billing Statement |  | M | FIS | Ayers | UAR | Kiehne | SAR | 20020524 | 20020523 | D | 4
Add signatures to salary letters for professionals |  | E | FIS | Ayers Wang | PER | Quintana | HRMS | 20020601 | 20020524 | D | 80
Modify Student Eligibility Criteria Check program | 662 | M | FIS | Wang Shaa | FSA | O'Larey | EAF | 20020524 | 20020524 | D | 24
HRMS Laser Print Implementation of Payroll Checks/Advices |  | E | FIS | Bagwell Wang | PAYR | Throneberry | HRMS | 20020531 | 20020531 | D | 160
Modify Graduate School field on EAF | 649 | M | FIS | Wang | FSA | O'Larey | EAF | 20020419 | 20020531 | D | 6
Change current URL address for the Print Blank Forms link | 670 | M | FIS | Wang | FSA | O'Larey | EAF | 20020530 | 20020531 | D | 2
Modify Graduate School field on EAForm2 | 669 | M | FIS | Wang | FSA | O'Larey | EAF | 20020530 | 20020531 | D | 3
Student and GA FICA modification |  | M | FIS | Wang | PAYR | Stuart | HRMS | 20020603 | 20020531 | D | 6
Update Security on Form | 10 | M | FIS | Wang | FSA | Baca | EAF | 20010406 | 20020601 | D | 80
Problem with accessing EAF when a name change occurs | 593/596 | M | FIS | Wang | FSA | O'Larey | EAF | 20011221 | 20020601 | D | 40
ICT Employee Listing for travel processing |  | M | FIS | Ayers | ICT | Quintana | HRMS | 20020612 | 20020607 | D | 8
Create English/Math Placement report for NSO |  | R | FIS | Ayers | Math | Talamantes | Vistas | 20020614 | 20020614 | D | 5
Modify PP3501NM to accommodate proration adjustments by FTE |  | M | FIS | Wang | PER | Quintana | HRMS | 20020617 | 20020614 | D | 7
Modify EEO Reports to use appointment begin date |  | R | FIS | Ayers | PER | Macrorie | HRMS | 20020620 | 20020619 | D | 4
Test print check numbers |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20020726 | 20020625 | D | 5
Manual Check Printing using Create-a-check software |  | E | FIS | Bagwell Wang | PAYR | Stuart | HRMS | 20020731 | 20020711 | D | 40
Job Scheduler Implementation - HRMS Daily |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20020731 | 20020718 | D | 160
Provide Annual/Sick Leave balances electronically to OFS |  | R | FIS | Ayers | OFS | La Torra | HRMS | 20020719 | 20020719 | D | 3
Job Scheduler Implementation - HRMS Weekly |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20020731 | 20020719 | D | 32
HRMS PERI040 Research |  | M | FIS | Wang | SES | Barton | SES | 20020719 | 20020722 | D | 1
Labor Expense Errors |  | P | FIS | Bagwell | PAYR | Throneberry | HRMS | 20010928 | 20020723 | D | 40
Resolve problems with EAF Disapproval Process | 683 | M | FIS | Wang | FSA | O'Larey | EAF | 20020726 | 20020723 | D | 4
Resolve problem with grad tuition transactions |  | M | FIS | Montoya | PAYR | Stuart | HRMS | 20020731 | 20020724 | D | 15
FFX equipment inventory updates based on Hirons and Associates data collection |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20020731 | 20020725 | D | 24
FRS Year-end Support |  | M | FIS | Hammersmith | FAO | Ross | FRS | 20020731 | 20020731 | D | 80
Modification to program HRSZ2140 |  | M | FIS | Bagwell | PER | Quintana | HRMS | 20020726 | 20020805 | D | 5
Review NMS977-NMS97F packs prior to reformatting |  | M | FIS | Bagwell Wright | ICT | Wilson | M204 | 20020809 | 20020810 | C
Create labels for postcards |  | R | FIS | Ayers | ADM | Wilson | Banner | 20020731 | 20020816 | D | 4
Modify HRSZ0770 Account Number Flip-Flop Process |  | M | FIS | Wang | PAYR | Stuart | HRMS | 20020830 | 20020823 | D | 40
HRSZW220 Fringe Benefit Modification |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20020731 | 20020826 | D | 4
HRMS - Acct Line Start Date = Stop Date |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20020827 | 20020827 | D | 4
Implement GASB35 requirements TOS | 482 | M | FIS | Hammersmith | FSA | Ross | FRS | 20010416 | 20020828 | D | 160
Perform analysis on automating FBX010EP and FBX011EP load processes |  | M | FIS | Jeffries | OFS | La Torra | FRS | 20020831 | 20020831 | D | 2
Modify Telephone Directory file to include Empl Type for Faculty Listserve |  | M | FIS | Ayers | ICT | Cooper | HRMS | 20020913 | 20020909 | D | 2
Job Scheduler Implementation - HRMS List |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20021015 | 20020909 | D | 160
Modify Monthly ICT WO feed file |  | M | FIS | Hammersmith | ICT | Montano | FRS | 20020930 | 20020911 | D | 2
E-mail Billing via FRS |  | M | FIS | Hammersmith | ICT | Thompson | FRS | 20020930 | 20020912 | D | 4
Investigate problem w/ bank accts (2282154) |  | P | FIS | Jeffries | FSA | Rumford | FRS | 20021031 | 20020926 | C
Problem with Duplication of EAF Requisitions | 576 | P | FIS | Wang | FSA | O'Larey | EAF | 20020930 | 20020926 | C
Create report for determining length of time to hire additional pay jobs where primary job equals faculty |  | M | FIS | Ayers | Business & Finance | Noel | EAF | 20020913 | 20021002 | D | 3
HRMS 2002 Mid-Year Maintenance Release |  | M | FIS | Wang | PAYR/PER | Throneberry Quintana | HRMS | 20021004 | 20021004 | D | 40
Restore HRMS Dev with LEF data |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20021010 | 20021010 | D | 6
Restore FRS Dev to pick up PPD drops as of 7/14/2002 |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20021031 | 20021030 | D | 2
Modify HRSZ0140 to add employee type for LDAP |  | M | FIS | Ayers | USA | Ian | HRMS | 20021031 | 20021031 | D | 3
Automatic feed of UAR's manual check file into FRS |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20021031 | 20021106 | D | 6
Investigate reported problem with EAF feed to PER034 |  | P | FIS | Wang | PER | Quintana | EAF | 20021101 | 20021106 | D | 5
Depreciation reports for ICT |  | M | FIS | Hammersmith | ICT | Montano | FRS | 20021115 | 20021118 | C
Restore ftp file created by HRSZ0450 on 10/29/02 | 651 | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20021121 | 20021121 | D | 2
Route HRSZ0450 report to e~print | 650 | M | FIS | Hammersmith | FSA | Baca | HRMS | 20021122 | 20021121 | D | 2
Procurement Card Workflow Project |  | D | FIS | Wang Bagwell | Business & Finance | Noel | WF | 20030115 | 20021121 | D | 250
PBM095 output to e~Print |  | M | FIS | Hammersmith | FSA | Ross | FRS | 20021125 | 20021125 | D | 4
EAF Data Archival Project | 539 | E | FIS | Wang | FSA | O'Larey | EAF | 20021031 | 20021125 | D | 40
Sweep PROCURE CARD field on HRMS to 'Y' |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20021206 | 20021126 | D | 2
Route VBY110 output to e~Print |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20020803 | 20021126 | D | 24
Disbursement mods to FRS |  | M | FIS | Hammersmith | ICT | FIS | FRS | 20021101 | 20021126 | D | 10
Perform request to receive HRSZ0390 report electronically | 628 | M | FIS | Unassigned | FSA | O'Larey | EAF | 20021115 | 20021127 | C
Modify Pay Rate Field on EAForm3 | 709 | M | FIS | Wang | FSA | O'Larey | EAF | 20021031 | 20021127 | D | 6
HRSZ0750 - ERB List and Tape |  | M | FIS | Wang | PER | Macrorie | HRMS | 20021115 | 20021127 | D | 4
Implementation of W-2 Processing on Laser Printer |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20021206 | 20021204 | D | 30
Evaluation of Crystal Reports/MS Access/Excel |  | M | FIS | Ayers | FIS | Jeffries | All | 20021219 | 20021220 | D | 40
Evaluate EAF Project List |  | M | FIS | Jeffries | US | Wilson | EAF | 20021213 | 20021220 | D | 10
HRMS 2002 Year-End Phase I Release |  | M | FIS | Wang | PAYR/PER | Throneberry Quintana | HRMS | 20030110 | 20030103 | D | 40
HRMS 2002 Year-End Phase II Release |  | M | FIS | Wang | PAYR/PER | Throneberry Quintana | HRMS | 20030110 | 20030103 | D | 40
United Way Support |  | M | FIS | Ayers Bagwell | ENGR | Creed | UW | 20030110 | 20030106 | D | 40
MVS File Cleanup |  | M | FIS | All | MSA | Roberts | All | 20021220 | 20030109 | D | 15
Evaluate alternative vendor for training |  | M | FIS | Jeffries | US | Wilson | All | 20021213 | 20030114 | D | 4
Clone HRMS Screen PERI014 for Graduate School input |  | M | FIS | Wang | IRP | Meyer | HRMS | 20030131 | 20030115 | D | 8
Implement TOS FRIBM122 - 1099 regulatory changes |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030131 | 20030116 | D | 5
Test Procurement Card file feed into FRS |  | M | FIS | Hammersmith | FSA | Baca | FRS | 20030115 | 20030116 | D | 3
Implement TOS FRIBM127-1099 Laser Forms |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030124 | 20030123 | D | 4
Resolve FPR invoice date feed problem |  | M | FIS | Hammersmith | OFS | Puckett | FRS | 20021213 | 20030127 | D | 3
Migrate HRSZ1210 (Student Purge) to HRMS Production |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20030228 | 20030131 | D | 2
Resolve PAR Job Issues |  | M | FIS | Bagwell | Controller | Byford | HRMS | 20021220 | 20030206 | D | 10
Provide information from Vistas/HRMS on Visa Types |  | R | FIS | Ayers | PER | Jasper | HRMS | 20030131 | 20030214 | D | 5
Personal Data Report |  | R | FIS | Ayers | PER | Quintana May | HRMS | 20030214 | 20030224 | D | 120
Remove all FBM061 reports fiscal monitor attribute from MFICHE |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030301 | 20030228 | D | 2
Modify Student Eligibility Programs to exclude regular student - HRSZ0220/REGZ5254 |  | D | FIS | Wang | SP | Aranda | SES | 20030228 | 20030228 | D | 12
Generate EAF Comments Report |  | M | FIS | Ayers Wang | Business & Finance | Noel | EAF | 20030228 | 20030303 | D | 2
Generate EAF Routing Template Report |  | M | FIS | Ayers Wang | Business & Finance | Noel | EAF | 20030307 | 20030303 | D | 5
Resolve retirement monlthy "U" balance problem |  | M | FIS | Wang | PAYR | Stuart | HRMS | 20030307 | 20030304 | D | 4
Allow access to Ag property data only | 723 | M | FIS | Montoya | FSA | Ross | FRS | 20030304 | 20030306 | D | 2
Change max age of hire on EAF from 85 to 99 | 736 | M | SP | Rogers | FSA | O'Larey | EAF | 20030303 | 20030307 | D | 2
Adding new Visa Type Values to EAF and removal of 'other' pay base option on EAF | 721 | M | SP | Rogers | FSA | O'Larey | EAF | 20030303 | 20030307 | D | 2
Include schedule 12B & 12D in VCFILE | 737 | M | FIS | Montoya | AFR | Ross | FRS | 20030304 | 20030307 | D | 3
Create FTP output files from FBX010EP & FBX011EP | 724 | M | FIS | Hammersmith | FSA | Ross | FRS | 20030314 | 20030310 | D | 3
Split HRSZ0450 e~Print report by campus of the account that it is paid on | 729 | M | FIS | Bagwell | AFR | Ross | FRS | 20030311 | 20030311 | D | 8
Provide HRMS data to ERA InfoED system |  | M | FIS | Ayers |  |  | HRMS | 20030311 | 20030313 | D | 5
Develop EAF Edits Document |  | M | FIS | Wang | PAYR | Throneberry | EAF | 20030321 | 20030326 | D | 32
Proof of concept using Stored Procedures/Appl Security |  | M | FIS | Wang | FIS | Jeffries | FRS | 20030331 | 20030331 | D | 10
Evaluate SPA reporting |  | M | FIS | Jeffries | Business & Finance | Noel | FRS | 20030331 | 20030331 | D | 3
Modify Graduate Deduction Program to code for unavailable resource |  | M | FIS | Wang | UAR | Kiehne | HRMS | 20030418 | 20030409 | D | 3
Provide inventory assistance to Computer Science dept. |  | M | FIS | Jeffries | CS | Strnad | FRS | 20030407 | 20030418 | D | 2
Resolve NMSU Retiree Org problem |  | M | FIS | Wang | PAYR | Stuart | HRMS | 20030418 | 20030418 | D | 5
Add signatures to salary letters for classified employees and add field to PERU034 |  | E | FIS | Wang | PER | Quintana | HRMS | 20030411 | 20030422 | D | 60
Test the reuse of accounts payable check numbers |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030425 | 20030425 | D | 4
Upgrade on e~Print security extract program | 733 | M | FIS | Hammersmith | FSA | Ross | FRS | 20030502 | 20030428 | D | 3
Provide student payroll layout to USA group |  | M | FIS | Montoya | CS | Cooper | HRMS | 20030508 | 20030508 | D | 2
Fix options available on HCF section upon disapproval | 726 | M | FIS | Wang | FSA | O'Larey | EAF | 20030331 | 20030517 | D | 4
Changes to section titles of EAF/Heading using the word "Form" in EAF | 731 | M | FIS | Wang | FSA | O'Larey | EAF | 20030404 | 20030517 | D | 6
ERB Return To Work Program Policy Change |  | E | FIS | Wang Bagwell | Controller | Byford | HRMS | 20030418 | 20030517 | D | 80
Assist in bank reconciliation for December |  | M | FIS | Montoya | AFR | Ross | FRS | 20030523 | 20030521 | D | 4
Develop training documentation for using Excel with DB2 |  | M | FIS | Ayers | US | Wilson | ALL | 20030523 | 20030522 | D | 10
Send FJYREND1 to e~Print | 674 | M | FIS | Hammersmith | AFR | Ross | FRS | 20030505 | 20030522 | D | 3
MANTIS modifications (REGM0001, TBLM0001, REGM0403, REGM0413, REGM0414) |  | D | FIS | Montoya | SIS | Allwood | VISTAS | 20030606 | 20030603 | D | 40
Implement TOS FXIBM019 and FRIBM134 |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030606 | 20030605 | D | 5
Automate process for creating YTD transaction file |  | M | FIS | Hammersmith | FIS | Jeffries | FRS | 20030715 | 20030612 | D | 10
Include ZBA900 in APDAILY |  | M | FIS | Hammersmith | FIS | Jeffries | FRS | 20030630 | 20030613 | D | 6
Evaluate the possibility of automating the bank process for Bank 26 - Carlsbad | 765 | E | FIS | Montoya | AFR | Ross | FRS | 20030725 | 20030617 | D | 10
Make revisions to telephone directory memo |  | M | FIS | Ayers | PER | Padilla | HRMS | 20030606 | 20030624 | D | 3
Create labor expense data file to be requested annually |  | M | FIS | Bagwell | PAYR | Throneberry | HRMS | 20030613 | 20030630 | D | 10
Implement process improvements for SPA billing - modification to FBM090/91 fiscal monitor reports to sort by GCA grouping |  | M | FIS | Hammersmith | Business & Finance | Noel | FRS | 20030627 | 20030630 | D | 12
Perform analysis on Streamlining the Supplemental Compensation Approval Process | 750 | A | FIS | Wang | FSA | O'Larey | EAF | 20030617 | 20030704 | D | 24
Implement direct transmission of Payroll ACH file to bank |  | M | FIS | Bagwell | FSA | Baca | HRMS | 20030620 | 20030707 | D | 24
Systems Evaluation - FRS |  | M | FIS | Montoya | Business & Finance | Noel | FRS | 20030731 | 20030707 | D | 40
Idenfication of process improvements, system flaws, system admin tasks, etc. on EAF |  | A | FIS | Wang | FIS | Jeffries | EAF | 20030731 | 20030708 | D | 10
Modifications to BALQ screen |  | M | FIS | Montoya | SIS | Wilson | SAR | 20030715 | 20030715 | D | 8
Modify Faculty/Staff Directory program to produce two reports |  | M | FIS | Ayers | PER | Padilla | HRMS | 20030715 | 20030716 | D | 6
Perform feasibility analysis on changes to FFX scrren 536 | 780 | M | FIS | Montoya | AFR | Ross | FRS | 20030718 | 20030716 | D | 4
Modify United Way Web Pledge Form for proper instructions |  | M | FIS | Ayers | US | Wilson | UW | 20030716 | 20030721 | D | 4
SEVIS Evaluation/Analysis/Requirements Definition |  | D | FIS | Jeffries | Business & Finance | Taylor | HRMS | 20030718 | 20030721 | D | 6
Identification of FRS interfaces |  | M | FIS | Montoya | FIS | Jeffries | FRS | 20030731 | 20030721 | D | 20
Apply emergency PCN for Arizona |  | M | FIS | Wang | PAYR | Stuart | HRMS | 20030725 | 20030724 | D | 12
Identification of HRMS interfaces |  | M | FIS | Wang | FIS | Jeffries | HRMS | 20030731 | 20030725 | D | 20
Resolve PBM092 abend |  | M | FIS | Montoya | AFR | Ross | FRS | 20030731 | 20030728 | D | 2
Create final ERA file |  | M | FIS | Montoya | US | Wilson | HRMS | 20030730 | 20030730 | D | 1
FRS Year-end Support |  | M | FIS | Hammersmith | AFR | Ross | FRS | 20030731 | 20030731 | D | 80
Test ICT student file |  | M | FIS | Montoya | ICT | Cooper | HRMS | 20030731 | 20030814 | D | 3
Provide W-2 Processing Support (including rewrite of PP19 and implementation of W-2 reporting changes in YE release) |  | M | FIS | Wang | PAYR | Throneberry | HRMS | 20030831 | 20030814 | D | 20
ERB reporting changes - new job category "RP" |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031017 | 20030823 | D | 6
Convert U tapes to Zara Tapes (VCVOBKP, VJMNTH2, VJM030M) |  | M | FIS | Hammersmith | FIS | Jeffries | FRS | 20031031 | 20030902 | D | 12
Streamline the Supplemental Compensation Approval Process on EAF | 750 | E | FIS | Wang | FSA | O'Larey | EAF | 20030815 | 20030902 | D | 240
Modify FFX screen 536 to unprotect TA515/520/525 | 780 | M |  |  | AFR | Ross | FRS | 20030908 | 20030908 | C | 32
Review Eligibility Checks for Repeat Rule | 796 | P | FIS | Wang | FSA | O'Larey | EAF | 20030909 | 20030910 | D | 3
Field POU04 required field on screen 251 | 795 | M | FIS | Montoya | AFR | Ross | FRS | 20030916 | 20030916 | D | 2
Perform feasibility analysis on removing graduate school routing for approvals on EAFform 3 | 773 | M | FIS | Wang | FSA | O'Larey | EAF | 20030919 | 20030916 | D | 6
Remove SSN from HC e-mail notification |  | M | FIS | Wang | FSA | O'Larey | EAF | 20030919 | 20030919 | C | 2
Problem with EAF Reset Password Feature | 797 | P | FIS | Wang | FSA | O'Larey | EAF | 20030919 | 20030919 | D | 2
Document Attached Feature in EAF Not Working | 798 | P | FIS | Wang | FSA | O'Larey | EAF | 20030919 | 20030919 | D | 2
Supplemental Comp addition - rule for checking FLSA code = N | 750 | E | FIS | Wang | FSA | Haines | EAF | 20030926 | 20030924 | D | 6
Remove graduate school routing for approvals on EAForm3 | 773 | M | FIS | Wang | FSA | O'Larey | EAF | 20030926 | 20030925 | D | 32
Job Scheduler Implementation - HRMS Monthly/Quarterly |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS | 20020930 | 20030930 | D | 24
A/P Year End reports requested on e~Print | 734 | M | FIS | Hammersmith | AFR | Ross | FRS | 20031128 | 20031002 | D | 4
Send Departmental Inventory Reports to e~Print |  | M | FIS | Hammersmith | PROP | Ziehl | FRS | 20031006 | 20031003 | D | 24
Implement mandatory TSP reporting changes |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031017 | 20031013 | D | 32
HRMS 2003 February Maintenance Release Install |  | M | FIS | Wang | PAYR/PER | Stuart Haines | HRMS | 20031017 | 20031017 | D | 60
HRMS 2003 Mid-Year Maintenance Release Install |  | M | FIS | Wang | PAYR/PER | Stuart Haines | HRMS | 20031017 | 20031017 | D | 40
ERB reporting changes - Include GTN 018 U balance in monthly/quarterly periodic maintenance |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031017 | 20031017 | D | 4
Define/Evaluate process for creating departmental listing |  | M | FIS | Ayers | ICT | Ormand | HRMS | 20031031 | 20031027 | D | 5
Perform feasibility analysis on uploading PO line item data to FRS |  | M | FIS | Hammersmith | OFS | La Torra | FRS | 20031024 | 20031028 | D | 10
ERB reporting changes - HRSZ1240/1250/1270 |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031017 | 20031029 | D | 24
ERB reporting changes - Fix print problems on PERA report |  | M | FIS | Bagwell | PAYR | Stuart | HRMS | 20031017 | 20031029 | D | 4
Implement process improvements for SPA billing - combine FBM090/91 reports into one worksheet using MS Excel |  | M | FIS | Hammersmith | Business & Finance | Noel | FRS | 20031031 | 20031030 | D | 48
Perform feasibility analysis on printing FRS checks on laser |  | E | FIS | Hammersmith | FINOP | Stuart | FRS | 20031024 | 20031105 | D | 16
Personal Data Report Modifications - Flexible Spending Acct |  | M | FIS | Ayers | PER | May | HRMS | 20031031 | 20031105 | D | 24
Peform analysis/fix on 1.5 month rule for TX transactions |  | P | FIS | Wang | FIS | Roggow | HRMS | 20031105 | 20031105 | D | 4
Addition of previous years HRSZ0450 files to e~Print | 741 | M | FIS | Jeffries | FSA | Harrell | HRMS |  |  | C
Systems Evaluation - HRMS/EAF/FRS |  | M | FIS | Jeffries | Business & Finance | Noel | HRMS EAF FRS | 20030731 |  | D | 120
Provide Crystal Reports and Excel support to VISTAS/SAR users |  | M | FIS | Ayers | SIS | Allwood | VISTAS SAR | 20030926 |  | D | 80
Evaluate Crystal Enterprise (5 free licenses) |  | M | FIS | Ayers | ICT | Wilson | All | 20031114 | 20031118 | D | 5
Automate Bank 26 reconciliation process | 765 | M | FIS | Montoya | AFR | Ross | FRS | 20031114 | 20031201 | D | 40
Perform fix on selection/change to Emp Type for Suppl. Comp. | 811 | P | FIS | Wang | FIS | O'Larey | EAF | 20031114 | 20031120 | D | 2
Modify EAF to accept six digit job code for Broadbanding project |  | M | FIS | Wang | FIS | Slaughter | EAF | 20031128 | 20031206 | D | 4
Modification to EAF Feed report to add ST/EMPLMT field |  | M | FIS | Wang | FIS | Stuart | HRMS | 20031114 | 20031201 | D | 2
Implement TOS FRIBM137 - 1099 regulatory updates |  | M | FIS | Hammersmith | FIS | Ross | FRS | 20031128 | 20031126 | D | 4
Key:
Status Codes: |  |  | Types: |  |  | Group: |  | Dates:
W - waiting resources/requirements |  |  | D - Development |  |  | FIS |  | ESD - estimated start date
C - cancelled |  |  | E - Enhancement |  |  | SIS |  | ASD - actual start date
A - analysis |  |  | M - Maintenance |  |  | DRS |  | ECD - estimated completion date
P - programming |  |  | P - Problem |  |  | SP |  | ACD - actual completion date
T - developer testing |  |  | R - Report |  |  | US |  | (format - ccyymmdd)
S - client testing/signoff |  |  | T- Training
D - done |  |  | U- Urgent
H - hold
I - Instruction

## On Hold
University Systems Maintenance Projects
Financial Information Services
Project Description | Task No. | Type | Group | Dev Name | Client Office | Client Contact | System | ECD | ACD | Status | Time Estimate (hours)
Messages assoc. w/ student elig & approver prob | 336 | P | FIS |  | FSA | Baca | EAF |  |  | H
Enhancement to Student Eligibility Agent Process | 564 | M | FIS |  | FSA | O'Larey | EAF |  |  | H
Edit EAF to not allow negative position numbers |  | M | FIS |  | ICT | Bagwell | EAF |  |  | H
Resolve Organization Hierachy Problem |  | M | FIS | Bagwell | FSA | Baca | EAF |  |  | H
FFX PROJECT #1-4 |  | E | FIS |  | FSA | Ross | FRS |  |  | H
Proposed FRS Screens |  | E | FIS |  | CFR | Noel | FRS |  |  | H
Changes to FRS Screen 251 to allow room for additional entry |  | M | FIS |  | FSA | Blackman | FRS |  |  | H
Mapping Account controls on the FBM070 |  | M | FIS |  | FSA | Byford | FRS |  |  | H
WEB PAF | 193 | E | FIS |  | FSA | Rumford | HRMS |  |  | H
WEB TAD |  | E | FIS |  | FSA | Throneberry | HRMS |  |  | H
Delete "differential" transactions on a monthly basis |  | E | FIS |  | ICT | Quintana | HRMS |  |  | H
Addition of data elements in NMSU Dept Table |  | M | FIS |  | UC | Sadler | HRMS |  |  | H
Dependent Tuition Waiver |  | E | FIS |  | PER | Quintana | HRMS |  |  | H
Modify HRSZ0550 to look at Sal Trans for differentials |  | M | FIS |  | ICT | Quintana | HRMS |  |  | H
PAF Job Title Change |  | U | FIS |  | PAYR | Roggow | HRMS |  |  | H
Resolve Orphan Records Problem |  | P | FIS |  | PAYR | Throneberry | HRMS |  |  | H
HRMS org sweep change to sweep all HRMS orgs |  | P | FIS | Bagwell | IR | Meyer | HRMS |  |  | H
FRS DB2 Implementation including Focus Rewrite/Replacement |  | D | FIS | Montoya Hammersmith Ayers | Business & Finance | Noel | FRS |  |  | H
Provide required HRMS Data to DABCC |  | M | FIS | Ayers | DABCC | Lillibridge | HRMS |  |  | H
Address long term backup issues with HRMS |  | M | FIS | Jeffries | UCC | Gottlieb | HRMS |  |  | H
Develop manual procedures for applications in ESP including how to accomplish changes to JCL, SOURCE and LOAD members |  | E | FIS | Unassigned | US | Wilson | All |  |  | H
Develop high-level proposal for Front end Job Submission (Control cards and Change control) |  | E | FIS | Unassigned | US | Wilson | All |  |  | H
HRMS/EAF Forms Integration Analysis to include PAF, TAD, EAF, Time Entry/Leave -- Provide Narrative, Flow, Required Fields |  | E | FIS | Unassigned | Business & Finance | Noel | WF |  |  | H
Evaluate Telephone Directory process - HRSZ0670 |  | M | FIS | Ayers | PER | Quintana | HRMS |  |  | H
Perform request to create WCWT Earn Types |  | M | FIS | Unassigned | PAYR | Throneberry | HRMS |  |  | H
On-request job for Mass Print of Turnaround Documents |  | M | FIS | Unassigned | PAYR | Stuart | HRMS |  |  | H
Implement TSO FRIBM129 |  | M | FIS | Unassigned | AFR | Ross | FRS |  |  | H
Develop generic Excel Training Document |  | M | FIS | Ayers | US | Wilson | All |  |  | H
Crystal Reports Brownbag |  | T | FIS | Ayers | US | Wilson | All |  |  | H
Job Scheduler Implementation - HRMS Live |  | E | FIS | Bagwell | PAYR | Throneberry | HRMS |  |  | H
Convert to 3590 tape drives for HRMS |  | M | FIS | Unassigned | FIS | Jeffries | HRMS |  |  | H
Convert to 3590 tape drives for FRS |  | M | FIS | Unassigned | FIS | Jeffries | FRS |  |  | H
Key:
Status Codes: |  |  | Types: |  |  | Group: |  | Dates:
W - waiting resources/requirements |  |  | D - Development |  |  | FIS |  | ESD - estimated start date
C - cancelled |  |  | E - Enhancement |  |  | SIS |  | ASD - actual start date
A - analysis |  |  | M - Maintenance |  |  | DRS |  | ECD - estimated completion date
P - programming |  |  | P - Problem |  |  | SP |  | ACD - actual completion date
T - developer testing |  |  | R - Report |  |  | US |  | (format - ccyymmdd)
S - client testing/signoff |  |  | T- Training
D - done |  |  | U- Urgent
H - hold
I - Instruction