## Sheet1
UCIME
|  | Year 1 (1999): | [11 empty] | Year 2 (2000): | [11 empty] | Year 3 (2001): | [11 empty] | Year 4 (Future):
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Agu | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Agu | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Agu | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Agu | Sept | Oct | Nov | Dec
Objective 1: Develop conceptual and technical infrastructure (IME-1 + IME-2).
| Task 1: | Year 1 (1999): Jan: Conceptual and technical framework:
| (Couclelis) | Year 1 (1999): Jan: Review of other models and assess their compatibility with CA.; Year 3 (2001): Jan: Finish the project.
|  | Documentation of the theory behind UGM. | [23 empty] | Final publication.
Define the cellular model on a regular square grid.
State transitions among land uses from one time period to the next.
Investigate linkage of useful models with CA-based urban models.
|  | Fortmulate a set of measures for model parameters and outputs. | [11 empty] | Continuation of setting measures for model parameters and outputs.
Formulate and outline general model structures.
|  | Incorporate Input/Output Coupling and Adaptive Self-Modification. | [23 empty] | Adapt framework to needs of policy formulation and analysis.
|  | Model Calibration and Validation. | [11 empty] | Model Calibration and Validation. | [11 empty] | Dissemulation of results (theoretical and applied).
|  | Urban Model Building in Java. | [11 empty] | Couple UGM + Deltron Model. | [11 empty] | Implementation in Urban Securities Project.
Theoretical Paper.
Objective 2: Demonstrate and test validity of IME-1.
| Task 2a: | Year 1 (1999): Jan: Integrated Modeling of Urban Regions:
| (Clarke) | Year 1 (1999): Jan: Put together and test IME-1.
Model comparision across scales and levels of description (USGS).
Coupling of urban morphology with models of other types of morphology.
Build links between LANL and USGS NASA Ames projects.
Formulate and outline general model structures.
|  | Test the model in New York, Philadelphia, Chicago and Portland . | [11 empty] | More in-depth testing of the model in Portland. | [11 empty] | Test model abroad (Mexico City and possibly a Central American city).
Objective 3: Demonstrate and test validity of IME-2.
| Task 3: | Year 1 (1999): Jan: Linking settlement structure with changing land use intensity and population distribution:
| (Sutton) | Year 1 (1999): Jan: Research, implement and test coupled/integrated models in IME-2.; Year 2 (2000): Jan: Test model at a range of spatial and temporal scales for the 4 cities.; Year 3 (2001): Jan: Test model for its predictive ability against 2000 census results.
|  | Explore interrelationships of land usages with DMSP-OLS imagry. | [23 empty] | Evaluate levels of model accuracy, uncertainty and error, identifying confidence limits.
|  | Formulate and outline general model structures. | [23 empty] | Matrix for error band.
|  | Build better integrated links with the Environment + Urban Growth Models | [11 empty] | Comparitive modeling.
Extend model testing to include Soux Falls, Albequerque and Detroit.
Build a common coding language (Peter Burrough)
Build loose and complex coupling w/ UGM
Study historical urban growth patterns. (Jeannette)
[14 empty] | Visualization. | [11 empty] | Link to Web for visualization in Java.
Objective 4: Implement and disseminate an Integrated GIS-based Model.
| Task 4: | Year 1 (1999): Jan: Implement and Disseminate:
| (Clarke) | Year 1 (1999): Jan: Implementation of the model in a GIS framework.; Year 2 (2000): Jan: Implement and prototype the graphical user interface, non-web.; Year 3 (2001): Jan: Implement and finalize the web-user graphical interface, to be released on NCGIA web site.
|  | Build a common coding language (possibly using GeoAlgebra). | [23 empty] | Document and publish the results of the research.
|  | Devise a model linkage strategy (loose or tight coupling) | [23 empty] | Release source code, macros, dtc. For the IMEs upon request.
Integrate measures and comparative analyisis capabilities from T-1/2.
| Task: | Year 1 (1999): Jan: Assure intersections 1-4 work and are supported (Human-Built, Built-Natural, Human-Natural, Human-Built-Natural).
| Task: | Year 1 (1999): Jan: Build seamless integration of Urban and Natural Models.
| Task: | Year 1 (1999): Jan: Develop one graduate and one undergraduate course using human and technical resources of the project.
Meetings and Conferences:
|  | Monthly UCIME Team organizational meetings. | [7 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Urban Dynamics (USGS) Stakeholders Meeting
Urban Change Integrated Modeling (UCIME/LANL)
Conference - GIS and Environmental Modeling, Banff