## Sheet1
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan
Objective/Activity
Obj 1. Recruit participants | Oct: 1000
Activity 1.1 Advertise | bar: Nov
Activity 1.2 Screen applicants | bar: Mar
Activity 1.3 Invite participants | bar: Dec
Obj 2. Assess needs | Oct: 2500
Activity 2.1 Prepare survey | bar: Oct
Activity 2.2 Complete surveys | bar: Dec
Activity 2.3 Analyze needs | bar: Dec
Obj 3. Design Instruction | Oct: 4000
Activity 3.1 Review outlines and nds | bar: Oct to Nov
Activity 3.2 Ident learng activities | bar: Oct to Dec
Activity 3.3 Develop materials | bar: Nov to Dec
Obj 4. Logistics | June: arrangements covered as overhead
$600 for supplies and mailing
$20480 room and board for participants
Obj 5. Instruction | Oct: 22000
Activity 5.1 Coordinate and provide instruction | bar: Jan
Activity 5.2 Student learning | bar: Jan
Obj 6. Evaluate Learning | Dec: 3000
Activity 6.1 Grade projects | bar: Jan
Activity 6.2 Peer evaluation | bar: Jan
Obj 7. Post-Institute Mentoring
Activity 7.1 Online mentoring | May: 8000
Activity 7.2 ALISE update | Sep: 3500
Obj 8. Evaluate impact
Activity 8.1 Summarize mentoring | Apr: 2000
Activity 8.2 Review proposals | May: 6000