## Sheet1
EXTRACTION TEST
DEVICE CONTROL
Power Converters - ROCS | Francois | CMW Implemented. To be tested using our business layer stuff. Need to put elements on database.
Extraction Kicker - MKE | Guy, Michel | Device Explorer
Extraction Septum MSE | Guy, Michel | ROCS MuGeF - CMW implemenation to be tested.
Power Converters - bumper magnets - ROCS | SPS | Existing main ring software - to be logged.
ISSUES
Alarms | Mark & co | Work in progress. Interface to new system in place for Han
Errors from SPS2001 device server | Michel & Guy | Server side OK. messages arriving at GUI. Guy has implemented client side.
Logging Interface |  | New API from Ronny's section to be tested. Shot by shot list well established, need to get all equipment there in on to our database.
Interlocks | Kata | Still with SL-EQUIP, BT would like a standard API
XML mods for display of expert properties | Michel, Guy | Done
Interface to BIC | Katta
INSTRUMENTATION
BPMs |  | Data structure defined - to be tested.
BLMs | SPS
BCT |  | Prototype in place and tested.
Screens
ISSUES
Define measurements properties | Guy | Defined
Define measurement API | Lionel, Kata | JAPC is in existence, V1 BCT implemented with subscription
Acquisition (BCT, BPMs, Screens) and fixed display | Guy
Interface to logging system
Fixed Displays | Delphine | Java Dataview assumed. Waiting on JMS implemetation.
BCT extraction interlock | Michel
SPS
Settings generation
Work well in progress. Main ring alsmost complete. | Lasse | Finished Q'. Linking OK. RF done. Put in zero function for orbit correctors
Performance |  | Slowish. 8 minutes genration time v. 30 seconds previously. Improvement needed - dump OIDs where possible etc.
Map input data | Mike | Done
Parameter maintenance
Operational version of Display Settings (and thus Seq/Cycle/BP selection, parameter selection) | Delphine | Grouping for parameter selection
Operational version of SPS selection interface for BI | Delphine | Need live data this year
Cycle selection GUI plus sequence manager (add resisdent, change running etc.) | Delphine
Manual Trim prototype including trim, incorporation functionality. | Markus | First GUIs taking shape.
Implement orbit correctors and incorporated in SPS orbit control
Makerule implementation | Markus | Interface defined, String based prototype implementation in place
Beam - definition | Katarina
Name to properties. Where does the messy stuff get done? |  | What will we send to JAPC, to the muGeF device server, where do we hide the current to DAC conversion, the magnet to OC mapping???
HW compensation trims?
Measurements
What are we going to do with the measurements in the business layer? |  | Via JAPC into the business layer
Equipment Access
Device explorer V1 - updates for 2003 | Guy | New version deployed in Razor
Drive Hardware GUI
MuGeFs - full functionality in place | Francois, Michel | Mains…?
RF - load timings
MCSM: fully operational - interface to GPTM(?) | Markus | Where does it run? How does it get restarted?
Timing
Rationalise existing system for next year's CBCM implementation | Delphine
Resident cycle management at equipment level | Michel | Questions outstanding - resident cycle id in event etc. etc. see Issues
Interlocks
Implementation
Refactor present implementation for 3-tier | Lionel, Kata | OC4J (session beans) Katta and Lionel working hard on this. Build very complicated (dependancies between modules and exeranl libraries etc.). Eclipse demanding manual confgiuration of dependancies. New system now in place with Web site JAR repository. "Ant getJAR" etc. JMS implentation by end MAY.
Production database account mirroring C-tree where necessary | Kata
Test environment |  | Test muGefS available in lba, Unit test in place