## Sheet1
Project/Department | Fall '01 | Spring '02 | Summer '02 | Fall '02 | Spring '03 | Summer '03 | Fall '03 | Spring '04 | Summer '04 | Fall '04 | Spring '05 | Summer '05
HSGR/Cross Departmental Communication and Telecommuting Needs | [5 empty] | Evaluate end-user needs in all HSGR depts. Examine alternatives, make recommendations for most cost effective and universally usable communications technology products and services. | Complete purchase, set up and installation of technology, conduct training with end-users. Develop and provide documentation for use away from the office.
HSGR/Cross Departmental Desktop Support | Provide ongoing hardware, software and peripheral installation and support for users in all HSGR depts. | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>>
HSGR/Cross Departmental PC Training | [5 empty] | Conduct needs analysis by dept. Identify internal, external, web and CBT courses to meet identified needs. Develop training as required for specific SU related processes. | Track training completed in PS system. Continue to evaluate and offer training to existing employees and new hires on as needed basis. | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>>
HSGR/Cross Departmental GroupWise Installation and Support | Evaluate hardware to ensure compatibility with Groupwise. Upgrade where needed. Begin installation and training | Complete installation and training. Provide ongoing support | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>>
HSGR/Cross Departmental Web Development and Support |  | Provide full web development assistance and/or support changes and updates to existing pages. |  |  | Develop Community Website providing a single point of entry to locate information about SU programs for members of the Syracuse Community | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | >>>>>>>>>>>>>>
Human Resources Oracle installation/ PeopleSoft 8.0 Upgrade | Begin the Platform change from Sybase to Oracle, tech preparation. | Begin testing of delivered functionality and customizations on Oracle platform. | Continue testing for Oracle port, Begin functional project plan development for 8.0 upgrade. | Oracle platform complete. | PeopleSoft upgrade begins with project planning. Initial focus on technical activities. | 8.0 testing begins. Modifications challenged, functionality enhancements included in upgrade set up and testing. | 8.0 set up and testing continues. | 8.0 set up and testing continues. Security setup/testing and developing training plans begins. | 8.0 upgrade testing continues. End User Training begins. | 8.0 upgrade complete.
Human Resources Employee Self Service Implementation | [8 empty] | Employee Self Service modules evaluated, implemenation plan developed. | Implement self-service inquiry. Set up and test Employee Self-Serve to allow remote entry of address changes, dependent data and W-4 information. | Go live with self-service remote entry. Set up and test self-service benefits elections entry. | Evaluate web open enrollment, consider use during Fall OE. If it's a go, develop communications, training and support system for use during OE.
Human Resources Technical Support for Recruitment Redesign | Recruitment taskforce redesign of recruitment model. Evaluate additional 7.6 PS recruit workforce functionality. Begin project to create on-line tools to replace paper application/ forms. Evaluate make vs. buy options for total cost of ownership, support and functionality | Create or purchase on-line application software, to include self-disclosure, to allow development of minority candidate pool and applicant "data mining" for open reqs. Purchase and install PCs to allow candidates to complete on-line app at locations on campus. | Evaluate make vs. buy options for additional on-line functionality for requisitions, hiring proposals, candidate feedback mechanism, based on new recruitment model. | Implement on-line functionality, create communications and training materials, as required, for hiring managers and/or others involved in recruitment effort. |  |  |  | Evaluate 8.0 recruit workforce, e-recruit module and alternatives for functionality, ease of use, costs and maintenance requirements. Determine best alternative to support the recruitment process. | Purchase required hardware, software and/or services necessary to fully automate the recruitment process. Install, setup and test. | Go live with automated recruitment process. Develop communications and training materials to share with hiring managers as required.
Human Resources On-line Job Action Notice | Complete development of On-line JAN | Pilot iJAN, Devlop Training and Communications | Begin roll out to Campus | >>>>>>>>>>>>>> | >>>>>>>>>>>>>> | iJAN enhancements, including multiple job entry for Semi-monthly employees | >>>>>>>>>>>>>> | Eliminate paper Job Action Notice.
Human Resources Automation of employee and dependant tuition benefits | Complete automation of Remitted Tuition by December. Begin evaluation of Dependent tuition | Remitted Tuition live. |  | Begin automation of Dependent Tuition program administration | Revise policy as required, begin development of PeopleSoft functionality | Dependent Tuition goes live.
Human Resources Automation of Organizational Development tools | All training conducted by OD or CMS loaded into PS. Training inquiry panel available for managers. | Additional functionality for tracking internal and external training developed. Communications and training documents created. Full training functionality available to campus. |  |  |  |  | Evaluate competency models, determine best direction for SU. Begin building competency library structure in PeopleSoft, link to job requirements. | Complete competency library. Create communications and training materials to support use of PeopleSoft functionality for Performance Partnership activities. | Competency library, training adminstration, electronic development plan capability live.
Human Resources Improvement in HRMS reporting capabilities | Evaluate reporting requirements for HR, Payroll and campus users. Develop model for new data warehouse structure. | Begin creation of new data warehouse tables. | Complete data warehouse tables. Recreate existing repository reports, develop new reports based on customer needs. | Roll out new data warehouse/report repository to campus users. Develop communications and training materials.
Public Safety Develop Database for Residential Security Program |  | Evaluate make vs. buy alternatives to replace FileMaker Pro database for total cost of ownership, functionality and support. Begin development or installation. | Complete development or installation of new database. Create flat file interface from PeopleSoft. Map data from FileMaker if required. Conduct training and ensure knowledge transfer to staff.
Public Safety Enhancements to Public Safety Records Management System |  |  |  |  | Evaluate alternative software packages to replace current Computer Aided Dispatch/Records Management System. Sign Contract with new vendor | Begin implementation of new CAD/RMS system, install required hardware, software and interfaces. | Complete testing of new system for go-live 12/31/03. | Prepare for roll out of Field Reporting module, including testing and training, to allow officers to interface with system data and complete reports in their patrol zones
Public Safety Remote Data Interface for Public Safety Officers | Conduct a pilot, using laptops without wireless capabilities in 5 cars used in 3 shift operation. Develop templates and protocol for officers. Conduct training. | Gather feedback from officers regarding viability of using laptops to capture case narrative in the field. Complete cost/benefit analysis for going to a wireless system. | Continue with pilot. Consider additional laptops, if viability is proven. Begin keyboarding training for officers needing to improve skills. | [5 empty] | Complete radio system enhancements to create a dedicated wireless data transmission channel for CAD/RMS system interface. | Wireless PCs in all cars in the field, with link to live data in CAD/RMS system and other law enforcement databases.
Archives & Records Management Upgrade Archives and Records Management Software |  |  | Develop software upgrade project plan. Prepare for and begin software upgrade. Complete installation, convert data | Complete testing of upgrade. Go-live with Enterprise in Archives & Records Mgmnt.
Gov't Relations Upgrade Contact Software |  |  |  | Evaluate make vs. buy alternatives for possible replacement to Maximizer CRM system. | Complete upgrade/ installation of CRM software, test system. | Bring all users in Government and Community Relations up on new system, complete training.
Hendricks Chapel Develop Comprehensive Database |  | Evaluate make vs. buy alternatives to automate manual operations for total cost of ownership, functionality and support. Begin development or installation. | Complete development or installation of new contact software. Complete manual data entry. Conduct training and ensure knowledge transfer to staff.
Trustee Relations Reorganize Database |  |  |  |  | Analyze existing database and process. Make database and form changes.