## LifeTemp
WBS Elements From the Life Cycle Structure
| of IEEE 12207 | Include? | Your Label for This
1.0 | Acquisition Process
1.1 | Initiation
1.1.1 | Describe concept or need
1.1.2 | Analyze system requirements
1.1.3 | Approve system requirements
1.1.4 | Define software requirements
1.1.5 | Consider acquisition options
1.1.6 | Evaluate off-the-shelf products
1.1.7 | Document and execute acquisition plan
1.1.8 | Document acceptance criteria
1.2 | RFP Preparation
1.2.1 | Document acquisition requirements (RFP)
1.2.2 | Tailor standards
1.2.3 | Define contract milestones and audits
1.2.4 | Give requirements to performer
1.3 | Contract Prep and update
1.3.1 | Establish selection procedure
1.3.2 | Select supplier based on evaluation
1.3.3 | Get inputs on tailoring this Standard
1.3.4 | Prepare and negotiate contract
1.3.5 | Negotiate changes to contract
1.4 | Supplier Monitoring
1.4.1 | Monitor supplier activities
1.4.2 | Cooperate with timely solutions
1.5 | Acceptance and Completion
1.5.1 | Define acceptance tests and procedures
1.5.2 | Conduct acceptance review and testing
1.5.3 | Perform CM after acceptance
2 | Supply Process
2.1 | Initiation
2.1.1 | Review RFP, policies, regulations
2.1.2 | Decide to bid, or accept contract
2.2 | Preparation of Response
2.2.1 | Prepare proposal in response to RFP
2.3 | Contract
2.3.1 | Negotiate and enter into contract
2.3.2 | Mod contract per change mechanism
2.4 | Planning
2.4.1 | Define management and QA
2.4.2 | Select a life cycle model
2.4.3 | Plan management, assurance, resources
2.4.4 | Evaluate make-buy decisions
2.4.5 | Document project management plans
2.5 | Execution and Control
2.5.1 | Execute project management plans
2.5.2 | Develop, operate or maintain per process
2.5.3 | Monitor progress, identify problems
2.5.4 | Control subcontractors per Acquisition Process
2.5.5 | Interface with IV&V and test agent
2.5.6 | Interface with others per contract and plans
|  | Include? | Your Label for This
2.6 | Review and Evaluation
2.6.1 | Coordinate contract reviews
2.6.2 | Support meetings, reviews, tests, audits
2.6.3 | Conduct V&V per this process
2.6.4 | Report evaluations, audits, tests to acquirer
2.6.5 | Provide access to facilities
2.6.6 | Perform QA
2.7 | Delivery and Completion
2.7.1 | Deliver the product per contract
2.7.2 | Support acquirer with product per contract
3 | Development Process
3.1 | Process Implementation
3.1.1 | Define software life cycle model
3.1.2 | Document and control outputs
3.1.3 | Select and use standards, tools and languages
3.1.4 | Document development plans
3.1.5 | Deliver all needed products
3.2 | System Requirements Analysis
3.2.1 | Specify system requirements
3.2.2 | Evaluate Requirements Against Criteria
3.3 | System Architectural Design
3.3.1 | Establish top-level architecture
3.3.2 | Evaluate architecture against criteria
3.4 | Software Requirements Analysis
3.4.1 | Document software requirements
3.4.2 | Evaluate requirements against criteria
3.4.3 | Conduct joint reviews
3.5 | Software Architectural Design
3.5.1 | Transform requirements into architecture
3.5.2 | Document top-level design for interfaces
3.5.3 | Document top-level design for database
3.5.4 | Document preliminary user documentation
3.5.5 | Document preliminary test requirements
3.5.6 | Evaluate architecture against criteria
3.5.7 | Conduct joint reviews
3.6 | Software Detailed Design
3.6.1 | Document design for each component
3.6.2 | Document design for interfaces
3.6.3 | Document design for database
3.6.4 | Update user documentation
3.6.5 | Document unit test requirements
3.6.6 | Update integration test requirements
3.6.7 | Evaluate detailed design against criteria
3.6.8 | Conduct joint reviews
3.7 | Software Coding and Testing
3.7.1 | Document each unit, database and tests
3.7.2 | Conduct and document unit testing
3.7.3 | Update user documentation
3.7.4 | Update integration test requirements
3.7.5 | Evaluate code and test results
|  | Include? | Your Label for This
3.8 | Software Integration
3.8.1 | Document integration plans
3.8.2 | Conduct and document integration tests
3.8.3 | Update user documentation
3.8.4 | Document qualification tests
3.8.5 | Evaluate plans and tests against criteria
3.8.6 | Conduct joint reviews
3.9 | Software Qualification testing
3.9.1 | Conduct and document qualification tests
3.9.2 | Update user documentation
3.9.3 | Evaluate tests against criteria
3.9.4 | Support audits
3.9.5 | Prepare product for next phase
3.10 | System Integration
3.10.1 | Integrate software with hardware and others
3.10.2 | Document integration tests
3.10.3 | Evaluate integrated system against criteria
3.11 | System Qualification Testing
3.11.1 | Conduct and document qualification tests
3.11.2 | Evaluate system against criteria
3.11.3 | Support audits
3.11.4 | Prepare product for installation
3.12 | Software Installation
3.12.1 | Plan installation in target environment
3.12.2 | Install software per plan
3.13 | Software Acceptance Support
3.13.1 | Support acquirer's acceptance tests
3.13.2 | Deliver product per contract
3.13.3 | Provide training per contract
4 | Operations Process
4.1 | Process Implementation
4.1.1 | Document operational activities
4.1.2 | Document problem tracking procedures
4.1.3 | Document product testing procedures
4.2 | Operational Testing
4.2.1 | Conduct operational testing
4.2.2 | Test software code and databases
4.3 | System Operation
4.3.1 | Operate per user documentation
4.4 | User Support
4.4.1 | Assist users as requested
4.4.2 | Track user requests
4.4.3 | Provide problem work-around solutions
|  | Include? | Your Label for This
5 | Maintenance Process
5.1 | Process Implementation
5.1.1 | Document maintenance activities
5.1.2 | Document problem tracking procedures
5.1.3 | Manage modifications to the system
5.2 | Problem and Modification Analysis
5.2.1 | Analyze problem reports
5.2.2 | Replicate or verify problems
5.2.3 | Develop modifications
5.2.4 | Document problems, analysis, fixes
5.2.5 | Get modifications approved per contract
5.3 | Modification Implementation
5.3.1 | Document where changes are needed
5.3.2 | Implement modifications
5.4 | Maintenance Review/Acceptance
5.4.1 | Review integrity of modified system
5.4.2 | Get approval for modifications per contract
5.5 | Migration
5.5.1 | Ensure products meet this standard
5.5.2 | Develop and execute Migration Plan
5.5.3 | Notify users of migration
5.5.4 | Conduct parallel operations if needed
5.5.5 | Notify all concerned, archive all records
5.5.6 | Perform post-op review of changes
5.5.7 | Keep data from old environment
5.6 | Software Retirement
5.6.1 | Document plans for retirement
5.6.2 | Notify all users of plans and activities
5.6.3 | Conduct parallel operations
5.6.4 | Notify all concerned, archive all records
5.6.5 | Keep data from retired product per contract
6 | Documentation
6.1 | Process Implementation
6.1.1 | Develop a documentation plan
6.2 | Design and Development
6.2.1 | Use applicable standards for documents
6.2.2 | Confirm source of input data
6.2.3 | Review and edit documents against standards
6.3 | Production
6.3.1 | Produce documents per plan
6.3.2 | Control per CM Process
6.4 | Maintenance
6.4.1 | Modify documents per CM Process
|  | Include? | Your Label for This
7 | Configuration Management
7.1 | Process Implementation
7.1.1 | Develop CM Plan
7.2 | Configuration Identification
7.2.1 | Establish scheme to identify software items
7.3 | Configuration Control
7.3.1 | Manage change requests
7.3.1.1 | Record change requests
7.3.1.2 | Evaluate change requests
7.3.1.3 | Approve change requests
7.3.2 | Keep audit trail
7.3.3 | Control access to items
7.4 | Configuration Status Accounting
7.4.1 | Maintain records and status reports
7.5 | Configuration Evaluation
7.5.1 | Ensure functional completeness of products
7.6 | Release Management and Delivery
7.6.1 | Control release and delivery of products and documentation
8 | Quality Assurance
8.1 | Process Implementation
8.1.1 | Establish QA process
8.1.2 | Coordinate with Verification, Validation, Joint Reviews and Audit Processes
8.1.3 | Develop QA Plan
8.1.4 | Schedule and execute QA tasks
8.1.5 | Make QA records available to acquirer
8.1.6 | Give QA team organizational freedom
8.2 | Product Assurance
8.2.1 | Assure plans are executed
8.2.2 | Assure products comply with contract
8.2.3 | Assure delivered products satisfy requirements
8.3 | Process Assurance
8.3.1 | Assure processes comply with contract
8.3.2 | Assure practices, tests, libraries comply
8.3.3 | Assure prime requirements are passed to subs
8.3.4 | Assure support provided per contract
8.3.5 | Assure measures performed per standards and procedures
8.3.6 | Assure staff is trained
8.4 | Assurance of Quality Systems
8.4.1 | Assure additional quality management activities are performed per ISO 9001, if required
|  | Include? | Your Label for This
9 | Verification
9.1 | Process Implementation
9.1.1 | Determine if verification effort needed
9.1.2 | If so, establish process
9.1.3 | Select independent verification organization
9.1.4 | Identify activities and products to verify
9.1.5 | Develop verification plan and procedures
9.1.6 | Implement verification plan
9.2 | Verification
9.2.1 | Verify contract against criteria
9.2.2 | Verify process against criteria
9.2.3 | Verify requirements against criteria
9.2.4 | Verify design against criteria
9.2.5 | Verify code against criteria
9.2.6 | Verify integration against criteria
9.2.7 | Verify documentation against criteria
10 | Validation
10.1 | Process Implementation
10.1.1 | Determine if validation effort needed
10.1.2 | If so, establish process
10.1.3 | Select validation organization
10.1.4 | Develop validation plan
10.1.5 | Implement validation plan
10.2 | Validation
10.2.1 | Prepare test requirements, cases, specs
10.2.2 | Ensure requirements met
10.2.3 | Conduct tests
10.2.4 | Validate that product satisfies intended use
10.2.5 | Test product in target environment
11 | Joint Review
11.1 | Process Implementation
11.1.1 | Hold periodic and ad hoc reviews
11.1.2 | Agree to resources needed
11.1.3 | Set agenda, products, scope, procedures
11.1.4 | Record problems detected
11.1.5 | Document and distribute results
11.1.6 | Agree on outcome and action items
11.2 | Project Management Reviews
11.2.1 | Evaluate status against plans, schedules
11.3 | Technical Reviews
11.3.1 | Evaluate products or services
12 | Audit
12.1 | Process Implementation
12.1.1 | Audit at predetermined milestones per plan
12.1.2 | Select independent auditors
12.1.3 | Agree to audit resources
12.1.4 | Agree on agenda, products, scope
12.1.5 | Record problems detected
12.1.6 | Document and distribute results
12.1.7 | Agree on outcome and action items
12.2 | Audit
12.2.1 | Conduct audits per criteria
|  | Include? | Your Label for This
13 | Problem Resolution
13.1 | Process Implementation
13.1.1 | Establish problem resolution process for handling problems in products and activities
13.2 | Problem Resolution
13.2.1 | Track problems through detection, analysis, and resolution
14 | Management
14.1 | Initiation and Scope Definition
14.1.1 | Establish the requirements for management
14.1.2 | Check resources: personnel, materials, etc.
14.1.3 | Modify requirements to achieve criteria
14.2 | Planning
14.2.1 | Plan efforts, schedules, tasks, duties, costs
14.3 | Execution and Control
14.3.1 | Implement plan to meet objectives
14.3.2 | Monitor process
14.3.3 | Investigate and resolve problems
14.3.4 | Report progress
14.4 | Review and Evaluation
14.4.1 | Ensure products and plans are evaluated
14.4.2 | Assess evaluation results
14.5 | Closure
14.5.1 | Determine when process is complete
14.5.2 | Check results for completeness
15 | Infrastructure
15.1 | Process Implementation
15.1.1 | Define infrastructure needed
15.1.2 | Plan and document infrastructure establishment
15.2 | Establish Infrastructure
15.2.1 | Document configuration of infrastructure
15.2.2 | Install infrastructure in time for process
15.3 | Maintain Infrastructure
15.3.1 | Maintain, monitor, modify infrastructure to satisfy requirements of process
16 | Improvement
16.1 | Process Establishment
16.1.1 | Establish organizational processes for software life cycle
16.2 | Process Assessment
16.2.1 | Develop process assessment procedure
16.2.2 | Review process for effectiveness
16.3 | Process Improvement
16.3.1 | Improve processes as needed
16.3.2 | Collect and analyze process data
16.3.3 | Collect and use quality cost data
|  | Include? | Your Label for This
17 | Training
17.1 | Process Implementation
17.1.1 | Determine training needs, develop plan
17.2 | Training Material Development
17.2.1 | Develop training presentation materials
17.3 | Training Plan Implementation
17.3.1 | Provide training to personnel, keep records
18 | Tailoring
18.1 | Identify Project Environment
18.1.1 | Identify model, activities, requirements, policies, strategies, criticality, etc.
18.2 | Solicit Input
18.2.1 | Solicit input from users, support personnel, bidders, etc.
18.3 | Select Processes, Activities and Tasks
18.3.1 | Decide on processes, activities and tasks
18.3.2 | Specify in contract others not in this Standard
18.4 | Document Tailoring Decisions and Rationale
18.4.1 | Document decisions and rationale