## Ark1
Progress plan - Health and Human Rights Info
Week starting | sep 23 | sep 30 | oct 7 | oct 14 | oct 21 | oct 28 | nov 4 | nov 11 | nov 18 | nov 25 | dec 2 | dec 9
Graphical design | bar: sep 23
Setting up test site | bar: sep 23
Programming of database | bar: oct 7 to oct 28
Collection of data and materials
Feeding database with information | bar: nov 4 to dec 2
Launch of test site with database | bar: nov 11
Testing and debugging | bar: nov 11 to dec 2
Official launch | bar: dec 9