## Schedule
| COHYST II WORK PLAN SCH. |  |  |  | 2 | 0 | 0 | 1 | [6 empty] | 2 | 0 | 0 | 2 | [8 empty] | 2 | 0 | 0 | 3 | [8 empty] | 2 | 0 | 0 | 4
Task Number | Work Task Decsription | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M
3000 | Develop Water Data & Database
3100 | Surface Water Records | [21 empty] | X | X | [10 empty] | X | X | bar: J to F
3110 | Other time series data | [21 empty] | X | X | [10 empty] | X | X | bar: J to F
3120 | Contract for Missing & New Data
3121 | Riparian ET Study --- Phase I | X | X | X
| --- Phase II |  |  |  | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
3122 | Hydrogeology ---- Testholes |  | X | X |  | X | X | X | X | bar: A to 2 A
| --- Collect info Well Drillers |  | X | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
| --- Preform Aquifer Pump Test |  | X | X | bar: A to 2 M; 2 O to 2 N
| --- Geophysical testing |  |  | X | X | X | X | X | X | X | bar: J to 2 S
3123 | Canal & Lake Recharge Study | [6 empty] | X | X | [16 empty] | X | X | X | X | X | X | X | [6 empty] | X | X | X | X | X | X | X | X | bar: A to 2 N
3124 | Runoff Recharge Study | [6 empty] | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
3125 | Tracer Work |  |  |  | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
3126 | 1. 'Canals & Drains Spatial Data |  |  |  |  | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
| 2. Irrigation & M&I wells |  |  |  |  | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
| 3. Stream & Trib Spatial Data |  |  |  |  | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
3127 | Land Use 1. Historic | [6 empty] | X | X | X | [12 empty] | X | X | X | bar: J to 2 D
| 2. 2001 |  |  |  | X | X | X | X | X | X | bar: J to 2 D
3128 | Groundwater Use |  |  |  | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
3130 | Database Maintenance |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
4000 | Develop & Calibrate Tools & Models
4041 & 4051 | Database Model Interaction |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
4020 | Update GW Models with new data |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
4120 | GW Model improvements |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
4130 | Training and Education |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
6000 | Implement Coopertive Hydrology
Study Products
6001 | Develop Process for Constructing | [8 empty] | X | bar: J to A
Sub-regional Models
6002 | Wildlife Improvement Alternatives | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
6003 | Riparian Land Uses | [33 empty] | X | X | X | X | X | X | X | X | X | X | X | X
6004 | Understand Residual Effect of Past | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: 0 J to 2 D
6005 | Understanding GW-SW interaction | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
6006 | Stream Dep Modeling Procedure & Testing | bar: J to 0 J
6007 | Understanding GW-GW interaction | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: 0 J to 2 D
6008 | Understanding Zone of Influence | [21 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: 0 J to 2 D
6009 | Model Limitations / Sensitivities |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
6010 | Review and Consultation |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D
7000 | Out- Reach and Education |  |  | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | bar: J to 2 D

## Budget
COHYST II WORK PLAN BUDGET
Work Task | Priorty | Work Task Description | Cost | NET Funds | Cooperator Cost Share | Sponsors In-Kind | Sponsors Cash | Description
3000 |  | Develop Hydrologic Data & Database
3100 |  | Surface water records | 10000 |  |  | 10000 |  | As new flows are collected it would be added to the database.
Look at past gages deleted
3110 |  | Other Time Series Data | 10000 |  |  | 10000 |  | As new climatic data is collected it would be added to the database.
3120 |  | Contract for Missing & New Data
3121 |  | Riparian ET | 672000 | 336000 | 336000 |  |  | Conduct study to test method for measuring Riparian ET along Platte River
3122 |  | Hydrogeology | [5 empty] | Select sites of various vegetation types and measure plant water over time. (Phase I & II)
|  | 1. Testhole Drilling | 175000 | 150000 | 25000 |  |  | Identify new wells needed then drill & log new testhole (CSD)
|  | 2. Collect info Well Drillers | 76000 | 26000 | 50000 |  |  | Cost Share with drilles to get new and better data from there drilling operations
|  | 3. Perform Aquifer Pump Test | 64000 | 39000 |  | 25000 |  | Preform pump tests in various geological formations to measure hydrologic parameters
|  | 4. Geophysical testing | 150000 | 75000 | 75000 |  |  | Use geophysical methods to collect geologic information, like depth to water, type of material
Recharge Studies
3123 |  | Canal & Lake Recharge Study | 75000 | 75000 | 0 |  |  | Determine GW recharge contributed from seepage out of Canals and Lakes
3124 |  | Runoff Recharge Study | 125000 | 50000 | 50000 |  | 25000 | Determine GW recharge contributed from rainfall runoff water
3125 |  | Tracer Work | 275000 | 137500 | 137500 |  |  | Use water quality and traces for developing and understanding flow paths & travel time
3126 |  | Spatial data collection
|  | 1. Canals & Drains Spatial Data | 50000 |  |  | 50000 |  | Develop and update a time series spatial data coverage of Canals and Drains
|  | 2. Irrigation & M&I wells | 100000 |  |  | 100000 |  | Develop and update a time series spatial data coverage of Irr & M&I Wells
|  | 3. Stream & Trib Spatial Data | 72000 | 36000 |  | 36000 |  | Improve and update the Stream and Tributary spatial data coverage
(evelvations, wet points, cross sections,flow record history, etc)
|  | TOTAL | 1854000 | 924500 | 673500 | 231000 | 25000
Database Maintenance & New Additions
3127 |  | Land Use
|  | 1. 2001 | 160000 |  |  |  | 160000 | Add a new land cover map to the database and compare changes to 1997
|  | 2. Historic | 160000 | 160000 |  |  |  | Develop land cover maps for previous year but after 1973 when imagery was frist available
|  |  | 30000 |  |  | 30000 |  | To develop and access acuracy of land cover maps ground truthing data is needed for 2001
3128 |  | Groundwater Use | [5 empty] | Measure water pumped from irrigation wells and M&I wells to compare with water use
|  |  | 100000 |  |  | 100000 |  | Develop statiscal analysis of change in irrigated acres CALMIT or FSA records
3130 |  | Database maintenance | 195000 | 75000 | 75000 | 45000 |  | Fund a position and computer equipment to keep the COHYST database updated
|  | TOTAL | 645000 | 235000 | 75000 | 175000 | 160000
4000 |  | Develop & Calibrate Tools & Models
4041 & 4051 |  | Database Model Interaction | 150000 | 150000 |  |  |  | Link Net Recharge Model to directly use GIS inputs ( crop type, irrigated lands, soils, etc.)
4020 |  | Update GW models with new data | 50000 |  |  | 50000 |  | Have modelers update calibration of Models with new data after 1997
4120 |  | GW Model Improvments | 25000 | 25000
|  |  | 50000 |  |  | 50000 |  | Update Net Recharge Model to estimate GW recharge or develop Runoff recharge Model
4130 |  | Training / education | 15000 | 15000 |  |  |  | Train and Education Modelers and Database personel with last technologies in field
|  | TOTAL | 290000 | 190000 | 0 | 100000 | 0
6000 |  | Groundwater Modeling Applications
Test "Wildlife Improvement" Alternatives
6001 |  | Develop Process for Constructing | 75000 |  |  | 75000 |  | Make model runs for the water management alternatives that have a groundwater component
sub-regional Models
6002 |  | Wildlife Improvement Alternatives | 25000 |  |  | 25000 |  | Model other potenial wildlife management alternatives
6003 |  | Understanding Riparian Land use impacts | 50000 |  |  | 50000 |  | Look at possible Riparian land use changes and study consequences of changes
6004 |  | Understand Residual Effects | [5 empty] | Use regional model to develop estimated future baseline with pre-1997 groundwater develop
6005 |  | Understand GW - SW interaction | 50000 |  |  | 50000 |  | Model surface water depletions due to groundwater pumping
6006 |  | Stream Depl Modeling procedure &Testing | 25000 |  |  | 25000 |  | Develop the procedure for determining stream depletions by testing different methods
6007 |  | Understanding GW-GW interaction | 25000 |  |  | 25000 |  | Make model runs to determine the future GW pumping effect of existing wells
6008 |  | Understanding Zone of Influence | 25000 |  |  | 25000 |  | Make model runs to determine the "Recharge Zone" size or possible well spacing distance
6009 |  | Model Limitation / Senitivities | 25000 |  |  | 25000 |  | Make Model sensitivity runs for time steps, recharge, aquifer parameters, pumping schedules etc.
6010 |  | Review and Consultation | 135000 | 35500 |  |  | 99500
|  |  | 315000 |  | 157500 |  | 157500
|  |  | 105000 |  |  |  | 105000
7000 |  | Out reach / Education | 25000 | 15000 |  | 10000 |  | Develop outreach training to educate people about COHYST data and models
|  | TOTAL | 880000 | 50500 | 157500 | 310000 | 362000
|  |  | 3669000 | 1400000 | 906000 | 816000 | 547000
Maintenance