## Implementation Steps
Date |  | Steps in Implementation | Responsibility | Component
Interim |  | September, 2001-November, 2002 |  | EDUCATION | PUBLIC PROGRAMMING | RESEARCH | PRESERVATION
| * | Recruit & hire CRHC Admin. Asst; move from planning office to Research & Technology Bldg. | Co-Directors | X |  | X
| * | Begin design of relational database based on inventory | CITL; Co-directors, Pathseeker Group |  | X | x
| * | Grant proposals: Pathseeker & Dunbar Project | Co-directors & project partners | X | X | X
| * | File "Communication & American Studies" curriculum materials | Ohio U American Studies Steering Committee; Co-Directors | X
| * | Plan Native American Studies Teacher Workshop for GLASA | CRHC Native American Cultures Round-table; OSU Group, OU Ping Teaching Center | X
| * | Develop Dunbar website; call for papers for scholarly conference & partners for regional projects | Co-Directors & Dunbar Project Group | X | X | X
Years 1-2 |  | December, 2001-December, 2003
Dec. 2001 | * | Establish 800 number; Keeping Current becomes bimonthly e-publication (with print avail.), announces implementation, Advisory Board, to all org's in database | Co-Directors, Admin. Asst.
| * | Open REACH office. Initial services: troubleshooting for use of online center; support for locating partners and resources. | REACH, Online Services Team |  | X |  | X
2001-2005 | * | Expand collections inventory to comprehensive coverage & convert into relational database. Begin identifying reference needs; develop web interface for bibliographic tools | CRHC Regional Bibliographer, Collections Task Force (regional librarians & scholars), Online Services Team
2001-2003 | * | Develop & pilot prototype of regional calendar database & procedures for keeping it continually updated | REACH, Online Services Team, Programming Advisory Group |  | X |  | X
Mar. 15-17, 2002 | * | Sessions at Appalachian Studies Association (Helen, GA); meet with Appalachian collaborators | CRHC leaders & participants | X |  | X
April 9-10, 2002 | * | Convene Advisory Board: establish committees; draft bylaws, policies and procedures; establish guidelines for public programming grants | Advisory Board & Co-directors |  | X
April 11-13, 2002 | * | GLASA Conference (CRHC@Ohio U): Public lecture; Special sessions on Regional Native American identity; K-12 Workshop; Launch Pathseeker project & invite participation; CRHC planning discussions | GLASA/CRHC; OSU Committee for Native American Studies; CRHC Roundtables on Native American Culture and Riverine & Lakes Culture | X | X | X
Summer, 2002 | * | Identify leaders for & develop schedule for fall of online discussions (Web Crossing site to be renamed Central Region Humanities Crossing) among regional scholars and organizations, including parks, museums, etc. | REACH, in consultation with Co-directors; Roundtable & Task Force Leaders; Online Services Team | X | X | X | X
Fall, 2002 | * | Full proposal for regional studies M.A. submitted to Board of Regents | Ohio U American Studies Committee; Co-directors | X
| * | Pilot online regional calendar for 2003 | Admin. Asst./ REACH /CITL | X | X | X
2003 | * | Regional Publishers' collaborative catalog and authors' website | Publishing Group/G. Berchowitz/CITL |  | X | X
| * | Help organize Regional Research Communities | Co-Directors, Admin. Asst. |  |  | X
May, 2003 | * | First regional travel to collections grants (5 @ $2000 in grant period) | Advisory Board & Co-directors |  |  | X
June, 2003 & after | * | Launch Dunbar Project at Centennial Celebration of Dunbar Aviation Heritage National Park (Dayton); "Dunbar Detonations": regional performances of African-American music, poetry, and drama, past and present | Co-Directors, Shelley Fisher Fishkin, & Dunbar Project Group |  | X | X
| * | First grants for regional public programming | Advisory Board; subcommittee /external reviewers
Date |  | Steps in Implementation | Responsibility | Component
|  |  |  | EDUCATION | PUBLIC PROGRAMMING | RESEARCH | PRESERVATION
Years 3-4 |  | January, 2004- December, 2005
2004 | * | Dunbar scholarly conference; K-12 teacher workshops; high school programs; regional "Dunbar Detonations" | Shelley Fisher Fishkin, & Dunbar Project Group | X | X | X
| * | Develop policy for regional interlibrary loan & digitization standards for noncirculating materials | Advisory Board; Librarians Advisory Group; OHIO Libraries representative | X |  | X | X
| * | Review calendar of existing K-12 teacher programs; develop K-12 Education teacher workshop strategies | K-12 Advisory Group (Interdisciplinary) | X
| * | Publishers plan pilot regional book fair | Publishing Group/G. Berchowitz |  | X
Fall, 2004 | * | Admit 15-25 "Communication & American Culture" M.A. students | Ohio U American Studies Committee; Co-directors | X |  |  | X
2004-2005 | * | Production of Dunbar documentary; preparation of teachers' guide | Shelley Fisher Fishkin, & Dunbar Project Group |  | X
2005 | * | Conference on Riverine & Lake Cultures; sessions for K-12 teachers | Riverine and Lakes Cultures Roundtable, NCHE, K-12 Group, regional colleges, Ohio U Dean of Lifelong Learning
| * | Public beta-testing of Pathseeker | Pathseeker Group | X | X | X | X
Summer, 2005 | * | First regional book fair: | Publishing Group/G. Berchowitz; state councils; local and state tourist groups
Fall, 2005 | * | Begin planning regional studies B.A. program | Ohio U; American Studies Steering Committee; regional consultants | X
Years 5-6 |  | January, 2006-December, 2007
2006-2007 | * | Preservation regional use and condition survey to assess preservation needs & develop regional strategy | Preservation Field Services Coordinator; Preservation Task Force |  |  |  | X
| * | Design and develop Pathseeker's educational models for K-12 teachers and students (separate external funding) | Pathseeker Group; K-12 Advisory Group | X
May, 2006 | * | Humanities Fellowships begin (1@ $5000 during grant period; 5@$10,000 thereafter | Advisory Board; external reviewers
June-Nov., 2006 | * | "Dunbar Detonations": Centennial observances of P.L.Dunbar's death | Dunbar Project Group | X
Fall, 2007 | * | Pilot Humanities Ambassadors Programs | NCHE; K-12 Ed Task Force; regional scholars; local teachers | X
| * | Submit B.A. proposal for Undergraduate Regional Studies to Curriculum Council | Ohio U American Studies Steering Committee | X
Year 7 |  | January-December, 2008
July, 2008 | * | Center endowment complete--full implementation funding available
| * | Funded reference, research, media projects begin | Advisory Board/external reviewers
| * | K-12 Summer Institute (Riverine & Lake Cultures); follow up with distance learning modules | NCHE, Riverine Roundtable,
| * | Undergraduate Humanities Internships with regional organizations | Internship Advisory Group | X | X
Sept., 2008-June, 2009 | * | Visiting Professorship (at CRHC) | Advisory Board or designee; committee from sponsoring institution; | X |  | X
Year 8 |  | January-December, 2009
AY 2009-10 | * | Visiting Professorship (elsewhere in region) | Advisory Board or designee; committee from sponsoring institution; | X |  | X