## Regional Tidal Marsh Database
SiteID | ProjectName | City/Town | State/Province | Area | WaterBody | Latitude | Longitude | Owner | Cost | Funded | Historic | Alteration | Impacts | Restoration | Status | Date | Contact1 | Contact2
MA002 | Argilla Road Salt Marsh restoration | Ipswich | MA | 80937 | Patterson Creek | 424084 | 704669 | Trustees of the Reservation | 10k-100k | y | S. patens | tidal restriction | freshwater retention/invasive vegetation | culvert enlargement | post-mon/second year | 2000-09-20 | Eric Hutchins | John Catena
MA004 | Conomo Point | Essex | MA | 4704 | Essex River | 423862 | 704475 | Town of Essex | <10k | y | S. patens | tidal restriction | freshwater retention/invasive vegetation | culvert enlargement | permitted/implementation | 2000-11-08 | Bruce Gilian | Eric Hutchins
MA006 | Fishermans Bend | Gloucester | MA | 31363 | Boston Harbor | 422228 | 705897 | Town of Winthrop |  | y | S. patens | fill | invasive vegetation | fill removal/ditching | none | 2000-11-08 | Steve Block | Eric Hutchins
MA008 | Little Neck | Ipswich | MA | 43124 | Eagle Hill River | 424229 | 704864 | Ipswich/ECGA/prv | 10k-100k | y | S. patens | tidal restriction | freshwater retention/invasive vegetation | culvert enlargement | pre-mon/permitted | 2000-11-08 | Vicky Boundy | Eric Hutchins
MA010 | Eastern Point | Winthrop | MA | 39852 | Gloucester harbor | 423489 | 703489 | Mass Audubon Society | 10k-100k | y | S. patens | tidal restriction | freshwater retention/invasive vegetation | culvert enlargement | pre-mon | 2000-11-08 | Robert Buchsbaum | Eric Hutchins
ME001 | Weskeag Marsh-Phase 1 | South Thomaston | ME | 22577 | Weskeag River Estuary | 440400 | 690900 | pub-MDIFW | 10k-100k | y | E2EM/S. patens | ditching | altered hydrology | ditch plugging | post-mon | 2000-11-13 | Lois Winter | Ron Joseph
ME003 | Weskeag Marsh-Phase 2 | South Thomaston | ME | 238765 | Weskeag River Estuary | 440430 | 690900 | pub-MDIFW | 10k-100k | y | E2EM/S. patens | ditching | drained marsh/altered hydrology | ditch plugging | post-mon | 2000-11-13 | Lois Winter | Ron Joseph
ME005 | Weskeag Marsh-Phase 3 | South Thomaston | ME | 153781 | Weskeag River Estuary | 440430 | 690900 | pub-MDIFW | 10k-100k | y | E2EM/S. patens | ditching | drained marsh/altered hydrology | ditch plugging | post-mon | 2000-11-13 | Lois Winter | Ron Joseph
ME007 | Weskeag Marsh-Phase 4 | South Thomaston | ME | 554422 | Weskeag River Estuary | 450000 | 690800 | pub-MDIFW | >100k | y | E2EM/S. patens | ditching | drained marsh/invasive vegetation | ditch plugging | implementation expected in a few weeks | 2000-11-13 | Lois Winter | Ron Joseph
ME009 | Sprague River Marsh-North Phase | Phippsburg | ME | 91055 | Sprague River | 434430 | 694945 | nfo-Nature Conservancy ME | 10k-100k | y | E2EM/S. patens | tidal restriction/ditching/fill | drained marsh/invasive vegetation/altered hydrology | ditch plugging/fill removal/perimeter ditch | implementation planned for 1/2001 | 2000-11-13 | Lois Winter | Ron Joseph
ME011 | Sprague River Marsh-Beach Phase | Phippsburg | ME | 246859 | Sprague River | 434400 | 694930 | nfo-Bates College,Morse Mtn. Conservation Corp. | 10k-100k | y | E2EM/S. patens | ditching | drained marsh/altered hydrology | ditch plugging | implementation | 2000-11-13 | Lois Winter | Ron Joseph
ME013 | Chauncey Creek Marsh-Gerrish Island Phase | Kittery | ME | 181705 | Chauncey Creek | 430515 | 704000 | nfo-Kittery Land Trust | 10k-100k | p | E2EM/S. patens | ditching | drained marsh/invasive vegetation/altered hydrology | ditch plugging/perimeter ditch | pre-mon | 2000-11-13 | Lois Winter | Ron Joseph
ME015 | Chauncey Creek Marsh-Seawall Phase | Kittery | ME | 101172 | Chauncey Creek | 430515 | 703955 | nfo-Kittery Land Trust | 10k-100k | n | E2EM/S. patens | ditching | drained marsh/invasive vegetation/altered hydrology | ditch plugging | pre-mon | 2000-11-13 | Lois Winter | Ron Joseph
ME017 | Scarborough Marsh-Libby River Culvert | Scarborough | ME |  | Libby River | 433345 | 701830 | pub-MDIFW | >100k | n | E2EM/S. patens | tidal restriction | drained marsh/invasive vegetation | culvert enlargement | pre-mon | 2000-11-13 | Lois Winter | Phil Bozenhard
ME019 | Scarborough Marsh-Libby River Phase A | Scarborough | ME |  | Libby River | 433400 | 701830 | pub-MDIFW | 10k-100k | p | E2EM/S. patens | ditching/fill | drained marsh/altered hydrology | ditch plugging/fill removal | pre-mon | 2000-11-13 | Lois Winter | Phil Bozenhard
ME021 | Scarborough Marsh-Nonesuch River | Scarborough | ME |  | Nonesuch River | 433515 | 701900 | pub-MDIFW | >100k | n | E2EM/S. patens | roadway berm | drained marsh/invasive vegetation/altered hydrology | ditch plugging/berm removal | none | 2000-11-13 | Lois Winter | Phil Bozenhard
ME023 | Scarborough Marsh-Seavey Point | Scarborough | ME |  | Scarborough River | 433315 | 702100 | pub-MDIFW | 10k-100k | n | E2EM/S. patens | ditching | drained marsh/altered hydrology | deepen pannes | pre-mon | 2000-11-13 | Lois Winter | Phil Bozenhard
ME025 | Scarborough Marsh-Rt 1 Mudflats | Scarborough | ME |  | Dunstan River | 433420 | 702300 | pub-MDIFW | 10k-100k | n | E2EM/S. patens | ditching | drained marsh/altered hydrology | ditch plugging/deepen pannes | pre-mon | 2000-11-13 | Lois Winter | Phil Bozenhard
ME027 | Scarborough Marsh-Cascade Brook | Scarborough | ME |  | Cascade Brook | 433330 | 702245 | pub-MDIFW | >100k | n | E2EM/S. patens | fill | invasive vegetation | fill removal | none | 2000-11-13 | Lois Winter | Phil Bozenhard
NH002 | Awcomin Marsh Ecosystem Restoration | Rye | NH | 76890 | Rye Harbor | 430019 | 704523 | pub/State Park | >100k | y | S. patens | fill | invasive vegetation | fill material manipulation | expected to start 10/01/00 | 2000-09-20 | Jim Raynes | John Catena
NH004 | Little River Salt Marsh Restoration | N. Hampton/Hampton | NH | 607031 | Atlantic Ocean | 425743 | 704676 | pub/prv/ASNH | >100k | p | S. patens | tidal restricition | freshwater retention/invasive vegetation | culvert enlargement | pre-mon | 2000-09-25 | Ted Diers | Eric Hutchins

## Contacts
CONTACT | ORGANIZATION | ADDRESS | CITY | STATE/PROVINCE | ZIPCODE | PHONE | FAX | EMAIL
Steve Block | Wetlands Restoration and Banking Program, Mass. EOEA | One Winter St. 5th Floor | Boston | MA | 2108 | 617-292-5743 |  | steve.block@state.ma.us
Vicky Boundy | Eight Towns and the Bay, c/o Merrimack Valley Planning Commission | 160 Main St. | Haverhill | MA | 1830 |  |  | vboundy@mvpc.org
Phil Bozenhard | MDIFW | RR1, 358 Shaker Rd. | Gray | ME | 4039 | 207-657-2345 |  | philip.bozenhard@state.me.us
Robert Buchsbaum | Coastal Ecologist William B. Endicott Wildlife Sanctuary | 346 Grapevine Rd. | Wenham | MA | 1984 | 978-927-1122 |  | rbuchsbaum@massaudubon.org
John Catena | NMFS | 1 Blackburn Dr. | Gloucester | MA | 1930 | 978-281-9313 |  | john.catena@noaa.gov
Ted Diers | NH Coastal Program | 2 1/2 Beacon St. | Concord | NH | 3301 | 603-271-1775 | 603-271-1728 | t_diers@osp.state.unh.us
Bruce Gilian | Town of Essex DPW | 44 Centennial Rd. | Essex | MA | 1929 | 978-768-6262
Eric Hutchins | NMFS | 1 Blackburn Dr. | Gloucester | MA | 1930 | 978-281-9313 |  | eric.hutchins@noaa.gov
Ron Joseph | USFWS | 1033 S. Main St. | Old Town | ME | 4468 | 207-865-5938 |  | ronald_joseph@fws.gov
Jim Raynes | Chair for Rye ConCom |  | Rye | NH |  | 603-431-6962 | 603-964-5523
Lois Winter | USFWS | 4R Fundy Rd. | Falmouth | ME | 4105 | 207-781-8364 |  | lois_winter@fws.gov