## Sheet1
EHS Systems-related tasks |  |  | (Revised 9/30/2002)
Area | Task # | Task Description | Who | Time estimate | Depends on | EPA deadline | When to do task (tentative)
Labs DB | L1 | Tweak current prototype Labs DB for Hazard-type by room | JR | 3 days |  |  | Oct, 2002
| L2 | Decide on list of Hazard Types, using Mitch Galanek's list as a starting point | MG, JR, others | 1 day |  |  | Oct, 2002
| L3 | Make sure Mitch's effort to collect Labs Registration data is coordinated with Katie Blass's effort to renew data for Green Sheets | MG, KB, JR | 1 day |  |  | Oct, 2002
| L3.5 | Decide how to handle DLC-based form info. (Paper forms and simple Excel spreadsheet?) | MG, SIG | 2 days |  |  | Oct, 2002
| L4 | Collect Lab Registration and new Green Sheet data from departments | EHS Office Lead contacts for each DLC | 2 months | L2, L3, L3.5 |  | Nov - Dec, 2002
| L5 | Input Lab Registration and new Green Sheet data into prototype Labs DB | EHS Office | 2 months | L1, L2, L3, concurrent with L4 |  | Dec, 2002 - Jan, 2003
| L6 | Reevaluate data model, UI of Labs Database prototype based on knowledge gained from inputing data. Make tweaks to prototype Labs DB, continue reevaluating. | JR | 2-4 weeks | L5 (at least partial completion) |  | Feb - Mar, 2003
| L7 | Resolve issue of keeping track of people by facility or by PI. | high-level mgmt | ? |  |  | Oct, 2002 - Feb, 2003
| L8 | If necessary, change Labs Database to record people's activities by PI rather than by facility | JR | 0-4 days | L7 |  | Mar, 2003
| L9 | Collect and input people/activity/place-or-PI information to prototype Labs DB | EHS Office | 1-2 months | L5, L8 |  | Mar - Apr, 2003
| L10 | Keep up with changes in labs in other facilities, keeping data in prototype system up to date | EHS Office | a few hours per month | L5 |  | Continuing
| L11 | Write down specifications for Labs Database schema and UI based on information gained -- use specs for future production system | JR | 1-2 weeks | L6, L8 |  | Apr, 2003
Training | T1 | Make the interim program for determining training needs more general, using easily-updated tables of requirements, based on a combination of the following criteria: (a) Activities the person performs, (b) Job title, (c) DLCs the person is affiliated with, (d) Proximity to certain hazard types, (e) Enrollment in certain lab courses. | JR | 1-2 weeks |  |  | Oct - Nov, 2002
| T2 | Add LDS-derived info on people's appointments to known data on people's DLC and PI affiliations | JR | 1 day |  |  | Oct, 2002
| T3.1 | Build a web interface for updating training rules | JR | 1-2 weeks |  |  | Dec, 2003
| T3.2 | Decide on the rules for determining training needs - allow the traiing team to try different scenarios in a test system | Training team + others | 1-2 months |  |  | Jan - Mar, 2003
| T4 | Complete the work for data feeds between ehsweb and Netcasters | JR, Netcasters | 2-4 days |  |  | Oct - Nov, 2002
| T5 | Get a more complete list of PIs and facility supervisors. | JR | 1-2 days | L5 |  | Jan - Feb, 2003
| T6 | Finish work to integrate the interim ehsweb server with live training information | JR, Kevin C. | 1-3 days |  |  | Dec, 2002
| T7 | Implement nightly uploads of training information into the Warehouse, where people will be able to run more sophisticated reports than those available with the Traincasters software. | JR, Warehouse team | 2-3 days | T4, T5 |  | Jan, 2003
| T8 | Write one or two Brioquery reports for Warehouse-based training reports | Warehouse team | 1-2 days | T7 | April, 2003 | Jan, 2003
Auditing | A1 | Write down list of items to be audited | Audit team | ? |  | Dec, 2002 | Oct - Dec 2002
| A2 | Review and revise data model for auditing | Audit team + JR | 2 weeks |  |  | Nov - Dec, 2002
| A3 | Build mockup or prototype system to store list of items to be audited, who does auditing, etc. (Interface with Roles Database) | ? | 2-4 weeks | A2 |  | Jan - Mar, 2003
| A4 | Input list of items to be audited, rules for who does auditing (based on Roles DB roles), etc. into prototype system | EHS Office | ? | L5, A1, L2 |  | Apr, 2003
| A5 | Write down specifications for auditing system that can be used for future production system | ? |  | A3, A4 | June, 2003 | May, 2003
Misc. Data modelling and planning | M1 | Update "EHS Data Flow Diagram" - add Inventory component, update other components | JR + ? | 1 week |  |  | Nov 2002 - Jan 2003
Ingegrated EHS Office Data | E1 | Build local EHSO system to keep track of "protocol" information | Seth S. | ? |  |  | Oct - Dec 2002
| E2 | Populate data in "protocol" info DB | Seth S. + others |  | L5, E1 |  | Jan - Feb 2003
Inventory | I1 | Investigate options for implementing an inventory system in SAP, taking into account integration points with Roles Database and Labs Database | ? | 2-4 weeks | M1 |  | Feb 2003 - May 2003