## ACTIVE
Facility | Classify | Type | Title/Description | Status/Next Action | Next Action | Date Next Action Due | Est. Date to DOE | Date Received by DOE | Date Complete | Lead(DOE, SBO, DIV) | Class | Program Importance | Institutional Importance | Security | Environment | Ease of Implementation | Rank Priority | Comments
Top LANL/Safety Issues
DVRS (N) |  | Facility | HA for HC-2 Campaign | Facility developing HA (BIO) | LANL |  |  |  |  | Steele, Kobi, McLain | S1
RLWTF (N) |  | Activity | PDSA (TA-50 tanks): New tanks at RLWTF to replace existing tanks. | Under review by NNSA | DOE |  | 2003-10-17 | 2003-10-20 |  | Janke, Kobi, Johnson | L1
RANT (N) | Master | Facility | HC2 BIO and TSR | SER Issued | DOE | 2003-12-12 | 2003-12-12 | 2003-12-11 | 12/23/003 | Steele/Janke, Kobi, McLain | S1
WCRRF (N) | Master | Facility | HC-2 BIO and TSR | Respond to NNSA comments | LANL |  |  |  |  | Nez, Kobi, McLain | S1
WETF (N) |  | USQ | Implementation of DF HQLTS vessels | LANL Generating TSR Pg. Changes | LANL | 2003-09-28 | 2003-08-26 | 2003-08-28 |  | Sandoval, Reed, Sutcliffe | S1 | [6 empty] | USQ affects SC-SSC
TSD (N) |  | Activity | TSR page changes (Bubble Wrap) | Under review by NNSA | DOE |  | 1211//2003 | 2003-12-12 |  | Nez, Nolan,King | C3
TSD (N) |  | Activity | TSR page changes (Tie downs) | Under review by NNSA | DOE |  |  | 2003-11-19 |  | Houghton, Nolan, King | C3
Compliance Issues
[12 empty] | 25 | 20 | 20 | 20 | 15 | 100
ER Sites (N) |  | Facility | Prep DSA for General's Tanks | SBO review 70% draft. Comment to RRES | LANL |  | TBD |  |  | TBD, Villegas, Chris well | C1
ER Sites (N) |  | ER Site | ER Sites DSA for S&M | 0% Scoping Meeting | LANL |  |  |  |  | TBD, Edmonds, Hurdle | C1
Area G |  | Facility | FWO-WFM 04-006: IP to address controls and conditions requested SER | Under review by NNSA | DOE |  |  | 2004-01-13 |  | TBD, Nolan, McLain | C1
Area G |  | Facilty | FWO-WFM 03-129: DSA and TSR Revision. SABT NS:121703: Close out DOE memo | Complete | DOE |  |  | 2003-12-09 | 2003-12-17 | Sandoval, TBD, McLain | C2
Area G |  | Facility | FWO-DO:03-121TSR Page Change request | Under NNSA Review | DOE |  |  | 2003-12-23 |  | TBD, Nolan, McLain | C2
TA-8-23 (N) | Master | Facility | HC-2 DSA and TSR | Under review by NNSA | DOE |  |  | 2003-03-28 |  | Tom, Reed, Anaya | C2
TSFF (N) | Master | Facility | HC-2 BIO and TSR | Facility withdrew DSA to update | LANL | 2004-03-31 | 2004-03-31 | 2003-04-10 |  | TBD, Edmonds, Tingey | C2
RLWTF (N) | Master | Facility | HC-2 BIO and TSR | Re-review to comform to issues rasied in PDSA | LANL |  |  |  |  | Janke, Kobi, McLain | C2
TA-55 (N) |  | Facility | FSAR/TSR update. | DOE Reviewing pending higher priorities | DOE |  | 2002-04-02 | 2003-01-09 |  | Knoell, Peters, Gordon | C2
Mod Units (N) |  | Facility | PDSA | IR Comments to support CD-2 PDSA | LANL | 2003-10-08 | 2003-11-26 |  |  | Steele/Janke, Peters, Granzow | C2
Site Wide |  | Activity | Revised Radiological Facility Definition | SBO rework change justification | LANL |  | TBD |  |  | TBD, Nolan, Satterwhite | C2
Site Wide |  | Activity | Define Major Modification for Purposes of Requiring a PDSA | SBO developing white paper to support definition. | LANL |  | 2003-12-22 |  |  | TBD, Satterwhite, Satterwhite | C2
Site Wide |  | Site | PSWFASRP PSA of PSAIA IP and AB Compliance Plan | Under review by NNSA | DOE |  | 2003-09-10 | 2003-10-01 |  | Houghton, Satterwhite, Stanford | C3
External Obligation Issues
TA-55 (N) |  | USQ | MIS Can PrHA | Under review by NNSA. | DOE | 2002-12-20 | 2003-01-03 | 2003-01-03 |  | Nez-Lambight,Peters, Vigil | O1 | [6 empty] | Upgraded from L2 to O1
Site Wide |  | Activity | LIR 300-00-05.3 revision | Incorporating new direction | LANL | 2003-12-12 |  |  |  | TBD, Nolan, Satterwhite | O1
CMR (N) |  | Activity | HA on clean out of Test vessels | Incorporating Comments | LANL |  |  |  |  | Tom, Peters, Gordon | O1
BTF |  | Activity | Vault Modification | Project construction placed on hold. | LANL |  |  |  |  | TBD, Edmonds, Norman | O1
BTF |  | Activity | Cartridge Filter House Modification | MST decision to proceed or hold construction in progress | LANL |  |  |  |  | TBD, Edmonds, Norman | O1
Site Wide |  | USQ | PISA/USQ Emergency Evacuation of the Central Alarm Station | Under review by NNSA | DOE |  | 2003-09-18 | 2003-09-23 |  | Houghton,Kobi, Streit | O1
TA-18 (N) |  | Activity | Amend TA-18: IP schedule change for installation of the temperature SCRAM |  | LANL |  | 2004-01-30 |  |  | TDB, Nolan, Pellette | O1
Site Wide (N) |  | Activity | Develop Aircraft Accident Analysis | 30% DSA under development | LANL |  |  |  |  | Nez, Kobi, Satterwhite | O1
Site Wide |  | Site | Configuration Modification, Vital Safety System (DNFSB) | Under review by NNSA | DOE | 2003-10-02 | 2003-10-02 | 2003-10-03 |  | Tom, Nolan, Bays | O1
TA-15 ATOC |  | Facility | FHC of the ATOC as a RAD Facility, Cat C Facility for Phase One Operation | Under review by NNSA | DOE |  | 10/22/203 | 2003-10-27 |  | Fredlund, Reed, Barnett | O1
TA-18 (N) |  | Activity | Update TA-18 Temperature Monitoring/Scram System for Critical Assemblies | DOE requested update 11/21/2003 | LANL | 2003-12-12 | 2003-12-12 |  |  | TDB, Reed, Pellette | O1
Site Wide (N) |  | Site | Update Nuclear Facility List | Out for review by POCs (Incorporate ER Site Data) | LANL |  | 2003-02-23 |  |  | Houghton, Kobi/Villegas, Satterwhite | O2
Site Wide (N) |  | Site | Update Rad Facility Inventory List | Letter request to RDL for input | LANL |  | 2003-02-23 |  |  | TBD, Villegas, Satterwhite | O2
Site Wide |  | Activity | LIR 300-00-07.3 revision | Awaiting LIR 300-00-05 for path forward | LANL | 2003-12-24 |  |  |  | TBD, Nolan, Satterwhite | O2
BTF | Master | Facility | Develop FSA | In progress | LANL |  |  |  |  | TBD, Nolan, Edmonds | O2
Sigma | Master | Facilty | Develop FSA | In progress | LANL |  | 2004-01-03 |  |  | TBD, Nolan, Edmonds | O2
BTF | Master | Facility | Change Due Date of FSA | DOE extended due date for FSA | DOE |  | 2003-12-03 | 2004-12-23 | 2004-01-07 | TBD, Nolan, Edmonds | O2
Sigma | Master | Facility | Change Due Date of FSA | Under review by NNSA | DOE |  |  | 2003-12-23 |  | Fredlund, Nolan, Edmonds | O2
Programmatic Issues
[12 empty] | 25 | 20 | 20 | 20 | 15 | 100
TA-55 (N) |  | Activity | PF-41 Mod to Support NDE Ops | PDSA to be developed | LANL |  |  |  |  | TDB, Peters, Gordon | L1 | [5 empty] | 0
TA-55 |  | TSR | TSR Page Change for Op Training resources. | Under review by NNSA | DOE |  |  |  |  | Nez. Peters, Peters
CMR (N) |  | USQ | CMR DSA Amendment (NMT-DO:03-283) | Under review by NNSA | DOE |  | 2003-11-19 | 2003-11-24 |  | Houghton, Peers, Gordon | L1 | 0 | 0 | 0 | 0 | 0 | 0 | Institutional importance is a "5" because of INP. On critical path for schedule.
TA-55 (N) |  | USQ | Parts sanitation furnace |  | LANL |  |  |  |  | TBD, Peters, Vigil | L3 | [5 empty] | 0
CMR-R (N) |  | Facility | PDSA at CD1 Level (Draft PDSA) | Facility resolving NNSA comments | LANL |  |  |  |  | TBD, TBD, Nelson | L3 | 0 | 0 | 0 | 0 | 0 | 0 | Institutional importance is a "5" because of INP. On critical path for schedule.
PHERMEX |  | Facility | Down grade facility to Low Hazard | Facility to present planned approache | LANL | 2003-12-17 |  |  |  | TBD, Reed, Barnett | L4
TA-18 (N) |  | Activity | Cost benefit analysis to implement DSA upgrades | Schedule budget review meeting with LANL. | DOE |  |  | 2002-10-28 |  | Tom, Pellette, Goen | L6 | [5 empty] | 0
WETF (N) |  | Activity | Cost benefit analysis to implement DSA upgrades | Schedule budget review meeting with LANL. | DOE |  |  | 2002-10-08 |  | Knoell, Sutcliffe, Goen | L6 | [5 empty] | 0
TA-8-23 (N) |  | Activity | Cost benefit analysis to implement DSA upgrades | Schedule budget review meeting with LANL. | DOE |  |  | 2003-01-29 |  | Tom, Anaya, Goen | L6 | [5 empty] | 0
| Master = Master Schedule (PS-OAB-903, Rev 2) | [7 empty] | CLASS: | S pertains to safety issues
| USQ = unreviewed safety questions | [8 empty] | C pertains to compliance issues
| COLOR CODE: RED are changes made by LANL since the last update, BLUE are changes made by DOE since the last update | [8 empty] | O pertains to obligation issues
L pertains ot programmatic issues

## SUCCESSES
Facility | Title/Description | Status Next Action | Date R'cd by DOE | Completed | POC | Class
CMR (N) | Change CMR BIO Update Schedule | Approed | 2003-12-15 | 2003-12-16 | Steele, Peters, Gordon | O1
TA-18 (N) | TA-18 Inventory Changes | Approved | 2003-11-04 | 2003-11-21 | Tom, Nolan, Pellette | O1
CMR (N) | Request for Additional IAEA Training Activities at CMR | Approved | 2003-10-20 | 2003-11-21 | Houghton, Peters, Sasa | O1
CMR (N) | Extension SR for MAR Inventory over Xmas Break | Approved | 2003-10-20 | 2003-11-21 | Houghton, Peters, Sasa | C2
ER Sites (N) | Hazard Categorization of ER Sites | Approved | 2003-11-21 | 2003-11-26 | Steele, Villegas, Hurdle | C1
Area G (N) | HC-2 BIO and TSR | Approved | 2003-04-10 | 2003-11-28 | Sandoval, Peters, McLain | S1
Site Wide (N) | USQ Procedure, Rev. 3 | Approved | 2003-06-19 | 2003-11-04 | Tom, Kobi, Marth | C2
TA-18 (N) | TSR change for increased MAR to accommodate OSRP containers | Approved | 402771 | 2003-11-21 | Tom, Nolan, Pellette | C2
LANSCE (N) | Extension of DSA and SAD Submittal Dates | Approved |  | 2003-11-14 | Nez, Kobi, Seely | C2
TSD (N) | TSD Implementation Extension | Approved | 2003-11-06 | 2003-11-06 | Janke, Nolan, Smith | C2
TSD (N) | Annual Update for TSR and Annual Summary of USQD | Approved | 2003-11-04 | 2003-11-06 | Steele, Nolan, Smith | C2
RC-1 | Request to downgrade facility to low hazard. |  | 2003-10-14 | 2003-11-15 | TBD, Villegas, Bolig | L5 | 0
TA-35-189 | Trident Laser Facility Rad Facility Concurrence request | NNSA reversed facility categorization. Remove to Success List | 2003-10-07 | 2003-10-30 | Fredlund, Nolan, Erickson | L3
RANT (N) | LL BIO Extension | Autorization to extend LL BIO to March 31, 2004- Move to success list |  | 2003-10-29 | Janke, Peters, McLain | C1
Site Wide (N) | SB documentation modified to reflect reorganization and change of TSR responsibilities | Success | TA-55: 3/31/03 LANSCE: 4/7/03 CMR: 1/27/03 | 2003-10-29 | Knoell, Satterwhite, Hayes | C1
WCRRF (N) | Letter request to advance purchase GB | Include in BIO rewrite - move to success list | 2003-08-27 | 2003-10-30 | Nez, Peters, McClain
WETF (N) | Accurate mesurement of Halon agent in the Halon Suppression system in Rm 110 | Approved | 2003-10-23 | 2003-10-29 | Knoell, Edmonds, Sutcliffe
TA-18 (N) | Accident analyses mod to include 18.28 kg MAR from School House | Approved | 2003-10-14 | 2003-10-22 | Tom, Nolan, Pellette | C2
Site Wide (N) | LANL DSA Annual Update Schedule - Request for LASO Review and Concurrence. PS-DO: 03-174 | Approved | 2003-07-31 | 2003-10-22 | Janke, Kobi, Satterwhite | C2
TA-18 (N) | Amend Facility SB-TA-18 TSR Administrative Change; NIS-6:03-194 | Approved | 2003-09-17 | 2003-09-17 | Steele, Nolan, Pellette | C2
WCRRF (N) | HC-2 BIO and TSR | Returned to LANL with Comments | 2003-04-08 | 2003-10-02 | Nez, Peters, McLain
TA-55 (N) | Request to remove Pu Storage Glovebox; NMT-14:03-075 | Approved | 2003-09-15 | 2003-09-17 | Steele, Gordon, Satterwhite
TA-18 (N) | Amendment to TA18 Implementation Plan | Approved | 2003-08-28 | 2003-09-11 | Tom/Nolan/Pellette
WETF (N) | Deviation from SER Containerization Requirements, Nuclear Safety Basis Violation, Lightning Considerations and Further MAR Required Reductions | NNSA approved deviation and revises SER. | 2003-09-04 | 2003-09-04 | Steele, None, Sutcliffe | S1
Site Wide (N) | PISA/USQ Flyover | Rejected and added new action to prepare AC AA/DSA. | 2003-07-08 | 2003-09-11 | Nez, Kobi, Marth | C2
WETF (N) | PISA/USQ on "Standard Tub" containers. |  | 2003-08-26 | 2003-09-17 | Sandoval, Reed, Sutcliffe | S1
WETF (N) | WETF TSR Page Changes | Approved Move to Success | 2003-07-15 | 2003-07-15 | Knoell, Dick/Angelo, Tingey | C2
TA-55 (N) | Amend Safety Basis, Waste storage rack- door open:NMT-14:03-065 |  | 2003-08-11 | 2003-08-19 | Steele, Peters, Gordon | S1
CMR (N) | Additional NIS-IAEA Training Activities at CMR | Success | 2003-07-31 | 2003-08-01 | Houghton, Kobi, Sasa | L
TA-18 (N) | Request for amendment to facility SB IP: NIS-6-03:148 | Success | 2003-07-25 | 2003-07-30 | Tom, Nolan, Pellette | L
RANT (N) | Request to extend current SB | Success | 2003-04-17 | 2003-08-26 | Janke, Peters, McLain
Site Wide (N) | Request for ecosystem assessment over flight: HSR-5-03-150 |  | 2003-08-07 | 2003-08-14 | Nez, Kobi, Hurdle | L1
TA-18 (N) | TSR Rev. 1 |  | 2003-06-25 | 2003-08-01 | Steele, Nolan, Pellette | L
TA-18 (N) | Request for approval to enhance the IP scope and schedule, make minor corrections in content, and correct typographical errors in the IP Appx A. Memo: NIS-6-03:94 | NNSA did not approve the request and returned it with comments for resolution | 2003-05-20 | 2003-05-30 | Tom/Satterwhite/Pellette
TA-18 (N) | Memo supersedes NIS-6-03:59 to change the TSRs to correct an error in the original letter. The proposal is to add a statement to clarify the use of robust containers. Memo: NIS-06-03:99 | NNSA returned for clarification. | 2003-05-20 | 2003-05-30 | Tom+K13/Satterwhite/Pellette | L3
TA-18 (N) | Request for amendment to increased MAR Levels (NIS-06-0-60) | NNSA did not approve the request and returned it with comments for resolution | 2003-04-01 | 2003-05-30 | Tom/Pellette | L3
BSL3 | LANL request for concurrence for a plan for authorization BSL-3 facility operations through the development of a SB document. Memo Bioscience 03-084 | LANL is working on resolving DOE comments | 2003-05-14 | 2003-06-11 | Janke/Satterwhite/Trewhella | L2
TSTA (N) | Request to approve extension of certain SER Conditions of Approval | NNSA approves request | 2003-05-28 | 2003-05-28 | Nez/Hanson | L2
TA-18 (N) | Request for TSR modification for adding Fire King #kr5021-2 safe to the list of approved ROBUST CONTAINERS (NIS-6-03:58) | DOE approves | 2003-04-01 | 2003-06-05 | Sandoval/Pellette | L3
Site Wide (N) | Program for Waste Management (a joint LANL/LASO document) |  | 2003-05-20 | 2003-06-09 | Nez/(Holt-Zerkle-Ramsey-Stanford)/?? | L2
RLWTF (N) | PDSA (TA-50 tanks): New tanks at RLWTF to replace existing tanks. | Conditional Approval | 2003-05-07 | 2003-07-03 | Nez & Janke, Lambergeti, Kobi | L2
DVRS (N) | Review 2b Tech Defense Report | DOE concurs | 2003-05-21 | 2003-06-20 | Janke/Peters/Christensen | L2
TA-55 (N) | Hazard Analysis Scrap Recovery: DNFSB commitment and tied to a NASA mission to Pluto | Approved | 2003-01-15 | 2003-05-29 | Knoell, Steele | O1
WETF (N) | WETF TSR Page Changes | Returned to LANL. | 2003-06-19 | 2003-07-07 | Knoell/??? | C
TSTA (N) | Review of TSTA Implementation Plan | NNSA Disapproves Request | 2003-04-30 | 2003-05-29 | Nez/TBD/TBD | C2
ER Sites (N) | Request to categorize General's Tanks as Cat 2 nuke and to use a HASP to conduct characterization activities.. | Feedback on proposed methodology | 2003-05-09 | 2003-05-23 | Houghton, Villegas, Criswell | C2
TSTA (N) | Request to downgrade TSTA from Nuclear HC3 to Radiological and Non-nuclear Hazard Category C | Request conditionally approved | 2003-06-09 | 2003-06-18 | Nez/Hanson
RC-1 (N) | Hazard Categorization to downgrade RC-1 from Hazard Category 3 to Radiological | NNSA approves | 2003-04-04 | 2003-05-21 | Janke, Villegas, Bolig | C1
RC-1 (N) | Strategy for RC-1 Downgrading | NNSA approves proposed strategy | 2003-05-02 | 2003-05-02 | Steele/Sattelberger | C1
RANT (N) | Continuation of Approved Limited Life BIO beyond June 1, 2003 | NNSA Approved: Can now work until Sept 4th |  | 2003-05-07 | Janke
TA-55 (N) | Request for Interperation on Certain type of Ammunition. | NNSA Approved | 2003-04-23 | 2003-04-30 | Nez | L
TA-18 (N) | Proposal to add statement to DF2 and DF5 to clarify the use of robost containers for HEU-FL10 Solution (NIS-60-03:59) | TSR Change approved | 2003-04-01 | 2003-05-02 | Tom/Pellette | L3
TA-55 (N) | USQ: Amend Safety Basis - Air System request to add air compressor | Not approved by NNSA | 2003-01-02 | 2003-05-07 | Janke, Koch | L3
ER Sites (N) | Request to use EM Methodogy to categorize inactive Potential Release Sites (PRSs). | Not approved by NNSA | 2003-02-19 | 2003-05-05 | Janke, Villegas, Criswell | C1
Area G (N) | Memo for path forward for inclusion of Mod Units in final DSA for QTW |  | 2002-11-25 | 2003-04-30 | Schlapper, Satterwhite, Knoell | O1
TA-8-23 (N) | Continued operations after expiration of JCO | Requested additional info, but allowed extension to 4/30/03 | 2003-03-13 | 2003-04-09 | Tom/Steele
RANT (N) | Continuation of Approved Limited Life BIO beyond June 1, 2003 | Returned to Lab for additional data | 2003-03-14 | 2003-04-10 | Janke
RC-1 (N) | Another request to remove from Nuclear List | Not approved. No documentation to support below HC3 | 2003-04-04 | 2003-04-09 | Janke/Steele | L3
WETF (N) | Request to accept meeting SER commitment on containerization | Not accepted because insufficient justification | 2003-04-09 | 2003-04-10 | Knoell/Hanson | O1
Site Wide (N) | Request to extend Site Wide JCO beyond 4/10/2003 | Extension not approved | 2003-04-09 | 2003-04-09 | Steele/Gordan
TA-18 (N) | Change request to AB for IP based on SER | NNSA Approves | 2003-03-04 | 2003-03-24 | TBD, Pellette | C2
TA-18 (N) | Request for TSR modification | NNSA Approves | 2003-01-13 | 2003-03-24 | Tom, KSK, Pellette
TSFF (N) | BIO Facility Cat 2 to Cat 3 | Returned to LANL |  | 2003-03-24 | Knoell, Reed, TBD | C1
Area G (N) | Development of Hazard Category 2 DSA and TSRs (TA-54) | Not Apporved, Returned to LANL | 2002-12-31 | 2003-03-11 | Sandoval, Peters, Schepens | C1
WCRRF (N) | Development of Hazard Category 2 BIO (TA-50) | Not Apporved, Returned to LANL | 2003-02-06 | 2003-03-24 | Nez, Peters, Vigil | C1
RLWTF (N) | Development of Hazard Category 2 DSA and TSR (TA-50) | Not Apporved, Returned to LANL | 2003-01-21 | 2003-03-25 | Janke, Peters, McLain | C1
TA-18 (N) | Amend TA-18 AB to allow sample material. NNSA Conditionally Approves | NNSA Conditionally approves | 2003-01-23 | 2003-03-06 | Tom, Pellette | L1
TA-18 (N) | Change request to AB for IP based on SER | COMPLETE | 2003-03-04 | 2003-03-24 | TBD, Pellette | C2
TA-18 (N) | Request for TSR modification | COMPLETE | 2003-01-13 | 2003-03-24 | Tom, KSK, Pellette | C2
TSTA (N) | BIO/TSR - Downgrade to HC3 Nuclear Facility to rad facility. NNSA Conditional Approves | COMPLETE |  | 2003-03-24 | Knoell, Koch Reed, Tingey | C1
RC-1 (N) | Request to receive and process medical radioisotope target | COMPLETE | 2003-03-06 | 2003-03-07 | Janke
RC-1 (N) | Processing Radioisotope Targets | COMPLETE | 2003-03-06 | 2003-03-07 | J anke/Satterwhite | L2
TA-55 (N) | Amendment Request for Laser Ablation | COMPLETE | 2003-02-11 | 2003-02-14 | Tom, Koch | C2
TA-18 (N) | NIS School at Bldg. 127 | COMPLETE | 2003-01-31 | 2003-02-03 | Tom/Satterwhite | L3
TA-55 (N) | TSR Change - Fire Loop | COMPLETE | 2003-01-31 | 2003-02-10 | Knoell, Satterwhite | L3
RC-1 (N) | Facility Path Forward | COMPLETE | 2003-01-30 | 2003-02-04 | Janke Satterwhite | C2
CMR (N) | Continuation | COMPLETE | 2003-01-29 | 2003-02-03 | Capshae, Satterwhite | L3
TA-55 (N) | Security Upgrades | COMPLETE | 2002-12-18 | 2003-01-16 | Nez
TRANSPORTATION | TSR Implementation Plan | COMPLETE | 2002-12-16 | 2003-01-30 | Janke, Satterwhite | L3
Site Wide | Non-nuclear facility hazard categorization, request for extension of due-date "after April 10, 2003 | COMPLETE | 2002-12-13 | 2002-12-16 | Nez, Satterwhite, Kim
PHERMEX | Change to Safety Survey Report | COMPLETE | 2002-12-12 |  | Sandoval, Koch, Hockaday
OWR | HASP Addendum for Restart of D&D activities | COMPLETE | 2002-11-27 | 2002-12-05 | Koch
DVRS | Technical defense report for DBRS (Mass Balance) | COMPLETE | 2002-11-22 | 2002-12-12 | Nez
RANT (N) | Limited Life BIO | COMPLETE | 2002-11-19 | 2002-12-23 | Steele, Janke, Koll, TBD
Site Wide | Rad Facility Inventory | COMPLETE | 2002-11-14 |  | Janke , Kim, Nolan
LANSCE (N) | Temporary Exceedance of TSR Limit in Actinide BIO | COMPLETE | 2002-11-04 | 2002-11-08 | Janke, Knoell, Kjm, Selvage
Site Wide (N) | JCO - FM Restructuring | COMPLETE | 2002-10-28 | 2002-11-27 | Steele
TSFF (N) | TSFF Experiment HA | COMPLETE | 2002-10-25 | 2002-12-11 | Sandoval, Koch. Tingey
TSTA (N) | Change in CA for Moisture Collector HA | COMPLETE | 2002-10-25 | 2002-12-11 | Sandoval, Koch, Tingey
TA-8-23 (N) | Request for Amendment to current SB | COMPLETE | 2002-10-17 | 2002-11-27 | Sandoval
TRANSPORTATION | Sitewide DSA | COMPLETE | 2002-09-30 | 2002-11-08 | Rowsome/Janke, Kim, Orourke
Site Wide | Rad Facility Inventory List | COMPLETE | 2002-09-26 | 2002-10-25 | Janke, Kim, Nolan
RANT (N) | RANT DSA Upgrade Program Redirection | COMPLETE | 2002-09-13 | 2002-09-13 | Steele, Peters, Bolig
DARHT (NN) | Axes 1 & 2 SAD | COMPLETE | 2002-08-29 | 2002-11-06 | Capshaw, Koch
DARHT (NN) | DX Forklift Operations HA | COMPLETE | 2002-08-19 | 2003-01-09 | Sandoval. Koch, Garner
Site Wide | Request for Temporary Suspension of DSA Annual Update Schedule | COMPLETE | 2002-08-06 | 2002-08-08 | Steele/ Kim/Kim
Site Wide | Updated Nuclear Facility List | COMPLETE | 2002-07-27 | 2002-07-25 | Nez, Kyo, Nolan
TA-18 (N) | Authorization for Substition of the Neutron Source in Godiva IV Glory Hole | COMPLETE | 2002-07-17 | 2002-07-31 | Janke/Nolan/Pellette
TA-55 (N) | PrHA for PF-41 Radiography Operations | COMPLETE | 2002-07-09 | 2002-07-19 | Sandoval, Koch, Vigil
Site Wide | 10CFR830 Subpart B Compliance Management Plan Update | COMPLETE | 2002-06-28 | 2002-06-30 | Tom/ Kim/Nolan
TA-48 (N) | Issued SER for BIO/TSR | COMPLETE | 2002-06-28 | 2002-08-15 | Janke, Peters, Vigil
TA-18 (N) | Uranium Solutions to CMR | COMPLETE | 2002-06-26 | 2002-08-01 | Janke/ Nolan/Pellette
CMR (N) | CMR Approved Container | COMPLETE | 2002-06-17 | 2002-06-20 | Rowsome, Koch, Partain
LANSCE (N) | Remove Target 4 from nuclear list | COMPLETE | 2002-06-17 | 67/8/2002 | Capshaw, Kim, Seely
CMR (N) | Backward Looking USQ Related to Stand Pipe System Event Circa 1997 | COMPLETE | 2002-06-14 | 2002-06-14 | Janke, Peters, Partain
CMR (N) | CMR Request to Change ITSRs for School House MAR | COMPLETE | 2002-06-14 | 2002-07-18 | Wald, Koch, Partain
TA-18 (N) | Authorization for Neutron Source in Godiva Glory Hole | COMPLETE | 2002-06-13 | 2002-06-14 | Orders/Nolan/Pellette
CMR (N) | Backward Looking USQ Related to Water Hammer Event Circa 1997 | COMPLETE | 2002-05-23 | 2002-05-23 | Janke, Peters, Partain
Area G (N) | HA for Modular Transportables, comments to facility | COMPLETE | 2002-05-14 | 2002-06-03 | Janke, Peters, McLain
DVRS | Hazard Analysis for Radiological Operations | COMPLETE | 2002-05-06 | 2002-05-09 | Tom, Peters, McLain
WETF (N) | HA New Experiment | COMPLETE | 2002-04-24 | 2002-04-26 | Steele/Knoell, Koch, Sutcliffe
TA-18 (N) | U-2001-532, Radiolytic Gas Production in SHEBA PISA, Rev. 1 | COMPLETE | 2002-04-23 |  | Wald, Livingston, DeYoung
TA-55 (N) | NNSA Response to DNFSB: Pu-238 Scrap Recovery | COMPLETE | 2002-04-23 | 2002-06-07 | Steele
LANSCE (N) | BIO for Storing Activated Components in LANSCE Bldg 53-3 Sector M "Area A East" | COMPLETE | 2002-04-05 | 2002-04-06 | Steele/Orders, Kim, Fink
TSTA (N) | Oxidation of UH Storage Beds, Amendment to Facility Safety Basis | COMPLETE | 2002-04-05 | 2002-04-12 | Knoell, Koch, Tingey
TA-55 (N) | PISA Glovebox Overpressurization | COMPLETE | 2002-04-01 | 2002-05-06 | Sandoval, Peters, Gordon
TA-18 (N) | Issued SER for BIO/TSR | COMPLETE | 2002-03-15 | 2002-07-30 | Tom, Nolan, Pellette
LANSCE (NN) | Interim SAD | COMPLETE | 2002-03-08 | 2002-04-25 | Tom/Rowsome, Kim, Graham
TA-18 (N) | MAR Limit Change for MMV, Approval of | COMPLETE | 2002-03-06 | 2002-03-06 | Steele,
TA-55 (N) | USQ 01-088, Instrument Air Supply from Process Air | COMPLETE | 2002-03-05 | 2002-03-13 | Wald, Peters, Gordon
HPTF (N) | Remove from nuclear list | COMPLETE | 2002-03-01 | 2002-03-28 | Knoell, Koch, Grace
TA-8-23 (N) | JCO DSA Effective Date Change | COMPLETE | 2002-02-28 | 2002-02-28 | Steele, Koch, Anaya
CMR (N) | HA SM-154 | COMPLETE | 2002-02-25 | 2002-03-14 | Janke, Nolan, Partain
CMR (N) | USQ 02-001, Crane Controller | COMPLETE | 2002-02-25 | 2002-03-22 | Order, Nolan, Partain
TSTA (N) | TSTA-01-003, Removal of TPE Glovebox thru Exterior Wall | COMPLETE | 2002-02-21 | 2002-02-28 | Knoell, Livingston, Tingey
TA-18 (N) | Resubmittal of NIS School , Bldg. 127 | COMPLETE | 2003-02-04 | 2003-02-04 | Tom/Satterwhite | L3
WETF (N) | DSA/TSR SER issued | COMPLETE | 2002-01-24 | 2002-04-09 | Knoell, Koch, Sutcliffe
Site Wide | Non-nuclear facility list | Nonconcur | 2002-01-22 | 2002-04-25 | Nez, Sasser, Nolan
TA-8-23 (N) | JCO addendum (Final) | COMPLETE | 2002-01-10 | 2002-01-11 | Tom, Koch, Anaya
TA-18 (N) | Material Relocation Project | COMPLETE | 2002-01-10 | 2002-01-11 | Steele, TBD, Pellete
TA-18 (N) | U-2001-491 Flattop Control Rod Limits --Returned by DOE with alternative engineered control | COMPLETE | 2002-01-09 | 2002-03-08 | Sandoval, Livingston, DeYoung
TA-8-23 (N) | JCO addendum | COMPLETE | 2001-12-02 | 2001-12-02 | Steele,
TA-55 (N) | NMT-14:01-088, PF-4 Sprinkler System, As Found Condition | COMPLETE | 2001-11-29 | 2001-12-18 | Wald/Capshaw, Koch, Gordon
CMR (N) | JCO on Sprinkler Operations | COMPLETE | 2001-11-06 | 2001-11-07 | Knoell
Site Wide | USQ Procedure Rev. 2 | COMPLETE | 2001-10-30 | 2001-11-30 | Wald, Marth, Sasser
Site Wide | Project PrHA for Cerro Grande Fire Rehabilitation Project - Task 16 Rev 0.0 | COMPLETE | 2001-10-24 | 2001-12-20 | Wald
TA-55 (N) | Removal of the Metal Preparation Glovebox Line | COMPLETE | 2001-10-17 | 2001-10-17 | Steele, Sasser, Art
CMR (N) | Subproject Nuclear Safety Hazards Analysis for Emergency Notification System | COMPLETE | 2001-10-15 | 2001-10-16 | Sandoval, Fischer,Orr
LANSCE | Emergent Condition: PISA/USQ on 1l Beam Target | COMPLETE | 2001-10-04 | 2001-10-08 | R. Tom, K. Kim, Fink
PHERMEX | Safety Survey |  | 2001-09-24 |  | Capshaw, Koch, Sasser
DARHT (NN) | Amendent to the DARHT Facility Safety Bases | COMPLETE | 2001-09-21 | 2001-10-21 | Steele
CMR (N) | USQ-01-082 Increased Vehicular Traffic through CMR Facility | COMPLETE | 2001-09-20 | 2001-09-20 | Steele, Koch, Partain
TA-55 (N) | Fire Protection Yard Main Replacement Project SB change for construction | COMPLETE | 2001-09-18 |  | TBD, McClure, Gordon
CGP Facility | Facility Safety Analysis for moderate hazard facility | DEFERRED | 2001-09-17 |  | Nez, Kim
LANSCE (N) | JCO for A Target |  | 2001-09-06 | 2002-01-15 | Capshaw, Kim, Donahue
LANSCE (N) | JCO for WNR Target 4 | COMPLETE | 2001-08-10 | 2001-09-06 | Tom, Kim, Donahue
Site Wide | USQ Quality Sampling Process | COMPLETE | 2001-08-01 | 2001-08-03 | Tom, Marth, Sasser
Site Wide | USQ Process Quality Review Guidance | COMPLETE | 2001-07-31 | 2001-08-03 | Tom, Marth, Sasser
TSTA (N) | HA for De-Inventory of Mositure Collectors | COMPLETE | 2001-07-25 | 2001-08-13 | Knoell, Koch, Michelotti
TA-18 (N) | Nuclear Mat'l STD for School Activities | COMPLETE | 2001-07-23 | 2001-07-23 | Steele, Sasser,Pellette
WETF (N) | MAR removal for Seismic Upgrade of Shelves | COMPLETE | 2001-07-19 | 2001-07-23 | Knoell
TA-55 (N) | 01-066, Staging of Waste Outside of PF-4 (PISA) | COMPLETE | 2001-07-18 | 828/2001 | Knoell, Marth, Gordon
Site Wide | 10CFR830 Management Plan | COMPLETE | 2001-06-26 | 2001-06-29 | Tom, Nolan, Sasser
LANL Special Project | Vessel Standard: approved by Crandall, issue with COR AL/HQ acceptance of vessel | COMPLETE | 2001-06-15 | 2001-07-11 | Steele, Sasser, Papazian
CMR (N) | Develop ITSR (Rev. 4) | COMPLETE | 2001-06-13 | 2001-07-19 | Nez, McClure, Orr
Site Wide | Nuclear Facility List | COMPLETE | 2001-06-06 | 2001-06-13 | Capshaw
TA-48 (N) | Justification to Extend JCO until 1/1/02 | COMPLETE | 2001-05-24 | 2001-06-07 | Steele, Marth, Helmick
DARHT (NN) | Firing Site HA Ligthning protection plan | COMPLETE | 2001-05-22 | 2001-06-06 | Steele, Sasser,Taylor
TA-18 (N) | U-2000-U-99-305, Operration of a Non-Sealed Tube Neutron Generator at TA-18, Rev 1m 11/3/00 | COMPLETE | 2001-05-22 | 2001-05-30 | Tom, Crawford, Pellette
WETF (N) | MAR Increase | COMPLETE | 2001-05-07 | 2001-05-07 | Steele
BTF (NN) | DSA extention request | COMPLETE | 2001-05-02 | 2001-05-18 | Nez
CMR (N) | CMR-Wing 9 Request for Additional MAR for Special Fabrication | COMPLETE | 2001-05-02 | 2001-05-03 | Steele, Orr
CMR (N) | Hood washdown fume capture system. | COMPLETE | 2001-05-01 | 2001-06-26 | Sandoval
CMR (N) | Medical Radioisotope Program | COMPLETE | 2001-05-01 | 2001-10-11 | Sandoval, Fischer,Orr
TA-16-411 | Remove from nuclear list | COMPLETE | 2001-04-23 | 2001-05-01 | Knoell/Capshaw
TA-8-22 | Remove from nuclear list | COMPLETE | 2001-04-23 | 2001-05-01 | Knoell
SIGMA (NN) | Condition of Approval Clarification | COMPLETE | 2001-04-19 | 2001-05-18 | Nez
CMR (N) | Upgrade Emergency Notification System SNSHA | COMPLETE | 2001-04-10 | 2001-04-20 | Sandoval
LANSCE (N) | Actinide BIO | COMPLETE | 2001-04-10 | 2001-10-29 | Steele/Rowsome, Kim, Graham
TA-55 (N) | USQD 01-034, Portable Water Tank | COMPLETE | 2001-04-05 | 2001-04-23 | Sandoval
Site Wide | Nuclear facilities meeting 10CFR830 requirements | COMPLETE | 2001-04-01 | 2001-05-17 | Tom, McClure
WETF (N) | 90% FSAR and issuance of DOE comments | COMPLETE | 2001-03-30 | 2001-05-11 | Knoell
TSTA (N) | TSTA Stablization Project-Authorization Basis Transition Plan | COMPLETE | 2001-03-23 | 2001-04-02 | Sandoval, Sasser, Tinge
Site Wide | USQ Procedure | COMPLETE | 2001-03-21 | 2001-04-05 | Tom, Sasser
TA-55 (N) | USQ-00-048, Accelerated Aging Project (HATCH) | COMPLETE | 2001-03-14 | 2001-05-03 | Wald, Laul, Nelson
WCRR | TA-50-69-01-162, Gas Generation Testing in Drum Equilibration Transportainer | COMPLETE | 2001-03-13 | 2001-04-06 | Wald, Nolan, Vigil
WCRR | ITSR/HA update | COMPLETE | 2001-03-12 | 2001-04-10 | Koch
SIGMA (NN) | Safety survey for moderate hazard facility | COMPLETE | 2001-03-05 | 2001-04-25 | Tom
TA-55 (N) | USQD 00-091, FSWSS Corrosion and the Use of Pipe Repair Clamps to Repair Leak | COMPLETE | 2001-03-05 | 2001-04-03 | Tom/Capshaw, Bolig, Gordon
SIGMA (NN) | Remove Sigma Facility from Nuclear Facility List | COMPLETE | 2001-03-02 | 2001-03-10 | Nez
Site Wide | LIRs 300-00-05, 06, & 07 | COMPLETE | 2001-02-26 | 2001-03-28 | Tom/Knoell/Nez
TA-18 (N) | U-2000-447, Critical Experiments Using U-235 and other Matrix Material | COMPLETE | 2001-02-21 | 2001-03-19 | Nez
TA-48 (N) | TA-48-01-167 Sodium Azide Operations in RC-1 | COMPLETE | 2001-02-12 | 2001-03-27 | Nez
CMR (N) | CMR JCO (Wing 7) Exit Request | COMPLETE | 2001-02-05 | 2001-02-05 | Sandoval
TA-18 (N) | Godiva Rossi-Alpha Measurements U-2000-442 | COMPLETE | 2001-02-01 | 2001-02-02 | Wald
TA-18 (N) | Godiva Administrative Controls U-2000-334 | COMPLETE | 2001-02-01 | 2001-02-02 | Wald
TA-48 (N) | Hazard Analysis for Perchlorate Ops at TA-48 | COMPLETE | 2001-01-31 | 2001-02-07 | Koch
CMR (N) | JCO f/ Wing 7 HEPA Replacement | COMPLETE | 2001-01-26 | 2001-01-26 | Wald/Steele
DARHT (NN) | Firing Site HE modeling report for off axis shots | COMPLETE | 2001-01-23 | 3/27/201 | Koch
DARHT (NN) | Second Axis SAD | COMPLETE | 2001-01-22 | 2001-03-08 | Whitman
TA-18 (N) | COMET (ZEUS Experiment) USQ | COMPLETE | 2001-01-19 | 2001-03-06 | Nez
TA-18 (N) | Receipt of Remainder of NIS-5 Standards for School Activities | COMPLETE | 2001-01-17 | 2001-02-05 | Kamiar/Wald
WCRR | TSR Changes for HEPA Filter surveillance | COMPLETE | 2001-01-05 | 2001-01-11 | Wald
CMR (N) | Request to approve Perchorate Action Level | COMPLETE | 2000-12-18 | 2001-02-02 | Steele
TA-18 (N) | 70% BIO Review | COMPLETE | 2000-12-18 | 2001-03-08 | Koch
WETF (N) | New FSAR/TSR 70% Review | COMPLETE | 2000-12-18 | 2001-02-09 | Knoell
Site Wide | Surveillance wavier for Xmas week | COMPLETE | 2000-12-14 | 2000-12-14 | Steele
Site Wide | Non-nuclear safety survey memo per App F 1.2.f | COMPLETE | 2000-11-29 | 2000-11-29 | Steele
CMR (N) | ITSR updates (Rev 3) | COMPLETE | 2000-11-27 | 2000-12-12 | Sandoval
TA-18 (N) | Lower DR for sealed sources from CMR | COMPLETE | 2000-11-17 | 2000-11-21 | Steele
TA-55 (N) | USQD, KARDEX seismic analysis | COMPLETE | 2000-11-16 | 2001-03-09 | Tom/Kimbal
TA-55 (N) | Surveillance procedure and basis change for H2 detectors | COMPLETE | 2000-11-02 | 2000-11-15 | Knoell
CMR (N) | Hot Cell Delta Pressure Monitors "SNSHA" | COMPLETE | 2000-11-01 | 2000-11-21 | Sandoval
LANSCE | Explosives HA | COMPLETE | 2000-10-30 | 2000-11-08 | Koch
WETF (N) | Roof Upgrade, Safety Plan | COMPLETE | 2000-10-05 | 2000-10-11 | Knoell
CMR (N) | Subproject 96-Fire Protection System | COMPLETE | 2000-10-02 | 2000-10-13 | Sandoval
TA-55 (N) | USQ for Installation of Shield Wall in NDA area | COMPLETE | 2000-09-28 | 2000-09-28 | Steele
TA-18 (N) | USQ for Flooding | COMPLETE | 2000-09-21 | 2001-05-29 | Kimbal/Wald
CMR (N) | Subproject #85, Internal Power Distribution | COMPLETE | 2000-09-20 | 2000-10-18 | Nez
CMR (N) | Hot Cell Controls/Radiation Monitor | COMPLETE | 2000-09-20 | 2000-12-21 | Nez
TA-18 (N) | Vault USQ for transfer of material from CMR | COMPLETE | 2000-09-16 | 9/17/200 | Wald/Chung
DARHT (NN) | Off Axis Explosive Shots for Modeling Input | COMPLETE | 2000-09-15 | 2000-10-11 | Koch
DARHT (NN) | Explosives tests at DARHT axis 1 firing site | COMPLETE | 2000-09-15 | 2000-10-11 | Koch
TWISP (N) | TSR Changes | COMPLETE | 2000-09-12 | 2000-09-26 | Wald
TWISP (N) | Criticality safety analysis (SER COA) | COMPLETE | 2000-09-01 | 2000-09-21 | Wald
CMR (N) | Fire Suppression System LCO updated | COMPLETE | 2000-08-10 | 2000-12-12 | Sandoval
TA-55 (N) | USQ for Pu-238 Scrap Recovery | COMPLETE | 2000-07-31 | 2000-12-01 | Wald
TA-48 (N) | JCO | COMPLETE | 2000-07-28 | 2000-08-18 | Koch
TA-18 (N) | TSR Changes for TA-18 due to last TSR violation | COMPLETE | 2000-05-01 | 2000-10-02 | Wald/Nez
TWISP (N) | BIO/SER | COMPLETE | 2000-04-24 | 2000-06-26 | Wald
TWISP (N) | TWISP USQ Procedure Approval | COMPLETE | 2000-03-24 | 2000-09-20 | Koch
LANSCE | LANSCE 1L BIO | COMPLETE | 2000-03-08 | 2000-03-22 | Koch
WCRR | BIO/ITSRs | COMPLETE | 2000-02-11 | 2000-03-11 | Koch
CMR (N) | BIO | COMPLETE | 1998-08-26 | 1998-08-31 | Steele
BTF (NN) | BTF change to Combustible Loading Limits | COMPLETE |  | 2000-09-20 | 7
CMR (N) | ITSR (Rev. 2) | COMPLETE |  | 2000-01-31 | Steele
CMR (N) | Hood Washdown System Upgrade | COMPLETE |  | 2000-06-26 | Sandoval
CMR (N) | Emergency Lighting Upgrade | COMPLETE |  | 2000-07-20 | Sandoval
CMR (N) | Personnel Accountability Upgrade | COMPLETE |  | 2000-08-16 | Sandoval
CMR (N) | Operations Center Upgrade | COMPLETE |  | 2001-06-13 | Sandoval
CMR (N) | Mosler Record Safe Model 308030 for CMR inventory contr | COMPLETE |  | 321/00 | Sandoval/Jofu, Fischer, Orr
DARHT (NN) | SA for Explosion Only | COMPLETE |  | 1999-08-01 | Galvin
DARHT (NN) | DARHT Phase II SAD, Rev. 2.1 | COMPLETE |  | 2001-05-02 | Koch
LAAO | EH Authorization Basis Finding closure package | COMPLETE |  | 2000-09-26 | Nez
RAMROD (N) | SAR | COMPLETE |  | 1998-08-01 | Steele/Galvin
RAMROD (N) | SAR Addendum for Gas Generation Test | COMPLETE |  | 2000-07-01 | Koch
RAMROD (N) | Downgrade from Haz Cat 2 to Rad facility | COMPLETE |  | 2003-01-13 | Koch, Sandoval
RANT (N) | Safety Analysis | COMPLETE |  | 1998-02-01 | Galvin
RLWTF (N) | ITSR | COMPLETE |  | 1999-09-01
Site Wide | LAAO Safety Basis Review Procedure | COMPLETE |  | 2000-09-08 | Nez
Site Wide | Closeout of all FY00 Unsatisfactory USQDs | COMPLETE |  | 2000-09-29 | Steele
TA-8-23 (N) | JCO Extension | COMPLETE |  | 2002-11-06 | Steele, Koch
TA-18 (N) | Flattop USQ | COMPLETE |  | 1999-05-27
TA-18 (N) | 30% BIO Review | COMPLETE |  | 2000-03-09 | Wald
TA-18 (N) | 90% review BIO/TSR | COMPLETE |  | 2001-05-18 | Wald
TA-55 (N) | TSR | COMPLETE |  | 1999-10-01
TA-55 (N) | USQ for 6 MeV LINAC Experiment at TA-55 | COMPLETE |  | 2000-05-05 | Sandoval
TA-55 (N) | Fire water cost benefit/risk analysis | COMPLETE |  | 2001-02-05 | Knoell
TA-55 (N) | DOE comments 90% TA-55 SAR upgrade | COMPLETE |  | 2001-04-18 | Knoell
TA-55 (N) | 70% SAR upgrade by DP-45 | COMPLETE |  |  | Chung
TA-55 (N) | Pigma Welder | COMPLETE
TA-8-23 (N) | JCO Extension | COMPLETE |  | 2002-11-06 | Tom, Koch
Area G (N) | 70% FSAR/TSR reiew | COMPLETE |  | 2000-12-07 | Koch
BTF (NN) | BTF USQ Procedure | COMPLETE |  |  | Nez
LANSCE (NN) | PRAD Hazard Analysis | COMPLETE |  | 2000-12-08 | Koch