## Sheet1
CIWQFS PDT Study Tasks - 7/25/02
Task List Number | Internal/Contract | ID # | Task | Predecessor | Duration (WD) | Assumptions | Scope | Task Lead
1 |  | 1000 | Objective # 1 - Identify the Linkages between Water Quality and Ecosystem Restoration
1A | Internal | 1100 | Coordinate with the RECOVER Water Quality Team
1A1 |  | 1110 | ID tasks that could be duplicated between the two teams | N/A | 15 | 33 total man-days; see subtask breakdown for assumptions
|  |  | 1A1 subtask |  |  | Meeting prep: 0.5 day x 2 staff = 1 man-day; disciplines PDT Leader, EPJV?
|  |  | 1A1 subtask |  |  | Meeting between WQT and CIWQFS: 2dayx10staff = 20 man-days; disciplines = PDT leaders + additional COE and DEP staff + 2 EPJV
|  |  | 1A1 subtask |  |  | Prepare meeting summary and distribute for comments: 1 day x 1 EPJV staff = 1 man-day, plus 9 man-days (1 day x 9 staff) for staff comment; assume 6 working day comment period | meeting summary
|  |  | 1A1 subtask |  |  | summarize comments and prepare meeting report: 3 days x 1 staff = 3 man-days; EPJV or PDT Lead | meeting report with WQT tasks, CIWQFS tasks, and coordination schedule and milestones
1A2 |  | 1120 | ID which team is responsible for which task | 1A1 | *15 | *concurrent and identical to 1A1 | see above
1A3 |  | 1130 | ID tasks with shared responsibility | 1A1 | *15 | *concurrent and identical to 1A1
1A4 |  | 1140 | Integrate shared tasks into CIWQFS team and WQT task development schedules according to assigned responsibilities | 1A2; 1A3 |  |  | see above
1B | Contract | 1200 | Conduct a comprehensive lit review of WQ efforts on ecosystem structure & function
1B1 |  | 1210 | Develop lit search strategy and keywords/criteria | N/A | 15 | Two individuals using established research methodology will develop a strategy. This is a two week effort for two people to research and develop the strategy. An additional week of effort for two people to compile the list of key words and criteria. Disciplines = a hydrologist/hydraulic engineer and an environmental scientist. 1 week = 5 working days, total man-days required for this task is 30. | Write-up of search strategy with list of topics and keywords and the associated criteria.
[5 empty] | add 3 more days | Comment on 1B1: suggest that search strategy needs to start with team input on search topics, keywords and sources; this would add 1-2 days to the total man-days
1B2 |  | 1230 | Compile existing bibliographies | 1B1 | 60 | CIWQFS literature search subteam formed to do this task (approx. 8 people including 5 DEP/COE scientist); disciplines include water quality specialist, ecologist, environmental scientist; environmental engineer; total effort = 15 days x 5 staff = 75 man-days.
[6 empty] | Subteam reviews results of schedule and prepares list of topics covered plus additional topics needed to search. Presents list of proposed additional topics to PDT for input. 2 days meetings x 5 staff to coordinate. | Updated list of coverage and strategy for remainder of seach.
1B3 |  | 1240 | Conduct additional literature searches to expand and update bibliography | 1B2 | 40 | CIWQFS literature search subteam formed to do this task (approx. 8 people including 5 DEP/COE scientist); disciplines include water quality specialist, ecologist, environmental scientist; environmental engineer; total effort = 15 days x 5 staff = 75 man-days.
1B4 |  | 1250 | Develop searchable bibliographic database | 1B1* | 90 | *Assumes that database is developed concurrently with the literature search. | draft and final database
|  |  | 1B4 subtasks |  | 20 | Design and set-up database; discipline requires one information technology specialist for 20 man-days; present db design at CIWQFS meeting for approval; revise
|  |  | 1B4 subtasks |  | 40 | Database entry: IT specialist for 40 man-days
|  |  | 1B4 subtasks |  | 10 | review cycle
|  |  | 1B4 subtasks |  | 20 | finalize database and put on Internet
1C | Internal | 1300 | Evaluate possible use of conceptual ecosystem models as a project framework
1C1 |  | 1310 | ID WQ linkages and gaps in existing conceptual models | 1B4 | 60 | This task should require approx. three 2-day workshops to cover all of the existing conceptual models. Propose grouping related CMs for purposes of the workshops. Staff would include CIWQFS PDT members and experts on the specific conceptual models being developed. This would require bringing in people from USGS, academia, and possibly outside Florida.
|  |  | 1C1 subtask |  | 30 | workshop planning and preparation: 1.5 day x 4 staff = 6 man-days per workshop x 3 workshops = 18 man-days; disciplines include project manager, water quality specialist, ecologists, environmental scientist, consultant/facilitator
|  |  | 1C1 subtask |  | 30 | Conduct three 2-day workshops. Assume attendance by 8 COE/DEP staff at each workshop = 16 man-days per workshop x 3 workshops = 48 man-days.
1C2 |  | 1320 | Expand existing conceptual models to fill identified WQ gaps | 3A; 1C1 | 100 | See subtask below
|  |  | 1C2 subtasks (a) |  | 40 | Develop workshop report with recommended steps for task 1C2. Each draft workshop report is estimated to take 15 day x 1 staff = 15 man-day plus 10 man-days for staff comment for each workshop, plus 4 staff days to revise each workshop report = 87 man-days for all three workshops. Follow-up workshop/PDT meeting to affirm workshop reports. Total duration to complete the reports and have a follow-up workshop would be about 40 days | draft and final workshop reports
|  |  | 1C2 subtasks (b) and c |  | 60 | Conduct additional 2-day workshops to develop new conceptual models identified in the report. Assume need for 3 additional workshops with attendance by 8 COE/DEP staff at each workshop = 16 man-days per workshop x 3 workshops = 48 man-days.
1D | Internal | 1400 | Prioritize WQ issues for the study based on lnks to ecological restoration
1D1 |  | 1410 | Choose prioritization criteria | 1C2 | 40 | This task is accomplished using a 2-day PDT workshop/meeting, with facilitation to help with prioritization tasks. Probably spans two PDT monthly meetings
|  |  | 1D1 subtask |  |  | Meeting prep: 3 day x 2 staff = 6 man-day; disciplines EPJV, Ecologist or WQ Specialist subteam leader
|  |  | 1D1 subtask |  |  | PDT meeting/workshop: 2 day x 10 staff = 20 man-days; disciplines = PDT leaders + additional COE and DEP staff + 2 contractor/facilitators
|  |  | 1D1 subtask |  |  | Prepare meeting summary and distribute for comments: 1 day x 1 staff = 1 man-day, plus 9 man-days for staff comment; assume 10 working day comment period | draft meeting report
|  |  | 1D1 subtask |  |  | Finalize priorities report: 6 days x 1 staff = 6 man-days | final priorities report
1D2 |  | 1420 | Prioritize eco-region areas based on criteria including: extent of degradation, need for protection, and imporatnce to the C&SF project, the CERP, and other possible actions | 1D1 | ?? | see above
1D3 |  | 1430 | Prioritize specific WQ issues and criteria that need to be addressed in the study | 1D1 | ?? | see above
1E | Internal | 1500 | Write a report that includes a prioritized list of WQ issues, their linkages to ecosystem restoration, and their relationship to study tasks | 1A2; 1A3; 1D2; 1D3; 1B4
|  |  | 1E continued |  | 30 | Writing team prepares final report, 15 man-days of writing. Duration assumes about 15 days to revise report and 15 day comment period. | final report
2 |  | 2000 | Objective # 2 - Identify Degraded and At-Risk Waters
2A | Internal | 2100 | Establish Method to Identify Degraded Waters |  |  | Contract to conduct unbiased review
2A1 |  | 2110 | Define degradation | 2A3 | 1 month | 10 Sr. Scientists for 1 day; 1 contractor (for compilation of comments and minutes) for 1 day; 1 person to plan the meeting for 1 day; 10 people for 2-week comment period; 10 people for 1/2 day to review.
2A2 |  | 2120 | ID additional water parameters and surrogate water quality measures | 1E; 2A3 | 1 month | 10 Sr. Scientists for 1 day; 1 contractor (for compilation of comments and minutes) for 1 day; 1 person to plan the meeting for 1 day; 10 people for 2-week comment period; 10 people for 1/2 day to review.
2A3 |  | 2130 | Compile existing methods | 2A5 | 12 days | 2 Mid-level Scientists for 1 week; 1 Sr. Scientist for 2 days | To evaluate how well the degradation definition is
2A4 |  | 2140 | Define and delineate water bodies | 2A3 | 1 month | 3 Sr. Scientists and 1 GIS Analyst to attend 4 meetings (like a workshop; held consecutively over 4 days); 2 additional meetings (1 north, 1 west coast) with 1 logistics person | TAC
2A5 |  | 2150 | Form a team to establish method | N/A | 1 day | 1 person to send letter and invitations to meeting; 1 day for PDT to decide who will be on the team (TAC) | Constructing a team at PDT meeting
2A6 |  | 2160 | Write method | 2A1; 2A2 | 1 month | 3 Scientists for one week; 10 Scientists with on e day each to review
2B | Contract | 2200 | Data Compilation |  |  | Contract / working with SFWMD using Battelle
2B1 |  | 2210 | Assemble existing water quality data | 2A2 | 1 month | 1 Scientist and 1 Programmer | Batelle Contract and contractor who gets assembly contract; Comprehensive water quality database in a standardized format
2B2 |  | 2220 | Apply CERP data Quality Management Protocol | 2B1 | 1 day | Maxine Cheeseman | A database that has been validated for quality and can confidently be used to determine baseline information
2C | Contract | 2300 | Compare Existing Data to Method (Data Analysis)
2C1 |  | 2310 | ID tools needed to accomplish data analysis | 2A6 | 30 hours | Use PDT members for one hour at a PDT meeting | Comparing existing data to method
2C2 |  | 2320 | Produce list and map of existing degraded waters and at-risk waters | 2E3 | 100 + 50 | 2 Scientists and 1 Mid-level Scientist; 10 weeks
2C3 |  | 2330 | Id data gaps for future data collection | 2C1; 2A4 | 10 days total | 2 people - 1 GIS Analyst, 1 Database specialist; 1 week per person | Report identifying the various data deficiencies in the compiled water quality database
2D | Internal | 2400 | ID methods and party responsible to fill remaining data gaps
2D1 |  | 2410 | Which can be filled | 2C3 |  | Perform at same time as 2E1
2D2 |  | 2420 | Who fills these | 2D1 |  | Perform at same time as 2E1
2D3 |  | 2430 | Timeframe necessary to close the gap | 2D2 |  | Perform at same time as 2E1
2E | Contract | 2500 | Field Sampling to fill data gaps
2E1 |  | 2510 | Develop sampling plan | 2C3; 2D3 | 2 months | 2 Scientists; 1 month each | Develop plan in concert with trips made for workshops in 2A4
2E2 |  | 2520 | Obtain field data | 2E1 | 18 months | 4 teams; 2 people per team | Field time and lab costs
2E3 |  | 2530 | Analyze data relative to methodology | 2E2; 2B2 | 1 month | 1 Sr. Scientist
2F | Internal / SFWMD Contract | 2600 | Project Future Condition through 2050 |  |  | Project future WQ (not plan formulation)
2F1 |  | 2610 | ID tools to project future water quality | 2A6 | 30 hours | Use one hour of PDT members during a PDT meeting
2F2 |  | 2620 | Use information from objective #3 to project future conditions | 2F1; 2E5 | 5 + 5 | 1 mid sci and 1 sci; 1 week --- (Dependent on 3E5)
2F3 |  | 2630 | Produce list and map of future conditions | 2F1; 2F2 | 10 + 10 | 1 mid sci and 1 GIS analyst; 1 week
3 |  | 3000 | Identify and Quantify Types and Sources of Pollution
3A | Contract | 3100 | ID historic, current and future land uses through 2050 | N/A | Elasped Time 6 months | Assumes 6 weeeks of time for cities and counties to send in comp plans.
3A1 |  | 3110 | FLUCCs - Florida Land Use and Cover Classifications / SFWMD |  | 20 | 2 GIS analysts 2 weeks
3A2 |  | 3120 | Review city and county comprehensive plans and regional planning council information |  | 30 + 25 | 1 week to review existing information, 1 sci and 1 GIS; 1 week to send out requests for information, 1 sci; 1 month to compile, 1 sci and 1 GIS analyst.
3A3 |  | 3130 | Historic vegetation, soils, and other maps |  | 20 | 2 GIS analysts 2 weeks
3B | Internal | 3200 | ID and quantify current and future permitted point source discharges |  | Elapsed Time 12 months | Includes 3 months time built in to account for other duties personnell may have.
3B1 |  | 3210 | Query databases (I.e. DEP) and comprehensive plans | 2A2 | 5 + 200 | 1 week determining who needs to be contacted, what are dulplicate records, and who has different permits, 1 mid-sci. 10 weeks entering data, 4 sci. | Data in format for 3B2
3B2 |  | 3220 | Compare actual to permitted discharges | 3B1 | 5 | 1 week, mid-sci
3B3 |  | 3230 | Produce current and future point source loading estimates | 3B2; 3F3; 3C1 | 260 | 2 modelers, 6 months (indlues IDing)
3C | Contract | 3300 | ID and Quantify Current and Future Permitted and Non-Permitted Non-Point Source Discharges |  | Elapsed Time 15 months | Includes 4 months time built in to account for other duties personnell may have.
3C1 |  | 3310 | Determine appropriate runoff coefficients | N/A | 30 | 3 weeks, 2 modelers
3C2 |  | 3320 | Query permitted non-point source databases and evaluate | 2A2 | 10 +200 | 2 weeks determining contacts and requesting information, 1 mid-sci; 10 weeks entering data, 4 sci.
3C3 |  | 3330 | Atmospheric loading estimates | 2A2 | 15 | 3 weeks, 1 modeler
3C4 |  | 3340 | Produce current and future non-point source loading estimates | 2A2; 3C2; 3C3 | 260 | 2 modelers, 6 months
3D | Contract with SFWMD or USGS | 3400 | ID Groundwater / Surfacewater Interactions |  | Elapsed Time 16 weeks | 6 weeks built in to allow for time for replies and to receive literature. | USGS = 50/50 cost share
3D1 |  | 3410 | Literature review | N/A | 25 | 5 weeks, sr. sci. | Report
3D2 |  | 3420 | ID and evaluate existing efforts and programs | N/A | 10 +5 | 2 weeks, 1 sci; 1 week, sr. sci.
3D3 |  | 3430 | ID critical areas of concern | 3D1; 3D2 | 5 | 1 week, 1 sr. sci | Report - probably combined with 3D4
3D4 |  | 3440 | Recommend areas for future study | 3D3 | 5 | 1 week, 1 sr. sci | Report - see above
3E | Internal/ Contract | 3500 | ID Water Quality Models and Ways to Integrate Their Output |  | Elapsed Time 12 months
3E1 |  | 3510 | ID data needs | N/A | 20 | 1 month, 1 sr. sci
3E2 |  | 3520 | Assessment of the output from water quality models | 3A; 3B3; 3C4; 3D3; 3E1 | 120 | 3 months, 2 sr. sci.
3E3 |  | 3530 | Develop needs analysis (models needed) | 1E | 20 | 1 month, 1 sr. sci
3E4 |  | 3540 | Develop modeling strategy | 3E2; 3E3; 5A; 5B; 5C; 5D | 15 | 2 days with 6 sr. sci at a meeting followed by 3 days for 1 sr. sci to write up results/notes
3E5 |  | 3550 | Implement modleing strategy | 3E4 | 260 | 6 months, 2 modelers.
3F | Internal | 3600 | ID Future Types and Sources of Pollution |  | Elapsed Time 4 months | 6 weeks built in to get papters, and 2 weeks built in to modeling time.
3F1 |  | 3610 | ID evolving technologies | 2A2 | 20 | 2 weeks, 2 sci. | Report
3F2 |  | 3620 | Land conversion for water storage | 3A | 20 | 2 weeks, 2 sci.
4 |  | 4000 | ID Appropriate Interim Restoration and Non-Degradation WQ Targets
4A | Internal/ Contract | 4100 | ID Appropriate Interim Restoration and Non-Degradation WQ Targets
4A1 | Internal/ Contract | 4110 | ID Existing targets | 2C2 | 3 months | form a team of 4 people (technicians); 3 technicians 20 hours/week; 1 Sr. 144 hours total; | review of technical publications; bibliography as end product with executive summary (approx. 2 pages)
4A2 | Internal/ Contract | 4120 | ID on-going efforts, timing and relevance to CERP | 2C2 | included in 4A1 | have same people as 4A2 complete this effort | state TMDL program; SWIM program; timing and when they will be finished; how they relate to the CIWQFS
4A3 | Internal/ Contract | 4130 | Target development procedures | 4A2; 4A5; 4A6 | 1 year | four groups w/ 2 Sr. scientists that assist them full time (1 year); and 7 experts will meet once/month and time to prepare (12 weeks) | must process and utilize existing data to come up with targets
4A4 | Internal/ Contract | 4140 | Recommend site specific alternative criteria where necessary or changes to state standards | 2C2; 4A3 | 3 months | Have one day workshop in each area or by type (3 workshops; 7 experts at each workshop); data has already been put together and analyzed; 2 Scientists to prepare and write up (5 weeks) | recommendation, not creating…look at areas that are problematic and have inappropriate criteria
4A5 | Internal | 4150 | ID Designated use and/or Outstanding Florida Waters (OFW) | 2C2 | 1 week | Janet Klem at FDEP doing this task; 1 GIS analyst 8 hours and 1 Env. Scientist | ID what classes are
4A6 | Internal/ Contract | 4160 | Identify specific loading targets | 3B; 3C; 4A4 | 6 months | 4 groups in 4A3 (7 Sr Scientists; 2 weeks); 1 modeler for each group (6 months); 2 Sr Scientists for 6 months - same people as 4A3 but add a modeler for each group | total load to system
5 |  | 5000 | Inventory and Evaluate the Suite of Structural and Non-Structural Measures throughout South Florida
5A | Contract | 5100 | Inventory and Evaluate Existing BMP Programs | 6B | duration = 1 year; time = 6 months | 6 Sr. Scientists (6 months over 1 year)/ 1 Expert (3 months); 1 GIS analyst (6 months) | do BMPs exist in area and are they sufficient; perform lit review;
5A1 |  | 5110 | State BMP efforts / programs
5A2 |  | 5120 | Regional / local BMP efforts / programs
5A3 |  | 5130 | Other state or Federal programs / examples
5A4 |  | 5140 | Develop synthesis and recommendation for the study
5B | Contract | 5200 | Inventory and Evaluate Operational Tool to Improve Water Quality | 6B | included in 5A | included in 5A
5B1 |  | 5210 | Regional / system-wide tools
5B2 |  | 5220 | Project / component-specific
5B3 |  | 5230 | Synthesis and recommendation for the study
5C | Contract | 5300 | Inventory and Evaluate Alternative Practices | 6B | included in 5A | included in 5A
5C1 |  | 5310 | Diversion
5C2 |  | 5320 | Fish / Plant harvesting
5C3 |  | 5330 | Sediment removal
5C4 |  | 5340 | Centrifuge
5D | Contract | 5400 | Inventory and Evaluate Structural Means to Improve Water Quality | 6B | included in 5A | included in 5A
5D1 |  | 5410 | STA
5D2 |  | 5420 | Reservoir
5D3 |  | 5430 | Chemical treatment / Advanced Wastewater treatement
5D4 |  | 5440 | Sediment removal
5D5 |  | 5450 | Sediment control
5D6 |  | 5460 | Stream channel restoration
5D7 |  | 5470 | Filter marshes
5E | Internal / Contract | 5500 | Perform Cost/Benefit Analysis of Pollutant Reduction Measures and Provide Recommendations | 5A; 5B; 5C; 5D | 6 months | 1 Economist (3 months); 1 Sr. Scientist (6 months); 1 Urban (1 month) & 1 Ag BMP Expert (1 month) | Sharon Tross (Everglades Stormwater Program)
5E1 |  | 5510 | Review Everglades Stormwater Program Standards of Comparison (ESWPSOC)
5E2 |  | 5520 | Unit costs
5F | Internal / Contract | 5600 | Write Recommendations Report | 5E | 6 months | 2 Sr. Scientists (2 months); 2 Scientists (2 months); 1 GIS analyst (2 months); 1 editor (2 months); 12 people to review (1 week); and 1 Scientist and 1 editor to do revisions (2 weeks) | includes synthesis; 1 chapter on BMP programs; 1 chapter on operational tools to evaluate water quality
6 |  | 6000 | Integrate Existing and Planned WQ Restoration and Management Programs (WQRMP)
6A | Contract | 6100 | Develop Evaluation Method / Criteria WQRMP | N/A
6A1 |  | 6110 | What is authorizing legislation |  | 90 | 270 total man-days, 3 people | a. Define WQRMP b. Computer search for WQRMP c. Field Reconnaisance Plan d. Report Format
6A2 |  | 6120 | Scale of WQRMP |  |  | included in 6A5 | a. Regulatory programs (permits) b. Planning Activities c. Activities associated with funding sources
6A3 |  | 6130 | ID individual program evaluation criteria |  | 2 | 4 total man days, 2 people
6A4 |  | 6140 | CIWQFS evaluation criteria |  | 26 | 50 total man-days
|  |  | 6A4 subtask |  | 10 | 40 total man-days, 4 people (included in 6A4) | CIWQFS evaluation criteria development
|  |  | 6A4 subtask |  | 3 | 3 total man-days, 1 person (included in 6A4) | Document and report CIWQFS evaluation criteria
|  |  | 6A4 subtask |  | 10 | n/a? | Peer review of CIWQFS evaluation criteria
|  |  | 6A4 subtask |  | 3 | 3 total man-days, 1 person (included in 6A4) | Finalization of CIWQFS evaluation criteria
6B | Govt Contract (probably OPS) | 6200 | Conduct Inventory of WQ restoration and management plans in the study area | N/A | 195 | includes 6B1-6B5
6B1 |  | 6210 | Define WQRMP |  |  |  | a. planning meeting b. computer search for evaluation criteria
6B2 |  | 6220 | Planning programs |  |  |  | a. Coverage/ Overlap of programs b. Success of individual program attaining their goal c. Environmental response d. Load reduction e. Stat e Water Quality Standards f. Scale of WQRMP g. AuthorLeg.
6B3 |  | 6230 | Funding stream (319 Program)
6B4 |  | 6240 | State/Regional/Local regulatory mechanisms
6B5 |  | 6250 | Aging and maintenance of programs (stormwater program)
6C | Contract | 6300 | Evaluate the Programs Using Method | 6A; 6B | 180 | 540 total man-days, 3 people
6D | Internal / Contract | 6400 | Develop Report and Recommendations | 6C | 180 | 540 total man-days, 3 people
6D1 |  | 6410 | What is working
6D2 |  | 6420 | What could improve
6D3 |  | 6430 | What is needed / gaps
6D4 |  | 6440 | ID counteracting efforts
6D5 |  | 6450 | Aging and maintenance
7 |  | 7000 | Recommend Additional Programs and Projects to Implement the CIWQ Plan
7 |  | 7000 | Recommend Additional Programs and Projects to Implement the CIWQ Plan | 2F3, 4A6; 5F; 6D
7A |  | 7100 | Best Management Practices
7B |  | 7200 | Monitoring
7C |  | 7300 | Modeling
7D |  | 7400 | Projects
7E |  | 7500 | Regulatory / Policy Modifications
7E1 |  | 7510 | Issues associated with implementing CERP
7F |  | 7600 | Guidelines/Recommendations
7G |  | 7700 | Identify Funding Sources
7G1 |  | 7710 | ID and review funding sources
7G2 |  | 7720 | Relate funding sources to recommended plan
7G3 |  | 7730 | Recommendation