## By Closed or Completed Items
BLUEPRINT FOR MANAGEMENT EXCELLENCE ACTION PLAN
Objectives | Actions | Action Owners (1) | Action Owners (2) | Action Owners (3) | Scheduled Dates | Comments | Documents Supporting Completion Provided | Change
Develop and maintain financial integrity and management and internal controls. | 5. Publish in one integrated document Government Performance and Results Act (GPRA) Strategic Plan results and financial reports to demonstrate to the public the relationship of financial and programmatic management. | ODS | ODS | OCFO | 2003-03-31 | Closed 7/8/02 - action item captured under Blueprint #144. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 9. Develop a project plan and commission a task force to gather Department-wide requirements for an Executive Information System capable of integrating program, financial, contracts and administrative data. Provide stakeholders with accurate and timely Financial Management Information using Oracle Financials and electronic dissemination techniques. | OCFO | OCIO |  | 2002-05-31 | Closed 4/30/02 - This action item has been combined with action item #122. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 10. Implement a plan to assure that discretionary and formula grant programs operate with the highest level of efficiency, effectiveness, and integrity. | EMT | Senior Officers |  | 6/30/2002 (One-ED Project) | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 228. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 11. Award 60 percent of new grants by May 31 each year. | OCFO | Senior Officers |  | 2002-06-30 | Closed 9/30/02 - action item goals were not met in FY 2002. This item will be monitored in FY 2003. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 14. Put a Financial Management Structure in place that is optimal for the Department’s needs and requirements. | EMT | FSA/OM |  | 9/30/2002 (One-ED Project) | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 227. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 21. Complete the examination of structures for effectively monitoring and holding accountable grantees, other intermediaries and contractors. | ODS | Senior Officers |  | 6/30/2002 (One-ED Project) | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 228. | ClosedNo
Improve the strategic management of the Department's human capital | 72. Determine employee skills needed by each PO’s management to most effectively perform program functions, with consideration given to attrition and retirement over the next five years. | EMT | OM | Senior Officers | 2002-06-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action items # 223 and #224. | ClosedNo
Improve the strategic management of the Department's human capital | 86. Implement a development program for senior managers. | OM |  |  | 2002-07-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 221 and #222. | ClosedNo
Improve the strategic management of the Department's human capital | 88. Initiate values-based ethics training for non-managers. | OGC | OM |  | 2003-01-01 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 217. | ClosedNo
Improve the strategic management of the Department's human capital | 118. Make it clear that managers are responsible for performance and conduct in their work units, including modeling a proper work ethic and appropriately addressing employee performance and conduct problems. | EMT | Senior Officers | OGC/OM | 2002-06-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 218. | ClosedNo
Improve the strategic management of the Department's human capital | 123. Training will be provided for managers on their responsibilities as managers, including values-based ethics training that addresses the specific ethics obligations of managers. All managers will receive this training. (through December 31, 2002) | OGC | OM |  | 2002-10-31 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 217. | ClosedNo
Improve the strategic management of the Department's human capital | 125. Improve the evaluation process to provide more meaningful appraisals and feedback to employees. | EMT | MIT | OM | 2002-09-30 | Closed 4/30/02 - This action was combined with #65, which will address changes in the evaluation process, development of training for managers, and an evaluation of the new EDPAS system. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 137. Identify and evaluate the advantages and disadvantages of centralizing the program monitoring function. | EMT | OM |  | 2002-06-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 228. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 138. Review and analyze administrative services provided by the Department to ensure responsiveness to customer needs, innovative approaches to problem solving, and best use of scarce resources. | EMT | MIT |  | 2002-06-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 220. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 139. After consultation with the community and members of Congress, resolve relationship issues between FSA and other Department offices. | ODS |  |  | 2002-06-30 | Closed 6/18/02 - this action item was modified under One-ED and is now being addressed under Blueprint action item # 225. | ClosedNo
Develop and maintain financial integrity and management and internal controls. | 23. Initiate a project to implement data-mining to detect possible fraud or abuse, set up a remedial program and increase efficiencies. Suspected fraud or abuse cases will be referred to the OIG. | OCFO | FSA |  | 2002-09-30 | Completed 9/25/02 - paper on file with MIT that describes data-mining efforts taken by FSA. | CompletedNo
Develop and maintain financial integrity and management and internal controls. | 26. For the period October 1, 2000-September 30, 2001 conduct testing using a representative sampling to ensure that all IT procurements are included in the inventory methodology. | OM | OCFO | OCIO/Senior Officers | 2002-02-04 | Completed 2/06/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 32. Meet regularly with GAO on status of and improvements to the student financial assistance programs’ high-risk status. | FSA |  |  | Quarterly | Completed 9/30/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 33. Work with OMB, Treasury, and OGC and OPE, to address the over- award of SFA funds to students. | ODS |  |  | 2001-11-15 | Completed 11/19/01 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 34. Identify areas for improving compliance effectiveness and take the appropriate steps toward improvement. | FSA |  |  | 2002-09-30 | Completed 9/30/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 37. Review baseline budget data and develop a framework for budget requirements using the single appropriation that has been agreed to by the Department and OMB. | Budget Service | FSA |  | 2002-09-30 | Completed 9/9/02 - included as part of FY 2004 budget submission to OMB. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 39. Continue the NSLDS data quality efforts and continue to demonstrate data quality improvement to support the FFEL program financial reporting. | FSA |  |  | Monthly | Completed 9/30/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 41. Implement improved Direct Loan (DL) servicing infrastructure to better support DL financial management reporting (FARS retirement). | FSA |  |  | 2002-07-31 | Completed 7/31/02 - FARS is retired. All resulting system updates will occur by 11/15/02. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 44. Improve reliability of lender billing data through a redesigned lender payment process. | FSA |  |  | 2002-10-31 | Completed 10/15/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 47. Complete items in the FSA Action Plan on time 95 percent of the time in FY 2002 and continuing in FY 2003. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - FSA Performance Plan Items, which incorporate the high priority High Risk Plan items, have been completed 95 percent of the time. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 48. Develop and Implement Phase IV of the Financial Management System, providing a reliable tool to improve the internal controls and financial management of the programs. | FSA |  |  | 2002-09-30 | Completed 10/15/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 50. Institute eligibility check for valid ISIR on file for all Direct Loan recipients (except PLUS). | FSA |  |  | 2002-09-30 | Completed 8/9/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 53. Demonstrate pursuit of improved default management and prevention strategies. | FSA |  |  | 2002-09-30 | Completed 10/15/02 - ED has made significant strides in the area of default management and prevention. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 55. Identify trends in risk areas and provide targeted technical assistance to schools. | FSA |  |  | 2002-09-30 | Completed 9/30/02 | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 56. Ensure the Department has strong documentation to demonstrate that it has addressed high-risk issues. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - Major High Risk initiatives are included in the FSA Performance Plan. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 57. Prepare action plans within 60 days of OIG issuance of final reports. Implement 95 percent of accepted OIG and GAO recommendations using action plans within the committed timeframes. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - FSA has demonstrated that they have established an effective process to ensure corrective action plans are developed and implemented on a timely basis. | CompletedNo
Modernize the Student Financial Assistance programs and reduce their high-risk status | 58. Strengthen FSA’s Internal Controls and Financial Integrity. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - FSA has taken numerous steps to improve their internal controls and financial integrity and has committed to updating the FY 2002 plan and monitoring it in FY 2003. | CompletedNo
Improve the strategic management of the Department's human capital | 80. Seek authority to provide managers with expanded personnel flexibilities. | OM | OM |  | 2002-03-31 | Completed 4/2002 - Bill Leidinger (OM Ass't Sec) met with OPM and OPM agreed (verbally) to provide authorities as needed. | CompletedNo
Manage information technology resources, using e-gov, to improve service for our customers and partners | 92. The Investment Review Board (IRB) will review, approve and prioritize 100 percent of the Department’s enterprise-wide significant information system investments. | OCIO | IRB |  | 2002-09-30 | Completed 7/16/02 | CompletedNo
Manage information technology resources, using e-gov, to improve service for our customers and partners | 106. Existing and new IT initiatives will have reasonable and reliable cost, schedule, and performance data in their business cases. | OCIO | Senior Officers |  | 2002-09-30 | Completed 7/16/02 | CompletedNo
Manage information technology resources, using e-gov, to improve service for our customers and partners | 107. Appropriately integrate IT investment management process with the budget process by the time the FY 2004 budget is submitted to OMB. | OCIO | FSA | Budget Service | 2002-09-30 | Completed 9/4/02 | CompletedNo
Manage information technology resources, using e-gov, to improve service for our customers and partners | 108. Fully integrate the IRB process with the budget and procurement processes. | OCIO | OCFO | Budget Service | 2002-09-30 | Completed 9/4/02 | CompletedNo
Improve the strategic management of the Department's human capital | 113. Every senior officer will reach agreement with the secretary on the program and management results they are responsible for in FY 2002 and the following two years. These agreements will link to the strategic plan, be updated annually, and be used to determine bonuses and other awards in the Principal Offices (PO). Senior leadership will begin to use the agreements in FY 2002 and will use them increasingly as the Department develops practical measures that link individual and organizational performance to the achievement of results. | ODS | PES | OS | 2002-07-31 | Completed 8/22/02 - Mike Petrilli has a copy of the performance agreements. | CompletedNo
Develop and maintain financial integrity and management and internal controls. | 134. Begin meeting with senior officers to encourage new information sharing mechanisms. | MIT | OM | Senior Officers | 2002-03-31 | Completed 4/18/02. Date changed from 12/31/01. | CompletedNo
Develop and maintain financial integrity and management and internal controls. | 8. Submit the audited FY 2001 financial statements for the Department to OMB. | OCFO |  |  | 2002-02-27 | Completed 2/27/02 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 15. Increase the number of performance-based contract actions to equal 20 percent of actions and 48 percent of all dollars awarded. | OCFO |  |  | 2002-09-30 | Completed 9/30/02 - performance goals met; specific numbers on file with the MIT. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 20. Reengineer the official process of developing directives, securing program feedback and issuing and disseminating administrative directives. Prepare a project plan for implementation. | OM | MIT |  | 2001-12-31 | Completed 11/19/01 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 24. Annually review internal controls consistent with the Federal Managers Financial Integrity Act (FMFIA) process. | OCFO |  |  | 2002-06-30 | Completed 2/27/02 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 25. Contract for and support an independent assessment of all physical, safety and security threats and vulnerabilities that may affect Department staff and facilities. | OM | OCIO |  | 2002-07-31 | Completed 7/30/02 - completed assessments are on file with the Office of Management Security Services. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 27. Reconcile the inventory database to determine with reasonable assurance that identified IT purchases have been inventoried according to Department policy. | OM | OCFO | OCIO/Senior Officers | 2002-09-30 | Completed 10/9/02 - IT purchases for the period 4/1/01 - 12/31/02 have been reconciled with inventory database. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 28. Prepare action plans that, in accordance with the Strategic Plan Framework, emphasize results and performance. | Senior Officers | PES |  | 2002-03-31 | Completed 3/29/02 | CompletedYes
Improve the strategic management of the Department's human capital | 29. Present to the EMT an analysis of the pros and cons of establishing a high-level security office with the responsibility for coordinating all Department security programs and activities. | OM | OCIO | OIG | 2002-01-25 | Completed 2/08/02 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 30. Assist PO staff in developing and implementing corrective action plans to address internal control weaknesses identified by the Department's auditors. (ongoing) | OCFO |  |  | 2002-04-29 | Completed 4/23/02 - process in place to ensure effective corrective actions are developed timely. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 31. Based on an independent security assessment, prepare a comprehensive physical security plan for the Department. | OM |  |  | 2002-08-31 | Completed 8/30/02 - plan is on file with the MIT. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 35. Provide continued support to channels for design and development of modernization projects by achieving 90 percent of the annual major modernization milestones that have been approved by the Information Technology Investment Review Board. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - achieved 92& of the annual major modernization milestones. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 36. Update the SFA High-Risk Action Plan for FY 2002. | FSA | OPE |  | 2001-10-31 | Completed | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 38. Develop FY2002 plan to strengthen FSA internal controls and financial integrity. | FSA |  |  | 2001-11-30 | Completed 11/30/01 | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 40. Use student demographic information to identify institutions that may be abusing the SFA programs. Refer suspected cases of fraud or abuse to the OIG. | FSA | OIG |  | 2001-12-31 | Completed 12/31/01 | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 42. Ensure a Departmental team is established as a forum for working with external parties (including GAO, CBO, OMB, Congress and the education community) and for working through outstanding issues surrounding risk in student aid. | ODS | FSA | EMT | 2002-04-30 | Completed 4/30/02. Date changed from 3/31/02. OPE named Dan Pollard as their point person. Initial meeting held 4/30/02. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 43. Implement a common business process and system for aid origination and disbursement of Pell Grants and Direct Loans to provide the infrastructure to improve school reporting, cash management and internal control processes. | FSA |  |  | 2002-09-15 | Completed 9/30/02 - accounting issues have been addressed. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 45. Implement Phase II of the Financial Partners Data Mart. This phase will provide self-monitoring and oversight tools and focus on the data load, and link with the new FMS to provide a continuous stream of financial data and selected NSLDS elements necessary to augment data comparisons and lender risk management assessment. | FSA |  |  | 2002-06-01 | Completed 6/19/02 - migrated into full production 6/19/02. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 52. Identify areas for regulatory and legislative changes in the Title IV programs (including improvements to strengthen program integrity). | FSA | OPE | OGC | 2002-09-30 | Completed 10/9/02 - FSA will ensure that the FY 2002 Annual Plan contains information as required by legislation. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 54. Expand the use of the National Directory of New Hires database matching program to recover $200 million in defaulted student loans. | FSA |  |  | 2002-09-30 | Completed 6/26/02 - NDNH collection totals have exceeded the $200 million goal for FY 2002. As of the end of May 2002, collections exceeded $233 million. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 59. Consistent with the Department’s strategic plan, utilize established trade association work groups to emphasize data integrity through consistent standards, and develop improved data reporting to FSA systems. | FSA |  |  | 2002-09-30 | Completed 9/30/02 - this action item is part of FSA's daily operations; a list of trade associations with which FSA worked in FY 2002 are on file with the MIT. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 60. Develop a design for providing consistent data across FSA from modernized systems to deliver consistent answers to customers and provide consistent information for employees for program oversight. | FSA |  |  | 2002-09-30 | Completed 7/3/02 | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 61. Expand the FSA enterprise-wide solution for electronic signatures (PIN, Digital Signature, Smart Cards, etc.) to several other business applications. | FSA | OCIO |  | 2002-09-30 | Completed 7/31/02 - electronic signatures expanded to Perkins enotes and notification of cohort default rates. | CompletedYes
Improve the strategic management of the Department's human capital | 63. Develop an overarching vision of human capital that ties to the strategic plan and the Department’s mission. | EMT |  |  | 6/30/2002 (One-ED Project) | Completed 6/18/02 - this action item was addressed in the One-ED report. | CompletedYes
Improve the strategic management of the Department's human capital | 64. Develop a workforce plan framework as a first step in completing the long-term workforce plan. | EMT | OM | Budget Service | 2002-02-22 | Completed 3/6/02 | CompletedYes
Improve the strategic management of the Department's human capital | 65. Perform a five-year workforce planning and restructuring analysis and include it as part of the FY 2003 Budget submission and annual performance plan. The EMT will identify the specific organizational changes proposed. The allocation of resources and the organization structure must support the strategic plan. | Budget Service | OM |  | 2002-08-31 | Completed 8/22/02 - The One-ED budget is being submitted to OMB as a separate "project." | CompletedYes
Improve the strategic management of the Department's human capital | 66. Determine the specific actions needed to implement the workforce and restructuring plan, including a timetable for each action. | OM | Senior Officers | EMT | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. EMT revised scheduled date from1/31/02. Date changed from 02/10/02. | CompletedYes
Improve the strategic management of the Department's human capital | 67. Publicize and expand the use of strategically targeted recruitment and retention bonuses. | OM |  |  | 2001-10-31 | Completed 12/20/01 | CompletedYes
Improve the strategic management of the Department's human capital | 68. Provide information to OMB indicating how the Department will meet the 5 percent (FY 2002) and 10 percent (FY 2003) competition goals required by the President’s Management Agenda. | EMT |  |  | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. Date changed from 11/15/01. To be closed-out through One-ED report. | CompletedYes
Improve the strategic management of the Department's human capital | 69. Complete the development of “EDHires,” an automated recruitment system. | OM |  |  | 2001-11-30 | Completed 12/7/01 | CompletedYes
Improve the strategic management of the Department's human capital | 70. Detail estimated costs and/or savings from the first through fifth year of implementing the changes in the organization structure. | EMT | Budget Service | OM | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. | CompletedYes
Improve the strategic management of the Department's human capital | 71. Estimate the impact of the workforce restructuring on the Department’s plan for improving program performance outcomes. | EMT | Senior Officers | PES | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. | CompletedYes
Improve the strategic management of the Department's human capital | 73. Encourage employees to use tuition reimbursement to pursue work-related off-site college courses. | OM | Senior Officers |  | 2001-12-31 | Completed 12/11/01. Additional marketing efforts are ongoing. | CompletedYes
Improve the strategic management of the Department's human capital | 74. Encourage and more effectively publicize the leadership coaching and mentoring programs. | OM |  |  | 2001-12-31 | Completed 1/7/02. Additional marketing efforts are ongoing. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 75. Develop a plan for ensuring that contracting officials, contracting officer representatives (CORs) and others responsible for monitoring contracts receive proper training and certification. | OCFO | CORs |  | 2001-12-31 | Completed | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 76. Develop training curricula and a program to train executives on their IT investment management responsibilities. New leadership will receive IT investment management training within two months of arrival. | EMT | OCIO |  | 2002-07-31 | Completed 7/16/02 - Training provided in 7/16/02 IRB meeting. | CompletedYes
Improve the strategic management of the Department's human capital | 78. Develop and employ recruitment materials focusing on the benefits of working for the Department of Education. | OM |  |  | 2002-01-31 | Completed 12/17/01 | CompletedYes
Improve the strategic management of the Department's human capital | 79. Initiate competitive sourcing of appropriate tasks performed by employees, consistent with the FAIR Act. | EMT | Senior Officers | OCFO | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. Date changed from 03/31/02. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 81. Develop and administer internal control training initiatives for presentation at all levels within the Department. | OCFO | OM |  | 2002-04-30 | Completed 4/30/02. Date changed from 3/31/02. Completion rate was 85%. The non-completers have been referred to Assistant Secretaries for action. | CompletedYes
Improve the strategic management of the Department's human capital | 82. Create a national recruitment network with key university programs, especially graduate programs in public affairs, public administration, financial management and information technology. | OM | Senior Officers |  | 2002-07-31 | Completed 7/30/02 | CompletedYes
Improve the strategic management of the Department's human capital | 83. Initiate revised ethics training for non-managers, incorporating financial management issues, and being consistent with ethics assessment results. | OGC | OM |  | 2002-04-30 | Completed 4/29/02 | CompletedYes
Improve the strategic management of the Department's human capital | 84. Expand innovative strategies to recruit employees, including notification in trade publications and state agencies. | OM | Senior Officers |  | 2002-07-31 | Completed 7/30/02 | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 91. After close consultation with state and local education agencies, the Department will establish and publish agreed-upon data dictionary elements for recommended use by federal, state and local education agencies. | ODS | OCIO |  | 2002-09-30 | Completed 9/27/02 - ED's data dictionary is published at www.educationadvisor.info. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 97. Produce standards and guidelines for agreed-upon national education data requirements. | ODS | OCIO |  | 2002-09-30 | Completed 9/27/02 - guidelines posted on web at www.ed.gov/offices/OCIO/info_quality and posted in 10/1/02 federal register. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 99. Draft and submit to OMB a comprehensive IT Security Corrective Action Plan reflecting all relevant OIG audit findings, GAO reviews, A-130 security reviews, Critical Infrastructure Protection vulnerability assessments, and Government Information Security Reform Act (GISRA) reviews. | OCIO | Senior Officers |  | 2001-10-31 | Completed 2/1/02. Report available for review. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 100. Complete the Department’s Critical Infrastructure Protection Plan, Phase 2, Vulnerability and Threat Assessment; and begin Phase 3, Remedial Action Plans, which are expected to be completed by spring 2002. | OCIO | Senior Officers |  | 2002-09-30 | Completed 9/27/02 - IT and Physical assesstments completed and are on file with the MIT. Phase 3 is being addressed through the GISRA remedial action plans for IT and through the physical assesstment. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 101. Conduct a Department-wide IT security awareness campaign, including mandatory completion by all employees of a new computer-based security awareness training program, and a Computer Security Day in November 2001. | OCIO |  |  | 2002-04-15 | Completed 4/15/02. Date changed from 2/28/02. Completion rate was 93%. Remaining 7% referred to Asst Sec for action. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 102. Make known the approximate amount of funding available for significant IT initiatives at the beginning of the IT investment management process. | OCIO | FSA | Budget Service | Ongoing | Completed 4/21/02. Date changed from 3/31/02. Consistent with Budget Service guidance, OCIO provided POs with estimates of PO-level FY 04 budget amounts available for purposes of the Spring 02 IT Investment Management Select Phase. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 103. The contracting officer, project sponsor, and project manager will approve the business cases for significant IT initiatives before consideration by the IRB. | OCIO | OCFO | POs | 2002-06-30 | Completed 6/10/02. Relates to 104 and 105. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 104. Contracting Officers will ensure 100 percent of significant IT procurements, (e.g., hardware, software, and services) are tied to an approved business case before processing. | OCIO | OCFO | POs | 2002-09-30 | Completed 9/30/02 - policies and procedures governing IT procurements were disseminated to program managers with IT investments and Procurement Officials and will be incorporated into the OCFO Contract Operations Procedures website. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 105. Appropriate integration of the IT investment management process with the acquisition process. | OCIO | OCFO | POs | 2002-09-30 | Completed 9/30/02 - policies and procedures governing IT procurements were disseminated to program managers with IT investments and Procurement Officials and will be incorporated into the OCFO Contract Operations Procedures website. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 109. Track significant IT initiatives against cost, schedule, and performance goals with the target that variances will be below 10 percent. | OCIO | Senior Officers |  | 2002-12-31 | Completed 10/3/02 - process in place to ensure data is being monitored on an on-going basis. Guide and policy documents on file with the MIT. | CompletedYes
Manage information technology resources, using e-gov, to improve service for our customers and partners | 110. Establish a core of project management professionals with the necessary training and skills to manage the Department’s IT initiatives. | OM | OCIO | Senior Officers | 2002-12-31 | Completed 9/27/02 - OM has developed and institutionalized a training program for project management. | CompletedYes
Improve the strategic management of the Department's human capital | 114. Each senior officer will have performance agreements with the managers (SES) reporting to them that are consistent with the Department’s strategic plan. These agreements will link to the strategic plan, be updated annually, and be used to determine bonuses and other awards. | Senior Officers | OM | PES | 2002-03-31 | Completed 3/1/02 | CompletedYes
Improve the strategic management of the Department's human capital | 115. The Department's employee performance agreements and bonuses/awards will link to the Department's Strategic Plan, Blueprint for Management Improvement, and Culture of Accountability Team Report. | OM | PES | Senior Officers | 2002-06-30 | Completed 6/18/02 - this item was addressed through One-ED Report. Date changed from 3/31/02. | CompletedYes
Improve the strategic management of the Department's human capital | 116. Establish a mandatory process for managers to consult with OM on disciplinary issues to ensure consistent and appropriate discipline. | OM | OGC |  | 2001-11-30 | Completed 12/17/2001 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 117. Publish new 5-year Department of Education Strategic Plan (FY 02-07). | ODS | PES | OS | 2002-02-28 | Completed 3/12/02 | CompletedYes
Improve the strategic management of the Department's human capital | 119. Finalize SES model performance agreements approved by OPM with results and accountability focus for use by the assistant secretaries and other senior managers. | OM |  |  | 2001-12-31 | Completed 2/26/02 | CompletedYes
Improve the strategic management of the Department's human capital | 120. Implement a five-tier performance appraisal system. | OM |  |  | 2002-08-31 | Completed 8/29/02 - implementation plan is on file with the MIT. | CompletedYes
Improve the strategic management of the Department's human capital | 121. Develop and disseminate a Department-wide core values statement. | EMT |  |  | 2002-06-30 | Completed 6/18/02 - this item was addressed through the One-ED report. Date changed from 1/31/01. Date changed from 5/31/02. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 122. Implement a “dashboard”-like monthly reporting system that the Secretary and the deputy secretary can use to track progress on each major Departmental performance goal. | EMT | ODS | OCIO | 2002-09-30 | Completed 10/3/02 - MS Project Server used to link existing tracking databases and a reporting tool will be used to generate consolidated reports. | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 127. Establish the Executive Management Team (EMT). | ODS |  |  | 2001-10-31 | Completed 11/07/01 | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 128. Continue the Management Improvement Team (MIT), composed of senior career staff representing key principal offices that will work as staff to the EMT. The MIT will prepare the EMT for decisions and actions needed to address issues that arise out of the performance tracking system for the strategic plan. The MIT will implement and update the Blueprint, as necessary. The MIT will track progress in meeting the secretary's management improvement goals. It will monitor adherence to project plans for the Blueprint actions. | ODS |  |  | 2001-10-31 | Completed | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 129. Establish MIT-like teams for each Blueprint goal facilitated by an MIT member who meets regularly with the deputy secretary, senior officers and steering committee to report on accomplishments and problems requiring high-level attention. | ODS | EMT | MIT | 2001-10-31 | Completed | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 132. Assign Council for Excellence in Government fellows to MIT initiatives. | MIT |  |  | 2001-10-31 | Completed | CompletedYes
Develop and maintain financial integrity and management and internal controls. | 133. Modify the current “dashboard” report to track progress implementing the Blueprint. | MIT | Senior Officers |  | 2001-12-31 | Completed 11/20/01 | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 135. Review the existing FSA/ED MOUs to determine what is and is not working as intended. Execute responsibilities as outlined in the MOUs, or change the agreements. | ODS | OGC | MIT | 2002-06-30 | Completed 6/18/02 - The strategic investment process outlined in the One-ED report will address the FSA/ED MOUs during Phase I. | CompletedYes
Modernize the Student Financial Assistance programs and reduce their high-risk status | 136. Review FSA’s current strategy for monitoring schools, lenders, guaranty agencies and third-party servicers; identify the various levels and types of monitoring, including where performed and by whom; and develop an improvement plan. Determine which kinds of monitoring are linked to the basic administration of the student financial aid programs. | EMT | MIT | FSA | 2002-06-30 | Completed 6/28/02 - FSA provided a report that addresses monitoring for schools (not lenders and guaranty agencies). This report will help inform the Strategic Investment Process conducted under One-ED. | CompletedYes