## Instructions
Washington Works Readiness Criteria
Instructions for Using the Readiness Criteria
Purpose: | The Washington Works Readiness Criteria is a reference tool to support the Agency Readiness Survey and the Agency Deployment Work Plan. The criteria are organized into the four key components of the HRMS Project: Leadership, People, Process, and Technology. The criteria will help the Change Agent and Deployment Work Team (1) prepare their work plan; (2) understand the metrics used to measure their readiness; and (3) complete the monthly readiness surveys. Throughout the life of the project there will be times when the readiness criteria will not link to the AgencyReadiness Survey or the Agency Deployment Work Plan. This is due to the monthly time frame of the survey, or because the preliminary steps on the work plan have already passed.
What You Need to Do: | Review the criteria with your Agency Director and/or Deputy Director and discuss how they link to your Agency Deployment Work Plan and Agency Readiness Survey.
Discuss the criteria with your designated Deployment Work Team. Ensure each person on your team understands the criteria which apply to their part of the project.
Refer to the criteria and planned completion dates as you build your Agency Deployment Work Plan.
Refer to the criteria as you prepare the Agency Readiness Survey, due no later than the 20th of each month.
When it's Due: | There is no due date for the readiness criteria. It is a planning and reference tool for your on-going use.
Tips for Using: | Distribute a copy of the criteria to all members of the Deployment Work Team. Before building the initial Agency Deployment Work Plan have the full team talk through the criteria and the linkages between the four components. Then, complete the initial plan for your agency, checking your internal due dates against the dates in the Agency Deployment Work Plan template. Continue to refer to the criteria as the team finalizes the plan through March. Additional criteria may be added as the full plan is provided prior to the Change Agent meeting on December 17th. Continue to refer to the criteria as you complete the monthly Readiness Surveys.
Field Definitions
Readiness Criteria | The activity that needs to be completed to prepare the agency for readiness.
WW Project | The component of the project that the criteria references.
Metric | The measure that is used to detemine whether the task is complete and/or the percentage of completion.
Information Source | The source where the information was obtained, such as a report, a survey, the training database, etc.
Target | The quantitative goal for the criteria.
Planned Completion | The date the activity is to be completed. This date is set by the HRMS Project Team to comply with project deadlines and milestones.

## Criteria
| Readiness Criteria | WW Project | Metric | Information Source | Target | Planned Completion Date
1.0 Leadership
1.1 | Agency has a designated team devoted to WW deployment, covering changes required in --Leadership --Process --People --Technology | ALL | 1. Change Agent Identified (yes/ no) 2. Agency Deployment Team Identified (yes/ no) | Change Agent, Deputy Directors | 1. Yes 2. Yes | 12/01/03 01/15/04
1.2 | Director and Deputy Directors have been briefed on WW timelines and the HRMS release approach | ALL | 1. Director and/ or Deputy Director attended one or more operations committee, small agency committees, etc. 2. Director and Deputy Director understand the WW timelines and HRMS Release Approach | Director and/ or Director Director | 1. Yes 2. Yes | 12/15/03 12/15/03
1.3 | Agency Change Agent has attended initial Change Agent Meeting and/ or Deployment Workshops | ALL | 1. Change Agent has attended initial Change Agent Meeting and/ or Deployment Workshop 2. Change Agent has an understanding and has agreed to carrying out the responsibilities of the Change Agent | Change Agent | 1. Yes 2. Yes | 12/15/03 12/15/03
1.4 | Agency has developed preliminary workplan to drive agency deployment efforts | ALL | 1. Completion of Agency Deployment Workplan 2. # of Days to complete Deployment Activities | Agency Deployment Work Plan | 1. Yes 2. >0 | 2004-01-15
1.5 | Agency has identified the resources required to implement WW initiatives from the activities identified on the work plan | ALL | 1. # of FTEs required | Agency Deployment Work Plan | 1. > 0 | 2004-01-15
1.6 | Agency has developed internal communication approach to push WW information to agency staff | ALL | 1. Communication Plan in Place (yes/ no) | Agency Communication Plan | 1. Yes | 2004-02-13
1.7 | Agency has committed to use the new HRMS | HRMS | 1. Strategy for Shadow System Retirement in-place? | Agency Impact Assessment | 1. Yes | 2004-02-27
1.8 | Agency understands and has agreed to be ready for their Release 1 deployment group | HRMS | 1. Agency has committed to the deployment group that has been assigned? 2. Deputy has assessed the work to be completed and signed off that it will be completed before their Go Live | Director and/ or Deputy Director | 1. Yes 2. Yes | 02/27/04 02/27/04
1.9 | Agency is monitoring agency's Deployment Work Plan | ALL | 1. Update Agency Deployment Work Plan on Monthly basis | Change Agent | 1. Yes | Ongoing
1.1 | Agency Change Agent has attended monthly CA Meetings and Deployment Workshops | ALL | 1. Change Agent has attended monthly Change Agent and Deployment Meetings | Change Agent | 1. Yes | Ongoing
1.11 | Agency Change Agent has communicated Key WW project initiatives information to appropriate people in their Agency | ALL | 1. Change Agent is communicating key WW initiatives as appropriate | Change Agent | 1. Yes | Ongoing
1.12 | Deputy Director and/or Director has attended monthly WW management meetings (Operations Committee, Small Agency Initiative, etc) | ALL | 1. Deputy Director or Director has attended monthly meetings | Director and/or Deputy Director | 1. Yes | Ongoing
2.0 Process
2.1 | Agency has inventoried policies, business practices and procedures and has identified which policies, processes and procedures will be affected by HRMS, CSR, CC or CB. | ALL | 1. # of business processes 2. # of business processes affected by WW initiatives | Business Process Inventory | 1. > 0 2. > 0 | 12/31/03 12/31/03
2.2 | Agency has identified unique HR legislative/federal requirements for HRMS | HRMS | 1. # of unique HR legislative/federal requirements | Agency Unique Legislative Requirements | 1. > 0 | 2003-12-31
2.3 | Agency has inventoried internal agency forms which will be affected by CSR, CC or CB | ALL | # of forms affected by WW initiatives | Change Agents, Inventory of Internal Agency Forms |  | 2004-01-15
2.4 | Agency has reviewed functional requirements for Release 1 | HRMS | 1. Attended Business Process End-to-End Meeting in January | Change Agent | 1. Yes | 2004-01-30
2.5 | Agency has reviewed future business processes (TO BE) to determine the impact of these processes on agency operations and current procedures | ALL | 1. Attended Business Process End-to-End Meeting in January 2. Determined impact of process on agency operations | Agency Impact Assessment | 1. Yes 2. Yes | 02/13/04 02/13/04
2.6 | Agency has identified System Configuration Requirements (e.g. agency work schedules, etc.) | HRMS | 1. Completed System Configuration Requirements Questionnaire | Agency Impact Assessment | 1. Yes | 2004-02-27
2.7 | Agency has developed an approach for revising agency policies | ALL | 1. TBD | Agency Impact Assessment | TBD | 2004-02-27
2.8 | Agency has updated internal operating procedures to support new business processes and rules | ALL | 1. # of operating procedures updated | Change Agent | TBD | TBD
2.9 | Agency has reviewed business warehouse functionality to determine the impact to their management reporting needs | HRMS | 1. TBD | Agency Deployment Work Plan | TBD | TBD
2.10 | Agency has reviewed their organizational structure and developed an approach to deal with allocations to the new classification/compensation structure | CSR | 1. TBD | Change Agent | TBD | 2004-02-27
2.11 | Agency has developed their Organizational Structures (organization units, jobs, and positions) | ALL | 1. TBD | TBD | TBD | TBD
2.12 | New operating procedures are rolled out to staff | ALL | 1. TBD | Change Agent | TBD | TBD
2.13 | Agency has adequate experience, supporting systems and/or skilled staff to accomplish full cost analysis | ALL | 1. # of programs in organization assessed with standard full cost analysis (utilizing Costing Government Services Guide model) | Change Agent | TBD | TBD
2.14 | Agency has created required agency forms or edited existing forms to comply with new policies and procedures | ALL | 1. # of forms created or updated | Change Agent | TBD | TBD
2.15 | Agency has conducted initial impact analysis of proposed CSR and CC rules on operations/ procedures | CSR & CC | 1. Complete assessment | CSR & CC Impact Analysis |  | 2003-12-31
3. People
3.1 | Agency has identified end users of the HRMS system | HRMS | 1. # of end users | End User Inventory | 1. > 0 | 2003-12-31
3.2 | Agency has developed a strategy for implementing the new performance management plan | CSR | 1. TBD | Agency Deployment Work Plan | TBD | 2004-01-30
3.3 | Agency has identified who in their organization is affected by WW initiatives (CSR, CB, and CC) | CSR, CB & CC | 1. # of staff affected | Change Agent | 1. > 0 | 2004-02-13
3.4 | Agency has identified the training team for CSR train the trainer | CSR | 1. Training Team Identified (yes/ no) | Change Agent | 1. Yes | TBD
3.5 | Agency has identified the training person(s) to identify and register HRMS end users for training | HRMS | 1. Training Person(s) Identified (yes/ no) | Change Agent | 1. Yes | TBD
3.6 | Agency has identified end users for the Business Warehouse application | HRMS | 1. # of business warehouse end users | Change Agent | 1. > 0 | 2003-12-31
3.7 | Agency has mapped HRMS end users to HRMS Roles | HRMS | 1. # of end users mapped to HRMS Roles | Change Agent | 1. > 0 | 2004-09-01
3.8 | Agency has reviewed the proposed HRMS training schedule | HRMS | 1. TBD | Change Agent | 1. Yes | 2004-09-01
3.9 | Agency has communicated roles and HRMS Training schedule to end users | HRMS | 1. No. of Training hours needed for HRMS end users | Change Agent | 1. > 0 | 2004-09-15
3.1 | Agency has registered all end users in the required training courses | HRMS | 1. No. of end Users registered for their required training | Change Agent | 1. > 0 | 2004-10-15
3.11 | Agency has rolled out new organizational structures and assignments to agency employees | CSR | 1. TBD | TBD | TBD | TBD
3.12 | Agency business warehouse users have been trained on the business warehouse application | HRMS | 1. # of business warehouse end users trained | Change Agent | 1. > 0 | TBD
3.13 | Agency end users have completed all required HRMS training courses | HRMS | 1. TBD | TBD | TBD | TBD
3.14 | Agency users have completed CSR training program | CSR | 1. TBD | TBD | TBD | TBD
4.0 Technology
4.1 | Agency Applications (shadow systems) have been identified | HRMS | 1. # of shadow systems | Agency Application Inventory | 1. > 0 | 2003-12-31
4.2 | Agency has identified interfaces | HRMS | 1. # of interfaces | Agency Interface Inventory | 1. > 0 | 2003-12-31
4.3 | Agency Applications (shadow systems) have been analyzed for impact of the new HRMS | HRMS | 1. # of shadow systems that will be impacted by HRMS 2. # of shadow systems that will be retired due to HRMS | Agency Application Inventory | 1. > 0 2. > 0 | 2004-01-30
4.4 | Agency has analyzed impact of HRMS on existing interfaces | HRMS | 1. # of inbound interfaces to SAP HR/Payroll 2. # of outbound interfaces from SAP HR/Payroll 3. List of Reporting Requirements from existing systems and/or DOP Centralized HR/Payroll System | Agency Interface Inventory | 1. > 0 2. >0 3. Yes | 2004-02-13
4.5 | Agency has agreed on the method to access HRMS | HRMS | 1. TBD | Agency IT Organization | TBD | 2004-03-31
4.6 | Agency has conducted a site survey of existing infrastructure against HRMS technical standards | HRMS | 1. TBD | Agency IT Organization | TBD | 2004-02-13
4.7 | Agency has conducted a data purification needs assessment | HRMS | 1. TBD | Agency Deployment Work Plan | TBD | TBD
4.8 | Agency infrastructure necessary to support HRMS has been implemented and tested | HRMS | 1. TBD | Agency IT Organization | TBD | 2004-11-01
4.9 | Agency has conducted a baseline performance test to the HRMS servers to measure their own network capacity | HRMS | 1. TBD | Agency IT Organization | TBD | TBD
4.1 | Agency interfaces to/from HRMS have been modified and tested | HRMS | 1. TBD | Agency IT Organization | TBD | 2004-11-30
4.11 | Affected system modifications have been completed and tested | HRMS | 1. TBD | Agency IT Organization | TBD | TBD
4.12 | Agency has completed data purification efforts | HRMS | 1. TBD | Agency Deployment Work Plan | TBD | TBD
4.13 | Agency has received confirmation from HRMS that its data meets HRMS data standards | HRMS | 1. TBD | TBD | TBD | TBD
4.14 | Security profiles and authorizations have been tested and signed off | HRMS | 1. TBD | TBD | TBD | TBD
4.15 | The agency has transitioned off of any Agency Applications (shadow systems) planned for retirement | HRMS | 1. TBD | Agency IT Organization | TBD | TBD