## Outline plan
146 Transport of food to famine relief camps - Outline plan
Date |  | J Smith | I Khan | P Jones (CAE) | F Higson
2003-12-15 | Monday | Briefing from CAE |  |  |  | Key:
2003-12-16 | Tuesday | Set up files/scope |  |  |  |  | Audit 146
2003-12-17 | Wednesday | Issue draft scope |  |  |  |  | Other audits
2003-12-18 | Thursday | Testing | Testing |  |  |  | Out of office
2003-12-19 | Friday | audit 142 | audit 144 |  |  |  | Holidays
2003-12-20 | Saturday | [5 empty] | Weekend
2003-12-21 | Sunday
2003-12-22 | Monday
2003-12-23 | Tuesday | Christmas holidays
2003-12-24 | Wednesday
2003-12-25 | Thursday
2003-12-26 | Friday
2003-12-27 | Saturday
2003-12-28 | Sunday
2003-12-29 | Monday | Testing | Testing
2003-12-30 | Tuesday | audit 142 | audit 144
2003-12-31 | Wednesday
2004-01-01 | Thursday | New year's day
2004-01-02 | Friday
2004-01-03 | Saturday
2004-01-04 | Sunday
2004-01-05 | Monday |  |  | Holiday
2004-01-06 | Tuesday | Scope meeting |  | Holiday | meeting
2004-01-07 | Wednesday | Amend scope |  | Holiday
2004-01-08 | Thursday | Testing | Testing | Holiday
2004-01-09 | Friday | audit 142 | audit 144 | Holiday
2004-01-10 | Saturday
2004-01-11 | Sunday
2004-01-12 | Monday | CAE approves scope
2004-01-13 | Tuesday | Issue final scope
2004-01-14 | Wednesday | Complete | Complete | Out of office
2004-01-15 | Thursday | audit 142 | audit 144 | Out of office
2004-01-16 | Friday
2004-01-17 | Saturday
2004-01-18 | Sunday
2004-01-19 | Monday | Holiday | Course
2004-01-20 | Tuesday | Holiday | Course
2004-01-21 | Wednesday | Holiday | Course
2004-01-22 | Thursday | Holiday | Course
2004-01-23 | Friday | Holiday | Course
2004-01-24 | Saturday
2004-01-25 | Sunday
2004-01-26 | Monday | Complete | Complete
2004-01-27 | Tuesday | audit 142 | audit 144
2004-01-28 | Wednesday | Prepare for overseas
2004-01-29 | Thursday | visit
2004-01-30 | Friday
2004-01-31 | Saturday | Fly to Kinshasa
2004-02-01 | Sunday
2004-02-02 | Monday | Audit 146
2004-02-03 | Tuesday
2004-02-04 | Wednesday
2004-02-05 | Thursday | Audit of Kinshasa office
2004-02-06 | Friday
2004-02-07 | Saturday
2004-02-08 | Sunday
2004-02-09 | Monday
2004-02-10 | Tuesday
2004-02-11 | Wednesday | Discuss draft report
2004-02-12 | Thursday | Fly back to UK
2004-02-13 | Friday
2004-02-14 | Saturday
2004-02-15 | Sunday
2004-02-16 | Monday | Write draft reports
2004-02-17 | Tuesday | Write draft reports
2004-02-18 | Wednesday | Write draft reports
2004-02-19 | Thursday | Write draft reports
2004-02-20 | Friday | Issue draft report
2004-02-21 | Saturday
2004-02-22 | Sunday
2004-02-23 | Monday
2004-02-24 | Tuesday
2004-02-25 | Wednesday
2004-02-26 | Thursday
2004-02-27 | Friday
2004-02-28 | Saturday
2004-02-29 | Sunday
2004-03-01 | Monday |  |  | Out of office
2004-03-02 | Tuesday |  |  | Out of office
2004-03-03 | Wednesday | Receive comments |  | Out of office
2004-03-04 | Thursday | Write final report
2004-03-05 | Friday | Final report sign approval
2004-03-06 | Saturday
2004-03-07 | Sunday
2004-03-08 | Monday | Issue final report
2004-03-09 | Tuesday
2004-03-10 | Wednesday
2004-03-11 | Thursday
2004-03-12 | Friday

## 146 Audit database
146 Transport of food to famine relief camps - Audit Database
Level 2 process |  | Risk on register | Level 3 process |  | Risk for this audit | Inherent risks |  |  | Control | Tests | Ref | Residual risks |  |  | Issue | Action | By whom | Conclusion | Conclusion | Conclusion | Conclusion | Report
|  | (appendix H) |  |  |  | Cons. | Like. | Sig. |  |  |  | Cons. | Like. | Sig. |  |  |  | Risks | Controls | Action | Monitoring | Reference
| Identify risks | Risks are not known |  |  | Risks are not known | 3 | 3 | 9 |  | Examine processes to set up the risk register and examine the register |  | 3 | 3 | 9 | No register | A risk assessment will be carried out as part of the contracting process (see below) | Logistics Director |  | n/a |  |  | 2
| Evaluate risks | Significant risks are not understood |  |  | Significant risks are not understood | 3 | 3 | 9 |  | Examine the process to score the risks |  | 3 | 3 | 9 |  | As above | As above |  | n/a |  |  | 2
| Manage risks | Significant risks are not controlled |  |  | Significant risks are not controlled | 3 | 3 | 9 |  | Check controls - below |  | 3 | 3 | 9 |  | As above | As above |  | n/a |  |  | 2
4.2 | Arrange land transport |  | 4.2.1 | Receive instructions from country office | Instructions not received | 3 | 3 | 9 | Country office confirms receipt. HQ chases if no confirmation received | Checked all instructions and confirmations for 2003. All satisfactory | n/a | 3 | 1 | 3 | None | n/a | n/a | n/a |  |  |  | n/a
4.2 | Arrange land transport |  | 4.2.1 | Receive instructions from country office | Instructions are late | 3 | 3 | 9 | No controls at HQ to ensure instructions are sent on time | n/a | n/a | 3 | 1 | 3 | No controls at HQ to ensure instructions are sent on time | Country Director to assume responsibility for notifying the country office | Country Director | n/a |  |  |  | 4
4.4 | Recruit drivers | Drivers not available | 4.2.2 | Hire drivers | Drivers not available | 3 | 3 | 9 | List of drivers available for hire is kept by the compound office | Checked list. It is not regularly updated | G3 | 3 | 3 | 9 | Drivers may not be available | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.2 | Arrange land transport |  | 4.2.1 | Hire drivers | Drivers not properly qualified | 2 | 3 | 6 | Drivers documents are checked and copies made | Checked copies exist. | G4 | 2 | 1 | 2 | Documents could be forged | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | n/a
4.2 | Arrange land transport |  | 4.2.2 | Plan route | Route is blocked | 3 | 2 | 6 | Work with other agencies and the military to plan routes | Check the last plan. Examine dates of collection and delivery | G5 | 3 | 1 | 3 | HQ also tries to plan routes | Local office to plan routes | Country Director | n/a |  |  |  | 5
4.2 | Arrange land transport |  | 4.2.3 | Plan route | Route is dangerous | 3 | 2 | 6 | The army escorts convoys | Ask drivers and supervisor about escorts | n/a | 3 | 1 | 3 | None - escorts are provided | n/a | n/a | n/a |  | n/a | n/a | n/a
4.2 | Arrange land transport |  | 4..2.4 | Arrange to collect food | No food available! | 3 | 1 | 3 | HQ arrange for food to available in the warehouses | Check loading sheets for the lorries | G6 | 3 | 1 | 3 | None - food was available | n/a | n/a | n/a |  | n/a | n/a | n/a
4.2 | Arrange land transport | Fuel not available for lorries |  | Load fuel | Fuel not available for lorries | 3 | 3 | 9 | Fuel is stored in the compound | Check fuel tanks | G7 | 3 | 3 | 9 | Tanks were empty, although stock records showed they should be full | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.2 | Arrange land transport |  | 4.2.5 | Load food | No loaders | 3 | 1 | 3 | The warehouse provides loaders | Supervisor said no problem in the past | n/a | 3 | 1 | 3 | None | n/a |  | n/a |  | n/a | n/a | n/a
4.2 | Arrange land transport |  | 4.2.6 | Deliver to camp | Food is stolen | 2 | 2 | 4 | Army and police provide some protection | Question staff and other agencies about problem |  | 2 | 2 | 4 | Theft is a problem, but as well controlled as possible | No extra action possible |  | n/a |  |  |  | 1
4.3 | Arrange land transport | Lorries not available to move food inland | 4.3.1 | Check lorries are working | Lorries are found to be unsuitable for the journey | 3 | 2 | 6 | Lorries are serviced and tested | Request a ride in the lorries |  | 3 | 2 | 6 | 2 lorries were not working due to lack of maintenance (bad brakes) | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.2 | Arrange land transport |  | 4.3.1 | Check lorries | Check is not complete | 2 | 2 | 4 | Maintenance schedules are signed by the senior mechanic | Check schedules |  | 2 | 2 | 4 | Scheduled checks not always carried out due to a lack of mechanics | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.2 | Arrange land transport |  | 4.3.1 | Check lorries | Action is not taken on faults | 2 | 2 | 4 | Maintenance schedules are signed by the senior mechanic | Check schedules |  | 2 | 2 | 4 | Repairs not always carried out due to a lack of mechanics | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.3 | Maintain lorries | Mechanics not available | 4.3.1 | Check lorries | Lack of mechanics | 3 | 3 | 9 | Two mechanics are on the permanent staff | Talk to mechanics. Examine work sheets |  | 3 | 3 | 9 | Only one, inexperienced mechanic on the staff | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.3 | Maintain lorries |  | 4.3.2 | Carry out maintenance checks as per the lorry manual | Maintenance checks not carried out thoroughly | 2 | 2 | 4 | Maintenance schedules are signed by the senior mechanic | Check schedules |  | 2 | 2 | 4 | Scheduled checks not always carried out due to a lack of mechanics | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.3 | Maintain lorries |  | 4.3.3 | Repair lorries as necessary | Repairs not satisfactory | 2 | 2 | 4 | Lorries checked by compound supervisor | Request a ride in the lorries | n/a | 2 | 2 | 4 | 1 Lorry was badly damaged | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.3 | Maintain lorries |  | 4.3.3 | Repair lorries as necessary | Repairs not necessary | 2 | 2 | 4 | Request for repairs and spare parts is approved by the compound supervisor | Check request documents |  | 2 | 2 | 4 | No documents exist for requesting spares | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
4.3 | Maintain lorries | Spares not available | 4.3.3 | Repair lorries as necessary | Spares not available | 2 | 3 | 6 | HQ arrange for spares to be shipped out | Talk to supervisor and mechanic. Examine any available documentation |  | 2 | 3 | 6 | Spares can take months to arrive | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
6.6 | Provide information technology |  | 6.6.1 | Maintain systems | Data lost through computer failure | 2 | 3 | 6 | Not applicable. No computer on site | n/a |  |  |  | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
6.7 | Provide human resources | Staff competencies required have not been identified | 6.7.1 | Establish job descriptions | Staff competencies required have not been identified | 1 | 3 | 3 | Job descriptions are maintained for all jobs | Check for job descriptions of all staff levels |  | 2 | 3 | 6 | No job descriptions exist. | Job descriptions will be written by the end of March 2004 | Country Manager | n/a |  |  |  | 3
6.7 | Provide human resources | Actual competencies of the staff have not been matched with required competencies | 6.7.2 | Carry out regular appraisals | Actual competencies of the staff have not been matched with required competencies | 1 | 3 | 3 | All staff have two appraisals every year | Check appraisal files |  | 2 | 3 | 6 | No appraisals are carried out. | Targets will be set by the end of March and staff will be appraised on these by the end of September | Country Manager | n/a |  |  |  | 3
6.7 | Provide human resources | Training is not provided | 6.7.3 | Training of staff | Training is not provided | 2 | 3 | 6 | Appraisals identify training needs | Check appraisal files |  | 2 | 3 | 6 | Mechanics are not trained - but move on too quickly | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
6.7 | Provide human resources | Staff not allowed to attend training | 6.7.3 | Training of staff | Staff not allowed to attend training | 2 | 3 | 6 | None | Question staff who have been on courses |  |  |  | 0 | No courses available | We will ensure staff are trained as part of the introduction of contractors | Country Manager | n/a |  |  |  | 3
6.8 | Provide security | Loss of the Charity's assets | 6.8.1 | Provide security | Loss of the Charity's assets | 3 | 2 | 6 | The compound is surrounded by a high fence | Asked staff about security |  | 3 | 2 | 6 | The fence is regularly broken down - hence the fuel has been stolen | The use of contractors is to be considered | Logistics Director | n/a |  |  |  | 1
6.9 | Provide continuity | Office destroyed | 6.9.1 | Identify documents required to achieve the objective of these processes | Documents may not be recorded | 1 | 2 | 2 | None | None |  |  |  | 0 | Not significant | n/a | n/a | n/a |  | n/a | n/a | n/a
6.9 | Provide continuity | Office destroyed | 6.9.2 | Decide on arrangements to safeguard these | Level of protection may not be sufficient | 1 | 2 | 2 | None | None |  |  |  | 0 | Not significant | n/a | n/a | n/a |  | n/a | n/a | n/a
KEY:
[16 empty] | n/a = not apllicable |  | Inadequate, or no, processes have been used, to identify risks. Score 9 or 6 | This risks is not being mitigated to an acceptable levels and it is probable that some objectives will not be/are not being achieved | No action is being taken, OR Insufficient action is being taken to mitigate risks | Major improvements are required to the monitoring of controls over this risk
[18 empty] | Processes have been used, but there are some deficiencies. Score 4 | The risk is not being mitigated to an acceptable level by the control(s), although the consequence from the risk occurring, or likelihood of the risk occurring, is not considered significant. There is the possibility that some objectives will not be achieved Score: 4 | The action being taken will result in some reduction in risk but not to acceptable levels | Some additional monitoring is required
[18 empty] | Thorough processes have been used and all significant risks should have been identified. Score 3,2,1 or 0 | This risk is being mitigated to an acceptable level by the controls Score 3,2,1 or 0 | The action being taken will result in this risk being mitigated | No more monitoring is necessary than is done at present