## Sheet1
MARCHMONT - PARTNER'S WORK-PLAN |  |  |  |  | Open University
| Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sept |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | March |  | April |  | May |  | June |  | July |  | Aug |  | Sept |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun
| 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
Introductory discussions with Exeter and partner meetings* |  | * |  |  |  |  | *
Development of prototype Web site for partner meeting July | [12 empty] | *
Development of full site - all areas except Good Practice database
Collect resources for action learning set 1 and resource bank
Technology and inputting routines defined for GPD | [21 empty] | *
Collect resources for action learning set 2 and abstract
First 50 records extracted, keyed checked and uploaded onto GPD
Initial evaluation
Minor alterations to website
Continue to collect and build on the GPD - several hundred reqd | [28 empty] | *
Work with KMI to build ontology + workshop
Collect resources for action learning set 3
Interim formative evaluation
Web user survey followed by and major site changes
Develop ontology
Review and exploration of possible new groupware
Populate knowledge model
Evaluation report
Focus group | [36 empty] | #
Collect resources for action learning set 4 | [38 empty] | *
Collect resources for action learning set 5
Focus group | [46 empty] | # *
Test model with key questions
Evaluate model
Dissemination event
Focus group | [52 empty] | #
Final evaluation plus final report
Stop collecting GPD and finish all oustanding work | [54 empty] | *
Partner meetings *
HOBSONS
Contact UK institutions for new prospectuses
Sort replies and co-ordinate work flow
Commence mark-up for dataentry/amendment
First upload of amended data
Continue amendments and second upload
Recontact first by mail and finally by phone all non responders
Finish mark-up and dataentry/amendment - upload of data
Contact all institutions and ask them to check records - amend on return
Download data/spellcheck/cut/organise/proof and send to Hobsons
Continue data tidying and reupload to system
Start the reseaching of new institutions for addition to database
Markup and dataentry of new institutions and continue to amend late returns
Contact UK institutions for new prospectuses
Sort replies and co-ordinate work flow
Commence mark-up for dataentry/amendment
First upload of amended data
Continue amendments and second upload
Recontact first by mail and finally by phone all non responders
Finish mark-up and dataentry/amendment - upload of data
Contact all institutions and ask them to check records - amend on return
Download data/spellcheck/cut/organise/proof and send to Hobsons
Continue data tidying and reupload to system
Start the reseaching of new institutions for addition to database
Markup and dataentry of new institutions and continue to amend late returns