## Sheet1
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Toriod | Toro | Installation | E | EFD |  | Walz
Toriod | Toro | Checkout | E | NLC | SLAC | Bharadwaj
Toriod | Toro | E166 DAQ | E | EFD | SLAC | Szalata
Beam Position Monitor | BPM1 | Checkout | O | NLC | SLAC | Bharadwaj
Beam Position Monitor | BPM1 | E166 DAQ | O | EFD | SLAC | Szalata
Bend magnet | HSB1 | Fabrication | E | EFD |  | Walz
Bend magnet | HSB1 | Support | N | EFD |  | Walz
Bend magnet | HSB1 | Power Supply | E | EFD
Bend magnet | HSB1 | Cabling | N | EFD |  | Hast
Bend magnet | HSB1 | Electronics | E | ESD
Bend magnet | HSB1 | Installation | N | EFD |  | Walz
Bend magnet | HSB1 | Alignment | N | Met. |  | Walz
Bend magnet | HSB1 | Checkout | N | NLC | SLAC | Bharadwaj
Bend magnet | HSB1 | SCP/database | N | ESD
Bend magnet | HSB1 | E166 DAQ | N | EFD | SLAC | Szalata
Optical Transition Monitor | OTR | Checkout | O | NLC | SLAC | Bharadwaj
Optical Transition Monitor | OTR | E166 DAQ | O | EFD | SLAC | Szalata
Beam Position Monitor | BPM2 | Fabrication | E | EFD | SLAC | Walz
Beam Position Monitor | BPM2 | Support | N | EFD | NLC | Walz
Beam Position Monitor | BPM2 | Cabling | N | EFD | NLC | Hast
Beam Position Monitor | BPM2 | Electronics | E | ESD | NLC
Beam Position Monitor | BPM2 | SCP/database | N | ESD | NLC
Beam Position Monitor | BPM2 | Installation | N | EFD | NLC | Walz
Beam Position Monitor | BPM2 | Alignment | N | Met. |  | Walz
Beam Position Monitor | BPM2 | Checkout | N | NLC | NLC | Bharadwaj
Beam Position Monitor | BPM2 | E166 DAQ | N | EFD | NLC | Szalata
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Wire Scanner | WS | Fabrication | E | EFD |  | Walz
Wire Scanner | WS | Support | N | EFD |  | Walz
Wire Scanner | WS | Cabling | N | EFD |  | Hast
Wire Scanner | WS | Electronics | N | ESD
Wire Scanner | WS | Installation | N | EFD |  | Walz
Wire Scanner | WS | Alignment | N | Met. |  | Walz
Wire Scanner | WS | SCP/database | N | ESD
Wire Scanner | WS | E166 DAQ | N | EFD |  | Szalata
Sliding Table | ST | Fabrication | N | EFD |  | Walz
Sliding Table | ST | Assembly | N | EFD |  | Walz |  | all components on table
Sliding Table | ST | Installation | N | EFD |  | Walz |  | all components on table
Sliding Table | ST | Alignment | N | Met. |  | Walz
ST/Collimator | Pcu | Fabrication | N | EFD |  | Walz
ST/Collimator | Pcu | TV camera | E | ESD |  | Walz
ST/Collimator | Pcu | TV cam. Cables | E | ESD
ST/Undulator | Und | Fabrication | N | Cornell | Cornell | Mikhailichenko
ST/Undulator | Und | Pulser | N | Cornell | Cornell | Mikhailichenko
ST/Undulator | Und | Power Supply | N | NLC | NLC | Sheppard
ST/Undulator | Und | Cabling | N | EFD |  | Hast
ST/Undulator | Und | SCP/database | N | ESD
ST/Undulator | Und | E166 DAQ | N | EFD |  | Szalata
ST/2.5 cm i.d. tube | Und | Fabrication | N | EFD |  | Walz
ST/Beam Position Monitor | BPMi | Fabrication | E | EFD |  | Walz
ST/Beam Position Monitor | BPMi | Cabling | N | EFD |  | Hast
ST/Beam Position Monitor | BPMi | Electronics | E | ESD
ST/Beam Position Monitor | BPMi | SCP/database | N | ESD
ST/Beam Position Monitor | BPMi | Checkout | N | NLC |  | Bharadwaj
ST/Beam Position Monitor | BPMi | E166 DAQ | N | EFD |  | Szalata
ST/Beam Position Monitor | BPMo | Fabrication | E | EFD |  | Walz
ST/Beam Position Monitor | BPMo | Cabling | N | EFD |  | Hast
ST/Beam Position Monitor | BPMo | Electronics | E | ESD
ST/Beam Position Monitor | BPMo | SCP/database | N | ESD
ST/Beam Position Monitor | BPMo | Checkout | N | NLC |  | Bharadwaj
ST/Beam Position Monitor | BPMo | E166 DAQ | N | EFD |  | Szalata
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Beam Position Monitor | BPM3 | Checkout | O | NLC |  | Bharadwaj
Beam Position Monitor | BPM3 | E166 DAQ | O | EFD |  | Szalata
Corrector Magnet | Hcor | Checkout | O | NLC |  | Bharadwaj
Corrector Magnet | Hcor | E166 DAQ | O | EFD |  | Szalata
Ion Chamber | IC | Fabrication | E | EFD |  | Walz
Ion Chamber | IC | Support | N | EFD |  | Walz
Ion Chamber | IC | Cabling | N | EFD |  | Walz
Ion Chamber | IC | Electronics | E | ESD
Ion Chamber | IC | Installation | N | EFD |  | Walz
Ion Chamber | IC | Alignment | N | Met. |  | Walz
Ion Chamber | IC | SCP/database | N | ESD
Ion Chamber | IC | E166 DAQ | N | EFD |  | Szalata
Bend magnet | HSB2 | Fabrication | E | EFD |  | Walz
Bend magnet | HSB2 | Support | N | EFD |  | Walz
Bend magnet | HSB2 | Power Supply | E | EFD
Bend magnet | HSB2 | Cabling | N | EFD |  | Hast
Bend magnet | HSB2 | Electronics | E | ESD
Bend magnet | HSB2 | Installation | N | EFD |  | Walz
Bend magnet | HSB2 | Alignment | N | Met. |  | Walz
Bend magnet | HSB2 | SCP/database | N | ESD
Bend magnet | HSB2 | E166 DAQ | N | EFD |  | Szalata
Bend magnet | HSB2 | Checkout | N | NLC |  | Bharadwaj
Silicon-Tungsten Calorimeter | PCAL | E166 DAQ | N | EFD |  | Szalata
Silicon-Tungsten Calorimeter | PCAL | Checkout | N | UT |  | Bugg
Profile Monitor | PRt | Fabrication | N | EFD |  | Walz
Profile Monitor | PRt | Support | N | EFD |  | Walz
Profile Monitor | PRt | Installation | N | EFD |  | Walz
Profile Monitor | PRt | Alignment | N | Met. |  | Walz
Profile Monitor | PRt | SCP/database | N | ESD
Profile Monitor | PRt | Checkout | N | NLC |  | Bharadwaj
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Collimator | At | Design | N | EFD |  | Walz
Collimator | At | Fabrication | N | EFD |  | Walz
Collimator | At | Support | N | EFD |  | Walz
Collimator | At | Installation | N | EFD |  | Walz
Collimator | At | Alignment | N | Met. |  | Walz
Shielding |  | Design | N | NLC |  | Munro
Shielding |  | Fabrication | N | NLC |  | Munro
Shielding |  | Installation | N | NLC |  | Munro
Positron Target |  | Fabrication | N | NLC |  | Munro
Positron Target |  | Installation | N | NLC |  | Munro
Positron Target |  | Alignment | N | Met. |  | Munro
Bend magnets (90 deg.) |  | Fabrication | N | Princeton |  | McDonald
Bend magnets (90 deg.) |  | Support | N | NLC |  | Munro
Bend magnets (90 deg.) |  | Power Supply | N | Princeton |  | McDonald
Bend magnets (90 deg.) |  | Electronics | N | ESD
Bend magnets (90 deg.) |  | Cabling | N | NLC |  | Munro
Bend magnets (90 deg.) |  | Installation | N | NLC |  | Munro
Bend magnets (90 deg.) |  | Alignment | N | Met. |  | Munro
Bend magnets (90 deg.) |  | SCP/database | N | ESD
Bend magnets (90 deg.) |  | E166 DAQ | N | EFD |  | Szalata
Bend magnets (90 deg.) |  | Checkout | N | NLC |  | Bharadwaj
Aerogel Counters |  | Fabrication | N | Princeton |  | McDonald
Aerogel Counters |  | Support | N | NLC |  | Munro
Aerogel Counters |  | Cabling | N | EFD |  | Hast
Aerogel Counters |  | Electronics | N | Princeton |  | McDonald
Aerogel Counters |  | Installation | N | EFD |  | Munro
Aerogel Counters |  | Alignment | N | Met. |  | Munro
Aerogel Counters |  | E166 DAQ | N | EFD |  | Szalata
Aerogel Counters |  | Checkout | N | Princeton |  | McDonald
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Magnetized Iron (15 cm) |  | Design | N | DESY |  | Schuler
Magnetized Iron (15 cm) |  | Fabrication | N | DESY |  | Schuler
Magnetized Iron (15 cm) |  | Support | N | NLC |  | Munro
Magnetized Iron (15 cm) |  | Power Supply | N | DESY |  | Schuler
Magnetized Iron (15 cm) |  | Electronics | N | ESD
Magnetized Iron (15 cm) |  | Cabling | N | EFD |  | Hast
Magnetized Iron (15 cm) |  | Installation | N | NLC |  | Munro
Magnetized Iron (15 cm) |  | Alignment | N | Met. |  | Munro
Magnetized Iron (15 cm) |  | SCP/database | N | ESD
Magnetized Iron (15 cm) |  | E166 DAQ | N | EFD |  | Szalata
Magnetized Iron (15 cm) |  | Checkout | N | NLC |  | Bharadwaj
Magnetized Iron (7.5 cm) |  | Design | N | DESY |  | Schuler
Magnetized Iron (7.5 cm) |  | Fabrication | N | DESY |  | Schuler
Magnetized Iron (7.5 cm) |  | Support | N | NLC |  | Munro
Magnetized Iron (7.5 cm) |  | Power Supply | N | DESY |  | Schuler
Magnetized Iron (7.5 cm) |  | Electronics | N | ESD
Magnetized Iron (7.5 cm) |  | Cabling | N | EFD |  | Hast
Magnetized Iron (7.5 cm) |  | Installation | N | NLC |  | Munro
Magnetized Iron (7.5 cm) |  | Alignment | N | Met. |  | Munro
Magnetized Iron (7.5 cm) |  | SCP/database | N | ESD
Magnetized Iron (7.5 cm) |  | E166 DAQ | N | EFD |  | Szalata
Magnetized Iron (7.5 cm) |  | Checkout | N | NLC |  | Bharadwaj
Silicon Counter | SiCntr | Fabrication | N | UT |  | Bugg
Silicon Counter | SiCntr | Support | N | NLC |  | Munro
Silicon Counter | SiCntr | Cabling | N | EFD |  | Hast
Silicon Counter | SiCntr | Electronics | N | UT |  | Bugg
Silicon Counter | SiCntr | Installation | N | NLC |  | Munro
Silicon Counter | SiCntr | Alignment | N | Met. |  | Munro
Silicon Counter | SiCntr | E166 DAQ | N | EFD |  | Szalata
Silicon Counter | SiCntr | Checkout | N | UT |  | Bugg
SYSTEM | Name | SubSystem | N/E/O | Dept. | Money | Responsible | Done by | Comment
Silicon-Tungsten Calorimeter | GCAL | Fabrication | N | UT |  | Bugg
Silicon-Tungsten Calorimeter | GCAL | Support | N | NLC |  | Munro
Silicon-Tungsten Calorimeter | GCAL | Cabling | N | EFD |  | Hast
Silicon-Tungsten Calorimeter | GCAL | Electronics | N | UT |  | Bugg
Silicon-Tungsten Calorimeter | GCAL | Installation | N | NLC |  | Munro
Silicon-Tungsten Calorimeter | GCAL | Alignment | N | Met. |  | Munro
Silicon-Tungsten Calorimeter | GCAL | E166 DAQ | N | EFD |  | Szalata
Silicon-Tungsten Calorimeter | GCAL | Checkout | N | NLC |  | Bugg
Cesium Iodide Calorimeter | CSI | Fabrication | N | Zeuthen |  | Stahl
Cesium Iodide Calorimeter | CSI | Support | N | NLC |  | Munro
Cesium Iodide Calorimeter | CSI | Cabling | N | EFD |  | Hast
Cesium Iodide Calorimeter | CSI | Electronics | N | Zeuthen |  | Stahl
Cesium Iodide Calorimeter | CSI | Installation | N | NLC |  | Munro
Cesium Iodide Calorimeter | CSI | Alignment | N | Met. |  | Munro
Cesium Iodide Calorimeter | CSI | E166 DAQ | N | EFD |  | Szalata
Cesium Iodide Calorimeter | CSI | Checkout | N | Zeuthen |  | Stahl
Vacuum System |  | Fabrication | N | EFD |  | Walz
Vacuum System |  | Installation | N | EFD |  | Walz
Vacuum System |  | Alignment | N | Met. |  | Walz
Vacuum System |  | Checkout | N | EFD |  | Walz