## Sheet1
DRAFT 2004 RTP DEVELOPMENT SCHEDULE
| 2003 |  |  |  |  | 2004 |  |  | 2005
| 1 Qtr. | 2 Qtr. | 3 Qtr. | 4 Qtr. | 1 Qtr. | 2 Qtr. | 3 Qtr. | 4 Qtr. | 1 Qtr. | 2 Qtr.
| Phase 1: Regional |  |  |  | Phase 2: Local |  |  | Phase 3: Hearings
2004 RTP Outreach Milestones
Key 2004 RTP Decision Milestones | 2003 3 Qtr.: Initial; 2003 4 Qtr.: Final
RTP Revenue Projections
Identify Regional and County Proposed RTP Investment Strategies/Criteria (based on major issues as shown below)
Transit & Roads MTS
Performance measure criteria
ABAG Smart Growth Projections
Air Quality Conformity (State Implementation Plan)
Water Transit Authority Plan Approval
Regional Freight Study
Lifeline Transit/Community Transportation Plans
$3 Bridge Toll
New Revenue: TEA 3
Countywide Plan Updates
Regional Gas Tax Measure
Contra Costa County Sales Tax
Marin County Sales Tax
Sonoma County Sales Tax
SMART Ballot Measure
San Mateo County Sales Tax
San Francisco Sales Tax
Statewide High-Speed Rail Bond Measure
Release Draft EIR for Public Review
Initial Performance Evauation and Alternative Develop.
Complete Modeling/Conformity of RTP and EIR
Release Draft 2004 RTP for Public Review
Commission Adoption of 2004 RTP
Federal Conformity Approval of 2004 RTP
Complete: 12/03
Complete: 6/03
8/04
1/05
9/04
3/05
Complete:7/03
Complete: 5/03
Complete 5/03
Nov. election
legislation completed
by late 2003
SIP
by 4/04
"budget" by
7/04
Complete by 7/04
Complete 9/03
March election
Nov. election
Nov. election
Nov. election
Nov. election
Complete: 9/03
draft SIP
by 12/03
Complete: 6/03
Preliminary
Complete: 7/03
Complete: 5/04
Complete: 2/04
Nov. election
Nov. election
Nov. election
RTP Summit Meeting: 7/03
Regional Workshops: 9/03 - 12/03
CMA Outreach: 1/04 - 6/03
Complete: 11/04
Final
9/04