## 1A
Goal 1: Employ processes and programs resulting in measurable improvement in all subject areas emphasizing reading,
mathematics, and writing.
Strategy 1A: Develop, deploy and evaluate effective classroom instructional models and practices for all grade level/subject area
teacher groups.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Utilizing the Plan, Do, Study, Act (PDSA) | PreK-12 Students, | In a district the size of Rock | Jay Marino, | Title II, Title V and | February 1,
model of continuous improvement, collect | Staff & | Island- in order to effectively | Curriculum Office | local district funding | 2003
baseline data from each school identifying | Administrators | deploy effective instructional | & Building
those effective, innovative instructional |  | models, it will be necessary to | Principals
strategies that are already deployed at the |  | implement a “trainer of trainers”
school level. (PLAN) |  | model
3 Review research and best practices of |  | This core group of teachers will |  |  | October
effective instruction and recommend a list of |  | receive training in the identified |  |  | Feb. 1, 2003
core effective strategies to be implemented in |  | instructional models and will in
all schools. (PLAN) |  | turn deliver the training in the
respective school.
3 Align instructional models to the "Effective" |  | This model is intended to create |  |  | October
Teaching Practices” in RISD (PLAN) |  | internal capacity for change. |  |  | Aug. 1, 2003
3 Identify common training needs (PreK-6; 7-12 |  |  |  |  | Feb. Aug. 1,
or other configurations) to deploy the effective |  |  |  |  | 20042003
instructional strategy training model. (PLAN)
3 Identify trainers and develop a cadre of |  |  |  |  | Mar. 1, 2004
trainers from each school. (DO) |  |  |  |  | Aug. 1, 2003
3 Review each school's SIP to identify |  |  |  |  | December 1,
specific training needs related to School |  |  |  |  | 2003
Improvement Plan (SIP) data and the designed
effective instructional strategy model. (PLAN)
 Provide training to the cadre “trainers” in |  |  |  |  | Aug. 1, 2004
how to train teachers at the school level. (DO) |  |  |  |  | 2003-2004
school year
1A-1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Schools will submit an implementation time- |  |  |  |  | August 1,
line in which training will take place. (DO) |  |  |  |  | Feb. 1, 2004
 Deploy training in a systematic manner |  |  |  |  | 2003-04 and
through the use of teacher training cadres at |  |  |  |  | 2004-05
the school level. (DO) |  |  |  |  | school years
 Develop learning opportunities and follow- |  |  |  |  | 2004-2005
up professional development as needed- |  |  |  |  | School Year
supported by building cadre and trainers
(and/or outside sources). (DO)
 Assess effectiveness of effective instructional |  |  |  |  | June 1,
model based on student achievement data and |  |  |  |  | 2005
teacher feedback and make adjustments as
necessary. (STUDY)
 Report progress to the Board of Education |  |  |  |  | August 1,
and RISD school community. Standardize |  |  |  |  | 2005
model to ensure maximum effectiveness. (ACT)
Updated 11/4/03 |  |  |  |  | 1A - 2
District Improvement Action Plan Strategy 1A

## 1B
Goal 1: Employ processes and programs resulting in measurable improvement in all subject areas emphasizing reading,
mathematics, and writing.
Strategy 1B: Develop, deploy and evaluate a K-12 student assessment system that provides timely and accurate feedback on
student academic performance and the effectiveness of instruction.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Evaluate and decide on expanding admini- | PreK-12 | It is important in a comprehensive | Director of Reading | $25,000 annually | January 1,
stration of the Iowa Test of Basic Skills in grades | Students | assessment system to track stud- |  |  | 2003
3-8 to (1) inform school improvement plans, |  | ents' achievement who remain in | Assistant Superin-
classroom instruction, and professional |  | remain in identified period of time. | tendent for
development and (2) inform stakeholders |  | We must use assessment to also | Instruction
(students, parents, Board of Education, and the |  | assess instruction and our
community) of student progress. (PLAN) |  | balanced literacy curriculum.
3 Evaluate the validity and reliability of the |  |  |  |  | January 1,
STAR reading test to (1) inform school improve- |  |  |  |  | 2003
ment plans, (2) classroom instruction, (3) profes-
sional development and (4) inform stakeholders
of student progress. We will decide on the future
use of STAR as a required reading test. (PLAN) |  |  |  |  | 1B - 1
3 Identify two appropriate Houghton Mifflin |  | These tests will complement the |  | Approx. $2,000 | Jan. Aug. 1,
Integrated Theme Tests to be collected district |  | requirement of a balanced assess- |  | for each school | 2003
wide in order to evaluate student achievement |  | ment system by providing teachers,
and the district's reading/language arts curricu- |  | principals, and central office with
lum. The purpose of the assessments is to provide |  | curriculum-based assessment.
timely and valid feedback during a student's time
in District 41. (PLAN)
3 Develop a district assessment philosophy |  |  |  |  | May Aug. 1,
which will guide the appropriate selection, uses, |  |  |  |  | 2003
and interpretations of current and future district
tests. (PLAN)
1B-1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Administer ITBS in grades 3-8 in late August, |  |  |  |  | August 1,
using test results to inform school improvement |  |  |  |  | 2003
plans. August testing will provide the district
with timely feedback--with results received before
the first intersession. (DO)
3 Refine and have ready a problem-free data col- |  |  |  |  | Sept. 1,
lection procedure for the Houghton Mifflin Inte- |  |  |  |  | 2003
grated Theme tests. Collect three two theme tests
district wide in grades 2-6 and enter this data in
Discovery in order to provide timely and accurate
feedback and to track students during their time
in District 41. (DO)
3 Identify and pilot the appropriate data collec- |  | This task insures that we are look- |  |  | Apr. Nov. 1,
tion form for the Houghton Mifflin Integrated |  | ing at the same group of students |  |  | 2003
Theme Tests. This data will be entered into |  | over an extended period of time.
Discovery in order to provide timely and accurate |  | An important criteria for an effec-
feedback during a student's time in District 41. |  | tive assessment system is to have
(PLAN) |  | readily available a variety of
|  | student profiles. |  |  | 1B-1
3 Utilize the district fall and spring writing |  |  |  |  | May 1, 2003
assessments to plan for professional develop-
ment, using the Writing Plan on a Page. (PLAN)
 Evaluate and decide on the necessity of contin- |  |  |  |  | Mar. 1, 2003
uing the language arts competency units in |  |  |  |  | Feb. 1, 2004
grades 3, 6, and 8 as required units for the
district-wide data collection assessment system.
(PLAN)
3 Collaborate with Riverside Publishing to con- |  |  |  |  | October 1 8,
duct professional development training using |  |  |  |  | 2003
data from Iowa Test of Basic Skills to (1) inform
school improvement plans, (2) classroom instruc-
tion, (3) professional development, and commun-
ication with stakeholders. (PLAN) |  |  |  |  | 1B - 2
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Provide training for Literacy Facilitators who |  |  |  |  | Oct. 1, 2003
will in turn provide training for their staff on |  |  |  |  | Feb. 4, 2003
preparing students for ISAT reading and writing.
(DO)
 Study the feasibility of using reading fluency |  |  |  |  | February 1,
tests in grades 2-6 to evaluate student reading |  |  |  |  | 2004
growth. (STUDY)
 Pilot reading fluency tests in grades 3, 4, and 5 |  |  |  |  | Sept. Jan. 1,
that provide timely and accurate feedback. (DO) |  |  |  |  | 2003 2004
 Integrate data from ITBS and the Houghton |  |  |  |  | Jan. Apr. 1,
Mifflin Integrated Theme Tests into school |  |  |  |  | 2004
improvement plans. Coaching sessions will be
scheduled for each building to accomplish this
task. (DO)
 Utilize Cognos reporting software to provide |  |  |  |  | May 1,
timely and accurate feedback to generate reports |  |  |  |  | 2004
which inform school improvement plans. (DO)
 Provide training for each elementary and |  |  |  |  | May 1,
junior high on using reading and writing assess- |  |  |  |  | 2004
ment data to inform school improvement plans,
classroom instruction, and professional develop-
ment. This action step implements data-driven
decisions. (DO)
 Align the Illinois Language Arts Learning |  |  |  |  | May 1,
Standards to the district's assessment system and |  |  |  |  | 2004
balanced literacy curriculum to insure coherence
in assessment, curriculum, and instruction. (DO)
1B - 3
Updated 11/4/03
District Improvement Action Plan Strategy 1B

## 1C
Goal 1: Employ processes and programs resulting in measurable improvement in all subject areas emphasizing reading,
mathematics, and writing.
Strategy 1C: Refine, deploy, and evaluate a system of academic interventions for students not meeting achievement standards as
measured by the District's assessment system.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Apply for funding sources to support indivi- | K-12 | Academic interventions are | Asst. Supt. for | Title I, Title II, Title | June 1,
dual school proposals for academic intervention |  | designed to assist students who | Instruction | V, REA, Reading | 2003
by completing the No Child Left Behind grant |  | are below grade level in the aca- | Director of Title I | Improvement,
and Reading Improvement grant. (PLAN) |  | demic areas of literacy; reading | Principals | Reading First
and writing.
3 Establish criteria that defines a need for inter- |  | Each building will be provided an | Asst. Supt. for |  | June 1,
ventions and criteria to guide effective selection |  | opportunity to utilize funds for | Instruction |  | 2003
of interventions and create academic measures to |  | academic intervention purposes in | Director of Title I
gauge effectiveness of interventions. (PLAN) |  | their building.
3 Schools will identify students who are in need |  | Schools will be asked to complete a | Principals |  | August 1,
of academic interventions, using data available |  | brief proposal on how they might |  |  | 2003
from the District assessment plan and other |  | utilize funds to create an effective
achievement data. (PLAN) |  | intervention program for their
students.
3 Communicate guidelines and proposal format |  | It will be essential that proposals | Asst. Supt. for |  | August 1,
for schools to apply for academic intervention |  | be aligned with building School | Instruction |  | 2003
funding (and to include in the school improve- |  | Improvement Plans (goals and | Director of Title I
ment plan). Announce a call for academic inter- |  | objectives).
vention proposals to all schools. (DO)
3 Accept, approve and fund academic interven- |  |  | Asst. Supt. for |  | Aug. 1 Sept.
tion proposals from schools. (DO) |  |  | Instruction |  | 30, 2003
Director of Title I
 Deliver interventions to students identified and |  |  | Asst. Supt. for |  | 2003-2004
measure academic progress according to |  |  | Instruction |  | School Year
approved proposals. (DO) |  |  | Director of Title I
Principals
1C - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Review academic intervention programs and |  |  | Asst. Supt. for |  | June 1,
measure student achievement growth. (STUDY) |  |  | Instruction |  | 2004
Director of Title I
Principals
 Evaluate effectiveness of academic intervention |  |  | Asst. Supt. for |  | August 1,
programs and report to Board of Education and |  |  | Instruction |  | 2004
make recommendations for future academic |  |  | Director of Title I
intervention activities. (ACT) |  |  | Principals
1C - 2
District Improvement Action Plan Strategy 1C

## 2A
Goal 2: Forge effective relationships with the Rock Island and Milan communities and parents to enhance students’ educational
opportunities.
Strategy 2A: Refine, deploy, and evaluate programs for parents and guardians to develop skills to enhance the
educational opportunities of their children.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Meet with parents to determine, through focus | Parents of K-12 | As it takes an entire community to | Assistant Superin- | Title IV, Title II, | May 1,
groups and surveys, types of parent training to |  | raise a child, parents are a crucial | tendent for Pupil | District Professional | 2003
be provided. (PLAN) |  | component of the team. Their abili- | Personnel Services | Development Funds
ty to support and enhance their
child’s education is vital to student
success.
 Identify, in conjunction with Title I Parent Out- |  |  | Assistant Superin- |  | June 1,
reach , Discipline Committee, PPS staff, teachers |  |  | tendent for Pupil |  | 2003
and principals, specific sessions and timelines |  |  | Services, Title I |  | December 1,
for training. (PLAN) |  |  | Director |  | 2003
 Provide parent training throughout the year. |  |  |  |  | Sept. 1,
(DO) |  |  |  |  | 2003-April
30, 2004
 Collect data and build on successful training. |  |  |  |  | May 1,
(STUDY) |  |  |  |  | 2004
 Evaluate and report to Cabinet, Principals, and |  |  |  |  | May 15,
Board of Education. (STUDY) |  |  |  |  | 2004
 Refine in-service program utilizing data and |  |  |  |  | Annually
feedback. (ACT) |  |  |  |  | and
throughout
the year
2A - 1
District Improvement Action Plan Strategy 2A

## 2B
Goal 2: Forge effective relationships with the Rock Island and Milan communities and parents to enhance students’ educational
opportunities.
Strategy 2B: Expand, deploy, and evaluate school/business partnerships within District 41
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Assess current status of school/business/commun- | Parents, citizens, | Collaboration among various | Dave Markward | District funds, | June 1,
ity collaboration to determine degree of collaboration | businesses of | community constituencies streng- |  | possible grants/ | 2003
and/or number of partnerships for each school. | RISD 41 | then communication and provide |  | donations from
(PLAN) |  | direct and indirect services to |  | community
parents and students that enhance
the offerings of the schools.
3 Determine schools in need of additional |  |  |  |  | June 15,
collaborative efforts. (PLAN) |  |  |  |  | 2003
3 Devise plan to increase collaboration/partnerships |  |  |  |  | August 1,
where necessary. (PLAN) |  |  |  |  | 2003
3 Establish evaluation system for partnerships/ |  |  |  |  | August 1,
collaborations. (PLAN) |  |  |  |  | 2003
3 Enlist new entities for partnerships/collaborations. |  |  |  |  | October 1,
(DO) |  |  |  |  | 2003
 Express appreciation all partnerships/collabations |  |  |  |  | January 15,
(new and old). (DO) |  |  |  |  | 2004
 Utilize evaluation system for partnership/collabora- |  |  |  |  | Aug. 1, '03
tions. (DO) |  |  |  |  | Annually
 Report findings to public and Board of Education. |  |  |  |  | Annually
(DO) |  |  |  |  | in July
 Develop strategies for improvement. (STUDY) |  |  |  |  | Annually,
following
evaluation
2B - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Implement strategies for improvement (ACT) |  |  |  |  | Annually
Updated 11/4/03 |  |  |  |  | 2B - 2
District Improvement Action Plan Strategy 2B

## 2C
Goal 2: Forge effective relationships with the Rock Island and Milan communities and parents to enhance students’ educational
opportunities.
Strategy 2C: Refine, deploy, and evaluate communication and public relations programs to provide accurate and timely
information about the District, its programs, and students.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Define current program. (PLAN) | All stakeholders | In times of mobility, Internet access, | Dave Markward | District funds, | June 1,
| as well as | and limited resources, it is impera- |  | possible grants/ | 2003
| individuals | tive that the District provide accur- |  | donations
| outside of | ate and timely information to pro-
| District 41. | mote the District schools as out-
standing places in which to be
educated and the community as an
outstanding place in which to live.
3 Determine effectiveness of existing public |  |  |  |  | July 15,
relations program. (PLAN) |  |  |  |  | 2003
3 Identify alternative funding sources. (Plan) |  |  |  |  | July 15,
2003
 Reaffirm or create job description and working |  |  |  |  | July 15, 2003
plan for PR program. (DO) |  |  |  |  | Oct. 1, 2003
 Develop evaluation process and cycle to |  |  |  |  | July 15,
determine program effectiveness. (DO) |  |  |  |  | 2003
 Recommend PR structure and evaluation |  |  |  |  | August 1,
process/cycle to Board of Education. (DO) |  |  |  |  | 2003
 Evaluation of program/personnel. (STUDY) |  |  |  |  | Biannually
 Determine and implement changes. (ACT) |  |  |  |  | Annually
2C - 1
District Improvement Action Plan Strategy 2C

## 3A
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3A: Refine, deploy, and evaluate District and school continuous improvement processes that contribute to improvement
of student learning.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Evaluate progress toward meeting the Lin- | PreK-12 Students, |  | Dave Markward | Title II, Title V and | June 1,
coln criteria for performance excellence award | Staff and |  | Jay Marino | local district | 2003
criteria and apply for Lincoln Award level II- | Administrators |  | Mike Oberhaus | funding
silver, if applicable. (ACT)
3 Enlist administrators to complete Lincoln |  |  | Dave Markward |  | June 1,
examiner training. (ACT) |  |  |  |  | 2003
3 Work on “opportunities for improvement” |  |  | Cabinet |  | 02-03 and
(OFI’s) from latest Lincoln site visit recommen- |  |  |  |  | 03-04
dation. (ACT) |  |  |  |  | school year
3 Continue developing leadership team |  |  | Dave Markward |  | 02-03 and
through the implementation of bi-monthly |  |  | Jay Marino |  | 03-04
meetings focused on deploying Lincoln/ |  |  |  |  | school year
Baldrige principles. (ACT)
3 Utilize Koalaty Kid Facilitators in each build- |  |  | Jay Marino |  | 02-03 and
ing to build internal leadership capacity and |  |  |  |  | 03-04
support for continuous improvement processes |  |  |  |  | school year
and tools. (ACT)
3 Continue to offer Koalaty Kid training to all |  |  | Jay Marino |  | 02-03 and
interested school improvement teams and staff. |  |  |  |  | 03-04
(ACT) |  |  |  |  | school year
3 Refine Lincoln/Baldrige school improvement |  |  | Cabinet, |  | August 1,
template and implement new SIP model district |  |  | Administrators |  | 2003
wide to align school goals to District goals.
(ACT)
3A - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Approve and monitor school improvement |  |  | Jay Marino |  | Sept. 30th
plans. (DO) |  |  |  |  | Annually
3 Create district-wide PDSA project for all | All Employees |  | Cabinet |  | Sept. 1,
stakeholders to participate and learn more |  |  |  |  | Nov. 1, 2003
about the PDSA model. (PLAN)
 Implement PDSA as the key model for | PreK-12 Students, |  | Jay Marino | Title II, Title V and | December 1,
improvement processes and monitor through | Staff and |  | Principals | local district funding | 2003
the SIP process. (DO) | Administrators |  | Cabinet
 Refine process management by identifying |  |  | Cabinet |  | Aug. 1, 2003
key processes in each central office department |  |  |  |  | Jan. 1, 2004
and school. Document key processes using
quality tools (flow chart). (DO)
 Integrate Baldrige criteria into other school |  |  | Cabinet |  | 02-03 and
district areas such as; school board, communi- |  |  | Board of Education |  | 03-04
cation council, cabinet, administrators and |  |  |  |  | school year
staff as appropriate. (DO)
 Design school improvement internal review |  |  | Jay Marino |  | February 1,
process with input from administrators and |  |  | Principals |  | 2004
staff. (PLAN)
 Implement external review and site visitation |  |  | Cabinet |  | August 1,
process for school improvement (including |  |  | Principals |  | 2004
necessary training) which is closely aligned
with validating Baldrige criteria for perform-
ance excellence. (DO)
3 Conduct a quarterly review of the District |  |  | Cabinet |  | Oct. 15,2003
strategic action plan (and individual school |  |  | Board of Education |  | Dec. 20,2003
SIPs) and report progress to the Board of Edu- |  |  | Principals |  | Mar. 15,2003
cation quarterly. (STUDY) |  |  |  |  | June 1, 2003
3A - 2
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Adjust District strategic plan as necessary |  |  | Cabinet |  | Oct. 15,2003
according to the quarterly review and continue |  |  | Board of Education |  | Dec. 20,2003
to implement the strategic plan. (ACT) |  |  |  |  | Mar. 15,2003
June 1, 2003
Updated 11/4/03 |  |  |  |  | 3A - 3
District Improvement Action Plan Strategy 3A

## 3B
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3B: Implement a budget process to efficiently allocate available resources to meet the programmatic needs of all students.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Review current program offerings, recom- | All students, Board | Effective utilization of District | Assistant Supt's, | N/A | Sept.-Nov.
mendations to delete or modify. (STUDY) | Community | assets to meet the programmatic | Principals |  | 2002 2003
needs of all students.
3 Project five years of financial data. (DO) |  | Provide long range planning for | Comptroller |  | Nov. 11 10,
|  | finance. |  |  | 2002 2003
3 Develop preliminary tax levy estimate. (DO) |  | Provide estimates of levies based | Comptroller |  | Nov. 11 10,
|  | on EAV and tax rates. |  |  | 2002 2003
 Present five year financial projections to |  |  | Comptroller |  | Nov. 26 25,
Board of Education. (DO) |  |  |  |  | 2002 2003
 Publish tax levy notice in Argus. (If levy is |  | Comply with state law, inform | Comptroller | 500 | Nov. 29 26-
greater than 105% above prior year.) (DO) |  | citizens. |  |  | Dec. 3 7, 2002
 Tax levy hearing and adoption. (DO) |  | Comply with state law, inform | Comptroller |  | Dec. 10 9,
|  | citizens. |  |  | 2002 2003
 Solicit principal input on budget adjustments. | Principals | Allow feedback from stake- | Superintendent, |  | Dec. 12 11,
(DO) |  | holders on budget priorities. | Principals |  | 2002 2003
 Develop 1st estimate of revenues. (DO) |  | Allow for analysis and revision. | Comptroller |  | Dec. 13 12,
2002 2003
 Solicit input from unions. (DO) | Representatives of | Allow stakeholders input in | Superintendent, |  | Dec. 18 17,
| collective bargain- | budget process. | Comptroller |  | 2002 2003
ing units
 Present revenue projections to the |  |  | Comptroller |  | Dec. 20 19,
Superintendent. (DO) |  |  |  |  | 2002 2003
3B - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Recommendations for new instructional | Students/staff | Determine focus on education- | Asst. Supt. for |  | Dec. 20 19,
direction. (DO) |  | al programs for following year. | Instruction |  | 2002 2003
 Develop draft of budget adjustments. (DO) |  | Compile input/feedback | Cabinet |  | Dec. 20 19,
|  | collected from stakeholders. |  |  | 2002 2003
 Prioritize draft of budget adjustments. (DO) |  |  | Cabinet |  | Jan. 3,
2003 2004
 Present new concepts to Superintendent. |  | Changes impacting operations | Assistant |  | Jan. 7
(DO) |  | and budget for the following | Superintendents |  | 2003 2004
year.
 Present draft of adjustments and solicit |  | Inform Principals of adjustments, | Superintendent, |  | Jan. 17, 2003
feedback. (DO) |  | receive feedback from them. | Comptroller |  | Jan. 16, 2004
 03-04 revenue estimates reviewed by Board |  | Share at public meeting revenue | Comptroller |  | Jan. 21, 2003
of Education. (STUDY) |  | estimates for next year. |  |  | Jan. 20, 2004
 Preliminary costing of salaries and fringe |  | Develop line item detail for | Comptroller, Asst. |  | Jan. 24, 2003
benefits. (DO) |  | salaries and fringes. | Supt. for HR |  | Jan. 23, 2004
 Recommendation for adoption of new course | Students/Staff | New course adoptions involving | Asst. Supt. for |  | Feb. 7, 2003
material. (STUDY) |  | costs to be incorporated into the | Instruction |  | Feb. 6, 2004
budget.
 Curriculum needs and instructional equip- |  | Establish budgetary needs for | Asst. Supt. for |  | Feb. 14, 2003
ment budget requests (approved programs). |  | this area. | Instruction |  | Feb. 13, 2004
(DO)
 Determine building projects for summer 2003 |  | Allow stakeholders input into | Principals, Supt., |  | Feb. 28, 2003
completion. (PLAN) |  | facility needs. | Maintenance Dir., |  | Feb. 27, 2004
Comptroller
 Finalize prioritized listing of budget |  | Review input from all stake- | Cabinet |  | Feb. 2003
adjustments. (DO) |  | holders to determine final prior- |  |  | Feb. 2004
itization of adjustments.
3B - 2
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Review annual requisitions with employee |  | Allows users of materials to have | Comptroller |  | Feb. 2003
teams. (PLAN) |  | input into products bid for |  |  | Feb. 2004
acquisition.
 Present prioritized adjustments to the Board. |  | Public presentation of adjust- | Superintendent |  | Feb. 25, 2003
(DO) |  | ments, receive input/feedback |  |  | Feb. 24, 2004
from Board.
 Present preliminary aggregate budget to |  | Public review of aggregate | Comptroller |  | Feb. 25, 2003
Board. (DO) |  | budget, highlight changes from |  |  | Feb. 24, 2004
prior year.
 Send annual requisition forms to buildings. |  | Order forms for warehouse | Comptroller |  | Feb. 27, 2003
(DO) |  | materials to buildings to estimate |  |  | Feb. 26, 2004
quantities to be bid.
 Prioritize capital project needs. (DO) |  | From input received by stake- | Supt., Maintenance |  | Mar. 7, 2003
|  | holders determine the priorities | Dir., Comptroller |  | Mar. 5, 2004
of projects.
 Begin detail work on line item budget. (DO) |  | Breakdown aggregate estimates | Comptroller |  | Mar. 10, 2003
|  | into line item detail. |  |  | Mar. 8, 2004
 Act of staff adjustments for 2003-04. (DO) |  | Board action on staff reductions. | Supt., Board |  | Mar. 11, 2003
Mar. 9, 2004
 Finalize program offerings and curriculum |  | Determine budgetary needs for | Asst. Supt. for |  | Mar. 12, 2003
needs. (DO) |  | programs and curriculum to be | Instruction |  | Mar. 10, 2004
delivered during 2003-04.
 Review of 2003-04 revenue budget by Board |  | Public review of detailed revenue | Supt., Comptroller |  | Mar. 25, 2003
of Education. (STUDY) |  | budget. Receive feedback from |  |  | Mar. 23, 2004
Board.
 Finalize supply and capital needs budgets. |  | Provide budgetary information | Supt., Comptroller |  | Mar. 28, 2003
(DO) |  | to buildings for their planning. |  |  | Mar. 26, 2004
3B - 3
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Complete detail revenue and expenditure |  | Work session on proposed bud- | Comptroller |  | April 4, 2003
projections. (DO) |  | get. Solicit input and feedback. |  |  | April 2, 2004
 Review preliminary budget with Board of |  |  | Supt., Comptroller |  | April 8, 2003
Education. (STUDY) |  |  |  |  | April 6, 2004
 Finalize detail budget. (ACT) |  | Based on feedback from April 8 | Comptroller |  | April 2003
|  | and any other pertinent informa- |  |  | April 2004
tion, complete detail budget.
 Public Presentation of 2003-04 Budget. (DO) |  | Present budget to Board in open | Supt., Comptroller |  | May 13, 2003
|  | meeting. |  |  | May 11, 2004
 Place tentative budget on file for public |  | Budget is placed on file for a | Board of Education |  | May 13, 2003
review. (STUDY) |  | minimum of 30 days prior to |  |  | May 11, 2004
adoption. During this time the
public may review and comment
on proposed budget.
 Place notice of budget hearing in the Argus. |  | Advertise notice of public | Comptroller |  | May 16, 2003
(DO) |  | hearing in newspaper. |  |  | May 14, 2004
 Return completed annual requisitions. (DO) |  |  | Principals, |  | May 16, 2003
|  |  | Administrators |  | May 14, 2004
 Review final budget with Principals. (DO) |  | Review budget with key | Supt., Comptroller |  | May 22, 2003
|  | stakeholders. |  |  | May 20, 2004
 Bid all annual requisitions. (DO) |  | Bid for acquisition of materials | Comptroller |  | May 2003
|  | for 2003-04. |  |  | May 2004
 Hold budget hearing and adopt budget |  | Conduct hearing allowing citi- | Board of Education |  | June 24, 2003
(must adopt prior to September 30, 2003). |  | zens to comment on budget. |  |  | June 22, 2004
(ACT) |  | Formal adoption of budget on
State Budget Form.
Updated 11/4/2003 |  |  |  |  | 3B - 4
District Improvement Action Plan Strategy 3B

## 3C1
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3C.1: Refine, deploy and evaluate a management system for monitoring the proper utilization of allocated funds
and enhancing data reporting systems providing timely and effective analysis of programs and resources.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Enhance financial software for ease of use
by employees.
3 Install upgrade of financial (APECS) | Employees | Provide greater access to inform- | Technology | Part of annual | Nov. 2002
software. (DO) |  | ation for employees. |  | maintenance fee | March 2003
 Train Human Resources and Payroll. (DO) |  | Train key staff in the upgrades to | Technology |  | Aug. 2003
|  | the software. Collect feedback to |  |  | Nov. 2003
resolve issues prior to deploying
any further.
 Train Administrators. (DO, STUDY, ACT) |  | Provide training to Administra- | Technology, |  | Sept. 2003
|  | tors on system access, data ele- | Human Resources, |  | Jan. 2004
|  | ments available, computation of | Payroll
changes and reporting. Collect
feedback to resolve issues prior
to deploying any further.
 Train Secretaries. (DO, STUDY, ACT) |  | Provide training to Secretaries on | Technology, |  | Oct. 2003
|  | access, data available, computa- | Human Resources, |  | March 2004
|  | tion of changes and reporting. | Payroll
Collect feedback to resolve issues
prior to deploying any further.
 Train Employees. (DO) |  | Provide a series of workshops | Technology, |  | Jan. 2004
|  | training employees to use the | Human Resources, |  | April 2004
|  | system to lookup up their per- | Payroll
sonal data within the Human
Resources and Payroll system.
Explain how to use system to
estimate changes to pay with
different deductions.
 Evaluate utilization of system. (STUDY) |  | Determine effectiveness of use. | Technology |  | June 2004
Updated 11/4/03 |  |  |  |  | 3C1 - 1
District Improvement Action Plan Strategy 3C1

## 3C2
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3C.2: Refine, deploy and evaluate a management system for monitoring the proper utilization of allocated funds
and enhancing data reporting systems providing timely and effective analysis of programs and resources.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Employee attendance and Student data
reporting.
3 Administrator introduction to COGNOS | Administrators | Provide management tools for | Technology Dept. |  | Nov. 2002
software. (DO) |  | consistent, accurate data entry
and reporting data in a flexible
and user friendly manner.
3 Technology staff trained on COGNOS | Technology | Train champion of COGNOS to | Technology Dept. | $1,500 Technology | Nov. 2002
software. (DO) |  | technically manage software, |  | Budget
develop data cubes and reports.
3 Develop cubes and sort routines. (PLAN) | Technology, Asst. | Work with stakeholders to devel- | Technology, Asst. |  | Dec. 2002
| Supt. ISI | op necessary data elements and | Supt. ISI
drill downs for data cubes.
3 Upgrade server for COGNOS software. (DO) |  | Provide a computer that will | Technology | $6,000 Technology | April 2003
|  | have enough computing capabi- |  | Budget/State grant
lity to allow quick turnaround to
users.
3 Develop standard reports. (DO) | Administrators | Utilizing input from stakeholders | Technology, |  | May 2003
|  | develop standard reports for | Principals,
|  | production. (ISAT, ITBS). | Cabinet
3 Train administrators on COGNOS software. | Administrators | Provide user training on stan- | Technology |  | Aug. 2003
(DO) |  | dard reports. Use of disaggrega-
tion/aggregation of data.
 Refinement of data cubes/sorts/reports. | Administrators | Evaluation of system after initial | Technology, |  | Jan. 2004
(STUDY) |  | use by Administrators. Make | Principals,
|  | adjustments as needed based on | Cabinet
input and feedback.
Updated 11/4/03 |  |  |  |  | 3C2 - 1
District Improvement Action Plan Strategy 3C2

## 3C3
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3C.3: Refine, deploy and evaluate a management system for monitoring the proper utilization of allocated funds
and enhancing data reporting systems providing timely and effective analysis of programs and resources.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Accurate, timely and pertinent data entry. | Employees
 Review and modify data elements to be |  | Currently data entry is not con- | Tech. Director, |  | March 2003
entered into computer software. (STUDY) |  | sistent across district. Review | Asst. Supt. ISI, |  | Jan. 2004
|  | requirements and determine those | Comptroller
elements necessary for entry.
 Present data elements to Principals. (STUDY) |  | Provide a report to Principals of | Tech. Director, |  | April 2003
|  | data elements to be collected. | Asst. Supt. ISI, |  | March 2004
|  | Receive feedback from Principals. | Comptroller
 Refinement of data elements from feedback. |  | Update data element list based on | Tech. Director, |  | April 2003
(ACT) |  | feedback from stakeholders. | Asst. Supt. ISI, |  | June 2004
Comptroller
 Develop procedures for entering data. (PLAN) |  | Standard operating procedures | Technology |  | May 2003
|  | enhance consistency and |  |  | July 2004
accuracy of data.
 Develop training program. (PLAN) |  | Well planned training will pro- | Tech. Director, |  | July 2003
|  | vide a tool to deploy data entry | Asst. Supt. ISI, |  | July 2004
|  | procedures. | Comptroller
 Provide training on data element entry. (DO) |  | Establish expectations and | Tech. Director, |  | Aug. 2003
|  | requirements for data element | Asst. Supt. ISI, |  | Aug. 2004
|  | entry and training on how to | Comptroller
accomplish the entry consistently
and accurately.
3C3 - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Provide additional training and mentoring. |  | Based on feedback from users, | Technology |  | Aug. - Dec.
(DO) |  | refine system. |  |  | 2003 2004
 Review and revise data elements. (STUDY) |  |  | Tech. Director, |  | Jan. 2004
|  |  | Asst. Supt. ISI, |  | Jan. 2005
Comptroller
Updated 11/4/03 |  |  |  |  | 3C3 - 2
District Improvement Action Plan Strategy 3C3

## 3D
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3D: Refine, deploy and evaluate a long-range plan for the use of district facilities including boundary designations
and transfer policies.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Establish facilities committee. (PLAN) | All stakeholders | Receive community input on | Board of Education | $2,000 general | August 12,
|  | long-term future of district |  | operating funds | Oct. 28, 2003
facilities.
 Conduct first meeting of committee. (PLAN) |  | Select chairperson, establish | Superintendent |  | Sept. 4, 2003
|  | guidelines, determine informa- |  |  | Nov. 24, '03
tion needs, establish timeline.
 Conduct committee meetings. (PLAN) |  | Review data about buildings, | Committee |  | Sept.-Dec.'03
|  | consider age/usefulness, consi- |  |  | Dec. '03-
|  | der alternatives, review future |  |  | March '04
direction of educational offerings.
 Draft report of recommendations. (DO) |  | Short-term and long-term, include | Committee |  | Dec. 31, '03
|  | funding mechanism, list assump- |  |  | Mar. 31, '04
tions used.
 Report to Board of Education. (DO) |  | Deliver the report to the Board of | Committee |  | Jan. 13, '04
|  | Education. |  |  | Apr. 13, '04
 Board reviews and discusses report. (STUDY) |  | Provide Board sufficient time to | Board of Education |  | Jan. 27, '04
|  | review report. |  |  | Apr. 27, '04
 Development of action plan to implement |  | Board accepts short-term plans. | Superintendent, |  | Feb. 10, '04
short-term items from report. (ACT) |  | Administration develops plans | Comptroller |  | May 11, '04
for implementation.
 Hold meetings with public to present facili- | Community | Inform stakeholders and solicit | Superintendent |  | March 2004
ties report of Committee and receive feedback. |  | feedback on long-range plan. |  |  | June 2004
(STUDY)
3D - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Development of action plans for long-term |  | Development of action plans will | Superintendent, |  | May 2004
facilities plan incorporating Committee report |  | drive the organization to systema- | Cabinet |  | June 2004
and feedback from public meetings. (ACT) |  | tically implement the recommen-
dations of the Committee and
Community.
 Present long-term facilities action plan to |  | Allow Board and public to | Superintendent |  | June 2004
Board. (STUDY) |  | become familiar with the action |  |  | Aug. 2004
plans.
 Modify plan to incorporate changes desired |  | Take feedback from Board/ | Superintendent, |  | July 2004
by Board. (ACT) |  | Community and revise plans. | Cabinet |  | Sept. 2004
 Hold public meetings to present long-term |  | Deploy throughout all stake- | Superintendent, |  | Aug. 2004
facilities action plans. (ACT) |  | holder groups. | Cabinet |  | Oct. 2004
Updated 11/4/03 |  |  |  |  | 3D - 2
District Improvement Action Plan Strategy 3D

## 3E
Goal 3: Build and maintain an excellent educational support system that focuses resources and effort on student achievement.
Strategy 3E: Refine, deploy and evaluate a system of student support within a positive school environment that enhances each
student's ability to succeed in the classroom.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Meet with administrators, counselors, SAP | PreK-12 | It is crucial that all schools ensure a | Asst. Supt. for | Title IV, Title II | May 1, 2003
(Student Assistance Program) team to consider | Students, | safe and secure learning environment. | Pupil Personnel |  | Feb. 1, 2004
areas of concern (data review) or patterns of | Teachers, | This goes beyond physical safety and | Services
problems (PLAN) | Administrators | security. All students need a support-
ive, student-centered environment to
obtain maximum academic achieve-
ment potential.
 Establish a solution-focused building intervention |  |  | Building |  | Sept. 1, 2003
team (Title I, Special Education, Student Assistance |  |  | Principals |  | Feb. 1, 2004
Program) to address behavior, academic, and social
need of identified students. (PLAN)
 Develop goals/targets. (PLAN) |  |  |  |  | Oct. 1, 2003
Mar. 15, '04
 Identify training/support needs for teachers, |  |  |  |  | Dec. 1, 2003
paraprofessionals, parents, students. (PLAN)
3 Provide necessary training (i.e. "No Bullying," |  |  |  |  | Feb. 1, 2003
Non-Violence Crisis Intervention, Aggression |  |  |  |  | Ongoing
Replacement Training). (DO)
 Design systems of support (i.e. district |  |  |  |  | Apr. 1, 2004
networking facilitator time). (DO)
 Collect data and build on success. (STUDY) |  |  |  |  | June 1, 2004
 Evaluate and report to principals and Board of |  |  |  |  | Aug. 1, 2004
Education. (STUDY)
 Refine program utilizing data and feedback. (ACT) |  |  |  |  | Aug. 1, 2004
Updated 11/5/03 |  |  |  |  | 3E - 1
District Improvement Action Plan Strategy 3E

## 4A
Goal 4: Recruit, develop, and maintain a work force that best meets the needs of our students and reflects the diverse makeup of
the student population.
Strategy 4A: Refine, deploy, and evaluate a program for employee recruitment.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Meet with building/central office administra- | All RISD 41 | Information collected is used to | Asst. Supt. for | N/A | January
tors to determine annual staffing needs. (PLAN) | Administrators | assess certified and non-certified | Human Resources |  | 2003-08
| and Cabinet. | needs.
 Determine Full-Time Equivalent (FTE) rates |  | Establish teacher/student rates. | Comptroller | N/A | February
for RISD 41. (DO) |  |  |  |  | 2003-08
3 Anticipated teacher/administrative vacancies | RISD 41 certified | Determine preliminary teacher/ | Asst. Supt. for | N/A | February
are determined. (DO) | staff, and build- | administrative vacancies for the | Human Resources |  | 2003-08
| ing/central office | purpose of recruitment.
administrators.
3 Participate in local/regional Teacher/ | Local /regional | Recruitment of certified staff and | Asst. Supt. for | 200 | February
Administrator Recruitment Fairs. (DO) | colleges and uni- | administrators. | Human Resources | Recruitment Budget | 2003-08
versities, profes-
sional associations
and educators.
3 Utilize local/regional recruiting network. | Assist. Supt./HR. | Recruitment of certified staff and | Asst. Supt. for | N/A | September
(DO) |  | administrators. | Human Resources |  | 2003-08
3 Implement employment practices that provide | Local/regional | Increase the number of certified | Asst. Supt. for | N/A | July
greater employment access for minority | media, school/ | and non-certified minority staff. | Human Resources |  | 2003-08
candidates. (DO) | community stake-
holders, other.
3 Employ traditional and non-traditional |  | Promotes greater access to | Human Resources | 2000 | July
recruitment advertisement. (DO) |  | potential employees. | Department | Recruitment Budget | 2003-08
3 Review and screen potential candidate | RISD 41 staff and | Identify qualified candidates that | Human Resources | N/A | Ongoing
credentials. (STUDY) | external candidates. | might meet the needs of RISD 41. | Department |  | 2003-08
4A - 1
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Review the recruiting process. (STUDY) |  | Collect and review data to deter- |  |  | July
|  | mine the effectiveness of the |  |  | 2003-08
recruiting process (i.e. teacher
surveys, evaluations and exit
questionnaires).
3 Make changes needed to improve the recruit- |  | Utilize collected survey, and |  |  | July
ment process. (ACT) |  | evaluation data to improve |  |  | 2003-08
recruitment processes.
Updated 11/4/03 |  |  |  |  | 4A - 2
District Improvement Action Plan Strategy 4A

## 4B
Goal 4: Recruit, develop, and maintain a work force that best meets the needs of our students and reflects the diverse makeup of
the student population.
Strategy 4B: Refine, deploy, and evaluate a program for employee orientation.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Organize the Certified, Non-Certified, and | All new certified | Provide an over view of RISD 41 | Asst. Supt. for | N/A | April
Miscellaneous Employee Orientation Day and | staff. | processes and procedures. | Human Resources |  | 2003-08
Luncheon. (PLAN)
3 Develop a Certified, Non-Certified, and |  | Provide input regarding informa- | Asst. Supt. for | N/A | July
Miscellaneous Employee Orientation Day |  | tion that is presented during the | Human Resources |  | 2003-08
Agenda. (PLAN) |  | orientation day. | and Cabinet
3 Select location for the orientation day. (DO) |  | Reserve a location that can | Asst. Supt. for | 200 | July
|  | accommodate equipment/materi- | Human Resources |  | 2003-08
|  | als, staff, and luncheon. | and HR Dept.
3 Mail invitations. (DO) |  | Invite all stakeholders associated | Asst. Supt. for | 400 | July
|  | with the New Teacher Orientation | Human Resources |  | 2003-08
|  | Day and Luncheon. | and HR Dept.
3 Conduct Orientation Day. (DO) |  | Enact agenda for Orientation Day. | Asst. Supt. for |  | August
|  |  | Human Resources |  | 2003-08
3 Use Plus/Delta to survey new staff. (STUDY) |  | Collect information regarding staff | Asst. Supt. for | N/A | August
|  | perceptions of orientation day | Human Resources |  | 2003-08
activities/luncheon.
3 Review/evaluate Plus/Delta data. (ACT) |  | Utilize Plus/Delta data to improve | Asst. Supt. for | N/A | August
|  | future orientation day/luncheons. | Human Resources |  | 2003-08
Updated 11/4/03 |  |  |  |  | 4B - 1
District Improvement Action Plan Strategy 4B

## 4C1
Goal 4: Recruit, develop, and maintain a work force that best meets the needs of our students and reflects the diverse makeup of
the student population.
Strategy 4C1: Refine, deploy, and evaluate a program for employee development.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
 Develop and implement a non-certified/ | RISD 41 certified, | Provide training and support in | Asst. Supt. for | TBD | September
miscellaneous and certified professional | non-certified and | an effort to improve knowledge | Human Resources |  | 2003-08
development plan. (PLAN) | miscellaneous staff. | and skill related to job duties and | and Cabinet
responsibilities.
 Cabinet members (Assistant Superintendents, |  | Develop specific goals to provide | Asst. Supt. for |  | January
Comptroller, Title I Director) submit annual |  | training for staff and to determine | Human Resources |  | 2003-08
staff development proposal s to the Assistant |  | priority and cost related to | and Cabinet
Superintendent for Human Resources. (DO) |  | proposal.
 Utilize Plus/Delta and professional develop- |  | Collect staff input regarding prof- | Asst. Supt. for | N/A | Ongoing
ment surveys to evaluate professional develop- |  | essional development activities. | Human Resources |  | 2003-08
ment activities. (STUDY) |  |  | and Asst. Supt. for
Instruction
 Evaluate Plus/Delta and survey data. (ACT) |  | Review data in an effort to deter- | Asst. Supt. for | N/A | Ongoing
|  | mine staff interest, attendance, | Human Resources |  | 2003-08
|  | and effectiveness of professional | and Asst. Supt. for
|  | development activities. | Instruction
Updated 11/4/03 |  |  |  |  | 4C1 - 1
District Improvement Action Plan Strategy 4C1

## 4C2
Goal 4: Recruit, develop, and maintain a work force that best meets the needs of our students and reflects the diverse makeup of
the student population.
Strategy 4C2: Refine, deploy, and evaluate a program for employee development.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Develop and implement a Teacher Induction/ | RISD 41 New | Provide support and consultation | Asst. Supt. for | N/A | September
Mentoring Program. (PLAN) | Teachers | in an effort to improve teaching | Human Resources |  | 2001-02
|  | effectiveness. | and other certified
staff
3 Provide Charlotte Danielson Teacher | RISD 41 certified | Provide effective teaching instruc- | Asst. Supt. for | 10000 | June 2002
Mentoring Program Training. (DO) | staff members with | tion in an effort to improve | Human Resources | (training and
| a minimum of 2 | teaching/learning. |  | materials)
years teaching
experience.
3 Select and assign Teacher Mentors. (DO) | RISD 41 experienced | Match Teacher Mentors and New | Asst. Supt. for | N/A | August
| and new teachers. | teachers for instructional purposes. | Human Resources |  | 2002
and Principals
3 Conduct quarterly Mentor meeting. (DO) | RISD 41 Teacher | Provide information to Mentors | Asst. Supt. for | 500 | Aug., Nov.,
| Mentors | regarding duties/responsibilities, | Human Resources | Annual Mentor | Feb., May
|  | curriculum, and compensation. |  | Stipend | 2003-08
3 Implement Plus/Delta, New Teacher and | RISD 41 New | Collect Plus/Delta and pre-and- | Asst. Supt. for | N/A | Sept. &June
Teacher Mentor surveys. (DO) | Teachers and | post survey data regarding staff | Human Resources |  | 2003-08
| Mentors | expectation, needs, and program
effectiveness.
3 Evaluate Induction/Mentoring program. |  | Review Plus/Delta and pre-and- |  |  | July
(STUDY) |  | post survey data to determine |  |  | 2003-08
program effectiveness.
3 Utilize evaluation data to improve the |  | Data will be used for continuous |  |  | July
effectiveness of the Teacher Mentor program. |  | improvements. |  |  | 2003-08
(ACT)
Updated 11/4/03 |  |  |  |  | 4C2 - 1
District Improvement Action Plan Strategy 4C2

## 4D
Goal 4: Recruit, develop, and maintain a work force that best meets the needs of our students and reflects the diverse makeup of
the student population.
Strategy 4D: Refine, deploy, and evaluate a program for employee evaluation.
Provide a detailed action plan that describes how the District will achieve the strategy and measure its impact on student achievement.
All action plans will be evaluated on a quarterly basis with updates provided for the Board of Education twice yearly.
| Targeted |  | Person(s) | Funding Source | Action Plan
Description of Proposed Action/Activity | Population | Research/Rationale For Activity | Responsible | & Estimated Cost | Timeline
3 Plan the implementation of a RISD 41 | Certified, non- | Review time-lines and procedures | RISD41 | N/A | May
evaluation process. (PLAN) | certified and misc- | for staff evaluations. | Administrators |  | 2003-08
| ellaneous employ- |  | and supervisors
ees, Assist. Princi-
pals and Deans
3 Implement and monitor prescribed evaluation | Certified, non- | Assessment of staff performance | Asst. Supt. for | N/A | June
instruments and processes as set forth in the | certified and misc- | related to job duties and responsi- | Human Resources |  | 2003-08
district’s collective bargaining agreements. (DO) | ellaneous employ- | bilities.
ees, Assist. Princi-
pals and Deans
3 Review all employee evaluation instruments. |  | Monitor and assess quality of |  | N/A | Ongoing
(STUDY) |  | prepared evaluation instruments. |  |  | 2003-08
 Report administrative evaluation progress to |  | Provide input to the Superinten- |  | N/A | March
Superintendent of Schools through input in the |  | dent of Schools related to depart- |  |  | 2003-08
Principal instrument. (STUDY-ACT) |  | mental duties and responsibilities.
3 Utilize information collected from the review |  | Provide feedback and recommend- | Asst. Supt. for | N/A | Ongoing
of staff evaluations to inform administrator/ |  | ations to Principals and super- | Human Resources |  | 2003-08
supervisor regarding evaluation improvements. |  | visors regarding needed improve-
(ACT) |  | ments in the evaluation process.
Updated 11/4/03 |  |  |  |  | 4D - 1
District Improvement Action Plan Strategy 4D