## Master Schedule
[6 empty] | Chancellor | Provost/VCs
STATE BUDGETS:
Continuation Budget Departmentalization (State Operating Budget)
|  | 1 | Financial Planning & Budgets sends to the Chancellor, Provost and Vice Chancellors |  |  |  |  | 2004-03-05
instructions concerning distribution of departmental continuation budgets.
|  | 2 | The Provost and Vice Chancellors submit completed departmental continuation budgets |  |  |  | b | 2004-04-23
to Financial Planning & Budgets.
|  | 3 | Financial Planning & Budgets provides copies of the new year departmental continuation |  |  |  |  | 2004-05-28
budgets to account holders.
Change/Expansion Budget (Enrollment, & Other)
|  | 1 | Financial Planning and Budgets provides an estimate of the new year Enrollment Change |  |  |  |  | 2004-03-22
Budget to the Chancellor, Provost, and Vice Chancellors.
|  | 2 | The Provost and Vice Chancellors submit requests for allocation of enrollment change |  |  |  | b | 2004-04-19
budget funds to the Chancellor.
|  | 3 | The Chancellor makes preliminary allocation decisions as a result of enrollment changes |  |  | b |  | 2004-05-23
|  | 4 | Financial Planning & Budgets receives the new year Change Budget Instructions from |  |  |  |  | 2004-07-12
the Office of the President.
|  | 5 | The Chancellor makes final allocation decisions for the Change Budget. |  |  | b |  | 2004-07-19
|  | 6 | The Provost and Vice Chancellors submit completed new year Change Budget detail |  |  |  | b | 2004-07-26
schedules to Financial Planning & Budgets based on those allocation decisions.
|  | 7 | Financial Planning & Budgets completes and assembles the final new year Change |  |  |  |  | 2004-07-28
Budget documents.
|  | 8 | The Chancellor approves and submits to the Office of the President the final new year |  |  | b |  | 2004-07-30
Change Budget documents.
Plan for the Use of the Prior Year Carryforward
|  | 1 | Financial Planning & Budgets sends to the Chancellor, Provost and Vice Chancellors |  |  |  |  | 2004-05-14
instructions for requesting undesignated carryforward funds from the previous year and
specific budget lines for previously approved carryforward items.
|  | 2 | The Provost and Vice Chancellors submit requests (including budget lines) for |  |  |  | b | 2004-06-25
undesignated carryforward funds to Financial Planning & Budgets.
|  | 3 | Financial Planning & Budgets summarizes the requests and submits them to the |  |  |  |  | 2004-06-28
Chancellor for allocation.
|  | 4 | The Chancellor makes allocation decisions of the previous year's carryforward funds. |  |  | b |  | 2004-07-08
|  | 5 | Financial Planning & Budgets prepares and the Chancellor transmits the planned use of |  |  | b |  | 2004-07-12
carryforward funds to the President for approval.
Plan for the Use of the New Year's Lapsed Salaries
|  | 1 | Financial Planning & Budgets sends to the Chancellor, Provost and Vice Chancellors |  |  |  |  | 2004-06-12
instructions for projecting the amount of and use of lapsed salaries for the new year.
|  | 2 | The Provost and Vice Chancellors submit their plans (including use and budget lines) for |  |  |  | b | 2004-06-26
lapsed salary funds to Financial Planning & Budgets.
|  | 3 | Financial Planning & Budgets integrates the Reversion Plan use of lapsed salaries with |  |  | b |  | 2004-07-30
departmental plans and the Chancellor transmits the plan for the use of lapsed salaries to
the President for approval.
New Year Reversion Plan
|  | 1 | Financial Planning & Budgets prepares a preliminary estimate of the total reversion to be |  |  |  |  | 2004-09-10
achieved. This estimate takes into consideration such factors as historical reversion
information, budget changes being considered or made by the legislature, projected
enrollment, and unbudgeted items.
|  | 2 | The Vice Chancellor for Business Affairs reviews the preliminary estimate with the |  |  |  |  | 2004-09-10
Chancellor to identify any additional factors desired to be reflected in the plan, and to
obtain the Chancellor's preliminary internal allocations of the reversion.
|  | 3 | Financial Planning & Budgets revises the preliminary reversion plan as necessary and |  |  |  |  | 2004-09-13
submits it to the Chancellor, Provost and Vice Chancellors for review and discussion.
|  | 4 | The Chancellor, after discussion with the Provost and Vice Chancellors, and |  |  | b |  | 2004-09-14
consultation with the Vice Chancellor for Business Affairs, makes final decisions
relative to the total reversion plan and the sources for covering the total reversion.
|  | 5 | Financial Planning & Budgets takes the appropriate budget actions to set aside the |  |  |  |  | 2004-09-21
sources for covering the reversion and to make necessary budget adjustments.
|  | 6 | The Reversion Plan is reviewed based on actual year to date information. |  |  |  |  | 2005-02-14
|  | 7 | The Chancellor makes any additional allocation decisions based on the revised Reversion |  |  | b |  | 2005-03-14
Plan.
Campus Based Tuition Increase
|  | 1 | The Chancellor appoints the Tuition Study Task Force to examine issues related to tuition |  |  | b |  | Completed
and recommend to Chancellor whether a Campus Based Tuition Increase should be requested.
|  | 2 | The Task Force recommends if an increase should be requested, and if so, the amount and uses. |  |  |  |  | Completed
|  | 4 | If accepted, the Chancellor presents the recommendations to the Board of Trustees. |  |  | b |  | Completed
|  | 5 | The Chancellor transmits the Trustee-approved recommendation to the President. |  |  | b |  | Completed
|  | 6 | The President presents the recommendation to the Board of Governors for approval. |  |  |  |  | 2004-02-13
INSTITUTIONAL BUDGETS:
Overhead Cost Recovery (Overhead Receipts)
|  | 1 | Contracts & Grant Accounting provides an estimate of indirect cost receipts for the fiscal |  |  |  |  | 2004-04-12
current year to Academic Affairs. (Budgets will be based on estimated rather than actual
figures. Differences between actual and estimated are reflected in the following year
budget.)
|  | 2 | Financial Planning & Budgets sends the Provost analyses and instructions concerning the |  |  |  |  | 2004-04-16
distribution of the Overhead Receipts budget. (Principal Investigators and Departments
will be instructed to prepare detail budgets.)
|  | 3 | The Provost submits the Overhead Receipts budget to the Chancellor for approval of the |  |  |  | b | 2004-05-07
summary budget requests.
|  | 4 | The Chancellor approves the summary budgets. |  |  | b |  | 2004-05-11
|  | 5 | The Provost submits departmental budgets to Financial Planning & Budgets. |  |  |  | b | 2004-06-10
Student Fees (including Health Services)
Rates (Regular Term)
|  | 1 | The Provost and Vice Chancellors forward to the Vice Chancellor for Business Affairs |  |  |  | b | Completed
recommendations for changes in fee rates.
|  | 2 | Financial Planning & Budgets projects preliminary fee revenues based on the projected |  |  |  |  | Completed
enrollment and cost increases.
|  | 3 | Financial Planning & Budgets receives instructions from Office of the President for |  |  |  |  | Completed
preparation and submittal of fee proposals.
|  | 4 | The fee proposals are presented to the Student Fee Advisory committee chaired by the |  |  |  | b | Completed
VC for Student Affairs.
|  | 5 | The Provost and Vice Chancellors forward to the Vice Chancellor for Business Affairs |  |  |  | b | Completed
requests for changes in Miscellaneous Service Charges for the Chancellor's approval.
|  | 6 | The advisory committee forwards its fee proposals to the Chancellor. |  |  |  | b | Completed
|  | 7 | The Chancellor reviews the fee recommendations with the Provost and VCs. |  |  | b | b | Completed
|  | 8 | The VCBA submits preliminary rate proposals to OP pending Trustee approval. |  |  |  |  | N/A
|  | 9 | The Chancellor presents the fee proposals to the Board of Trustees. |  |  | b |  | Completed
|  | 10 | The Board of Trustees approves the fees for the next fiscal year: |  |  |  |  | Completed
- Certify the need for each fee and that any increase has been thoroughly reviewed.
- Affirm that the type, level, and extent of services covered by each fee are appropriate
for UNCG, and that the services provided are commensurate with the fee charged.
- Certify that the alternative funding has been sought but is unavailable.
|  | 11 | The Chancellor submits the fee proposals to the Board of Governors and |  |  | b |  | Completed
Miscellaneous Service Charges to the President.
Rates (Summer Term 2004)
|  | 1 | Financial Planning & Budgets, in coordination with the Director of Summer School and the |  |  | b | b | Completed
Provost, prepares and submits to Office of the President, after approval of the Chancellor,
the summer term tuition rates and a proration of student fees.
Budgets
|  | 1 | Financial Planning & Budgets requests new year budget proposals from the Health Center |  |  |  |  | Completed
based on projected enrollment and proposed rates.
|  | 2 | The Vice Chancellor for Student Affairs submits the Health Services budget utilizing the |  |  |  | b | 2004-02-19
approved rates to Financial Planning and Budgets.
|  | 3 | The Chancellor makes preliminary decisions relative to the total amount of student fee |  |  | b |  | 2004-02-27
revenues to be allocated to the Provost and each Vice Chancellor.
|  | 4 | The Vice Chancellor for Business Affairs prepares and submits to the appropriate Vice |  |  |  |  | 2004-03-01
Chancellors/Provost a formatted worksheet for completion of their budgets by activity
(account) and object.
|  | 5 | The Provost and Vice Chancellors submit to Financial Planning & Budgets the worksheet
|  |  | of their budgets by activity (account) and object. |  |  |  | b | 2004-04-19
Food Services & Housing Services
|  | 1 | Preliminary budgets are submitted to Financial Planning & Budget using proposed rates. |  |  |  |  | Completed
|  | 2 | Financial Planning & Budgets reviews the proposed budgets for reasonableness and |  |  |  |  | Completed
compliance with bond covenants and makes budget recommendation for adoption or
modification.
|  | 3 | Food and Housing rates for the next fiscal year are proposed and approved by the Vice |  |  |  | b | Completed
Chancellor for Business Affairs and the Vice Chancellor for Student Affairs.
|  | 4 | Food & Housing rates are approved by the Chancellor for the next fiscal year. |  |  | b |  | Completed
|  | 5 | If applicable, Housing & Food Services submits revised detail budgets utilizing the |  |  |  |  | N/A
approved rates to Financial Planning & Budgets (same as #1 with applicable
modifications).
|  | 6 | Financial Planning & Budgets reviews the revised budgets for reasonableness and if |  |  |  |  | N/A
applicable, makes budget recommendation to Vice Chancellor Business Affairs for adoption.
Other Auxiliary Operations
|  | 1 | Financial Planning & Budgets updates position information and workbooks for the |  |  |  |  | Completed
preparation of detail budgets for auxiliary operations (Parking, Postal, Tel Services etc.).
|  | 2 | The parties responsible for the operating budgets submit detail budgets for the new year
to Financial Planning & Budgets.
|  |  |  | Parking & Traffic |  |  |  | Completed
|  |  |  | Telephone Services |  |  |  | 2004-02-06
|  |  |  | Motor Pool |  |  |  | 2004-01-26
|  |  |  | Scholarship Supporting Operations |  |  |  | 2004-02-09
|  |  |  | All other auxiliary operations |  |  |  | 2004-03-06
|  | 3 | Financial Planning & Budgets reviews the detail budgets for reasonableness and submits
them to the Vice Chancellor for Business Affairs for approval.
|  |  |  | Parking & Traffic |  |  |  | 2004-01-15
|  |  |  | Telephone Services |  |  |  | 2004-03-05
|  |  |  | Motor Pool |  |  |  | 2004-02-20
|  |  |  | Scholarship Supporting Operations |  |  |  | 2004-02-20
|  |  |  | All other auxiliary operations |  |  |  | 2004-03-30
Other Institutional Budgets
|  | 1 | Financial Planning & Budgets sends to the appropriate responsible parties instructions for |  |  |  |  | 2004-04-09
the preparation of detail budgets for other institutional operations (Music Camp, restricted
endowment income accounts, Annual Programs, Child Care Center, etc.).
|  | 2 | The parties responsible for the operating budgets submit detail budgets for the new year to |  |  |  | b | 2004-05-17
Financial Planning & Budgets.
|  | 3 | Financial Planning & Budgets reviews the detail budgets for reasonableness and prepares |  |  |  |  | 2004-05-31
Original Budget for new year on FRS.
Unrestricted Gifts and Investment Income
|  | 1 | The Vice Chancellor for Business Affairs distributes instructions for preparing and |  |  |  |  | 2004-03-12
submitting the new year Unrestricted Gifts & Investment Income budget requests.
|  | 2 | The Vice Chancellor for Business Affairs provides the Chancellor with projected income |  |  |  |  | 2004-05-17
from unrestricted and restricted current funds for UNCG and affiliated foundations.
|  | 3 | The Provost and Vice Chancellors submit Unrestricted Gifts & Investment Income Budget |  |  |  | b | 2004-05-24
Requests for the new year to Financial Planning & Budgets.
|  | 4 | The Chancellor allocates Unrestricted Gifts & Investment Income. |  |  | b |  | 2004-06-04
EPA SALARY INCREASES - BD 119
|  | 1 | Financial Planning & Budgets provides the Chancellor with an analysis of salary |  |  |  |  | 2004-07-09
increment funds available for EPA salary increases.
|  | 2 | Academic Affairs provides instructions and forms for use by the Provost, Vice Chancellors |  |  |  | b | 2004-07-16
Vice Chancellors, and Deans/Directors in awarding salary increases.
|  | 3 | The Chancellor submits salary increase recommendations for Senior Administrative |  |  | b |  | 2004-07-28
Officers to the Trustees and report on these salaries to the Office of the President.
|  | 4 | The Chancellor submits to the Office of the President: recommended salary increases in |  |  | b |  | 2004-07-28
excess of 15% and Point of Reference maximum exceptions.
|  | 5 | Financial Planning & Budgets completes the BD 119 and, after the Chancellor's approval, |  |  | b |  | 2004-08-13
submits it to the Office of the President.
2005-07 BIENNIUM:
CONTINUATION BUDGETS:
|  | 1 | Financial Planning & Budgets receives instructions from OSBM for preparation and |  |  |  |  | 2004-07-01
submission of the 2005-07 Biennial Continuation budget.
|  | 2 | Financial Planning & Budgets receives instructions from the Office of the President for |  |  |  |  | 2004-07-15
preparation and submission of the 2005-07 Biennial Continuation Budget.
|  | 3 | Supporting information is received from divisions where changes are allowed by OSBM to |  |  |  | b | 2004-08-16
the Continuation Budget (Library Books, Accreditation, etc.)
|  | 4 | The Chancellor formally transmits the Continuation Budget package to OP and Financial |  |  | b |  | 2004-09-09
Planning & Budgets submits Worksheets I, II to OSBM
EXPANSION BUDGETS:
This schedule assumes no significant undesignated Expansion funds will be received. If
UNCG expects to receive other funds, preliminary steps will need to be implemented to
solicit requests, approve funding based on estimated funding, prepare detailed requests,
submit to OP. These steps, due to their time requirements, would need to be
commenced in early summer.
|  | 1 | Financial Planning & Budgets receives instructions from the Office of the President. |  |  |  |  | 2004-04-02
|  | 2 | The Chancellor allocates any cross-divisional funds that are received. |  |  | b |  | 2004-07-01
|  | 3 | The Chancellor approves and submits to the Office of the President the final new Biennial |  |  | b |  | 2004-08-16
Expansion Budget Requests.
Transformation and Change
|  |  |  | Intellectual Capital Formation |  |  |  | 2004-05-15
|  |  |  | Creation and Transfer of Knowledge |  |  |  | 2004-05-15
K-16 Initiatives
|  |  |  | Internationalization |  |  |  | 2004-05-15
|  | 5 | The Chancellor approves and submits to the Office of the President the new Biennium |  |  | b |  | 2004-09-11
enrollment projections.
CAPITAL IMPROVEMENT REQUESTS:
|  | 1 | Instructions for preparing cost estimates (Form OC25) for Capital Improvement Requests for |  |  |  |  | 2005-10-29
the 2005-07 Biennium are received from UNC Office of the President.
|  | 2 | The University Planning Council reviews proposed projects and endorses the CI Project |  |  |  |  | 2005-12-06
Requests.
|  | 3 | The VCBA submits cost Estimates for capital projects to the Office of the President.
|  |  | • | 2005-07 Long Session Request |  |  |  | 2003-12-10
|  |  |  | - | Appropriated CI Projects
|  |  |  | - | Self Liquidating CI Projects
|  |  |  | - | State Funded R&R Projects
|  |  | • | 2004-05 Short Session Request |  |  |  | 2004-03-01
|  |  |  | - | CI Projects
|  | 4 | The VCBA submits land acquisition request to the Office of the President. |  |  |  |  | 2004-01-11
|  | 5 | Instructions for preparing Capital Improvement Requests (Budget Memorandum #3) and |  |  |  |  | 2004-06-12
Building Reserves (Budget Memorandum #4) for the 2005-07 Biennium are received from
UNC Office of the President.
|  | 6 | The Chancellor approves priorities for the 2005-07 Biennium, and the VCBA submits |  |  | b |  | 2004-08-01
Capital Requests to UNC Office of the President.