## Sample Budget Form
Itemize each expenditure or match value under Grant, Cash Match or In-kind Match categories | Detailed Explanation of Expenditures and Match Values | Grant Funding | Cash Match | In-Kind Match
Component 1: Conduct a street tree inventrory and prepare a management plan for downtown business district and old town neighborhood.
Grant Funding
Consultant fee for inventory and plan | estimated by phone quotes from 2 urban forestry consultants | 5500
Printing inventory report & management plan | 50 copies @ $5.00 | 250
Inventory software | Canopy software - Natural Path Forestry Consultants | 2600
Cash Match
Clip Boards & inventory supplies | $100 estimated |  | 100
In-Kind Match
Tree Board volunteers - data collection | 6 hrs/week @ $15/hr for 3 weeks X 6 volunteers |  |  | 1620
Asst. Parks Dir., David Meadowlark | Project admin. & volunteer coord.10 hrs/week @ $23/hr for 4 weeks |  |  | 920
Plat & street maps by engineering dept. | 7 sets @ $17/set |  |  | 119
Vehicle mileage - tree board volunteers | 200 miles @ $.345/mi. estimated |  |  | 69
| Subtotals | 8350 | 100 | 2728
Component 2: Prepare first draft of municipal tree conservation and landscape ordinance.
Grant Funding
Reference books | 2 copies - U.S. Landscape Ordinances, Abbey @ $50 | 100
| 2 copies - Tree Conservation Ordinances, APA @ $40 | 80
Cash Match
None expected
In-Kind Match
Town Planner, Joe Johnson, ASLA | 80 hrs research and preliminary draft @ $35/hr |  |  | 2800
Tree Board volunteers - research/review samples | 8 hrs/month @ $15/hr for 4 months X 8 members |  |  | 3840
Town Engineer, Fred Bridge | 12 hrs review preliminary draft @ $35/hr |  |  | 420
Town Attorney, Carson Spivey | 12 hrs review preliminary draft @ $45/hr |  |  | 540
Office Assistant - Planning Dept., Karen Stover | 16hrs/month @ $10/hr for 4 months to assist Tree Bd. & Planning Dir. |  |  | 640
| Subtotals | 180 | 0 | 8240
| TOTALS | 8530 | 100 | 10968

## Budget Proposal Form
Itemize each expenditure or match value under Grant, Cash Match or In-kind Match categories | Detailed Explanation of Expenditures and Match Values | Grant Funding | Cash Match | In-Kind Match
Component 1:
Grant Funding
Cash Match
In-Kind Match
Subtotals
Component 2:
Grant Funding
Cash Match
In-Kind Match
Subtotals
TOTALS