## Sheet1
DATE | ORGINATOR | SUB CATEGORY | DESCRIPTION | COMMENTS | FSTF | BAC | BFA | BMC | Responsibility | Status | PRIORITY | RAMIFICATION | ASG Task List | MyNuLook Task List
2000-03-15 | End User Needs | Reporting | "Unrestricted Closing Balance Analysis" & "Unrestricted Closing Balance" Reports for Dean's Office (used to determine year end position of departments) |  |  |  | ACCT |  | Shelly Sorensen & Mark Steffen | Completed | HIGH
2000-01-13 | End User Needs | Implemenation Issues | 6/3 Rule (Retro Active Pay) | Revise charge/ develop implemenation plan, identify issues/problems. Team is close to final recommendations. |  |  |  | X | Christine Steggs, Jaclyn Deniston | Completed | HIGH
2000-06-05 | Data Entry |  | 9027 & 90001 adhoc query |  | X | [7 empty] | X
2000-03-07 | End User Needs | Process Improvement | Accounts Receivable Module in SAP |  | X | [6 empty] | Consolidation of billing/collection efforts for the campus/university.
2000-01-13 | End User Needs | Training | Advance Report Training (excel/export) |  |  |  |  | X
2000-04-27 | MM |  | Analyze Auto-FAX options for faxing PO's directly from SAP. |  |  |  | PURCH |  | Julie Davids |  | Low |  | Yes
2000-04-27 | MM |  | Analyze RFQ functionality within SAP |  |  |  | PURCH |  | Bill Bode |  | New Enh
2000-05-05 | BAC |  | Archiving of SAP Data |  | X
2000-01-13 | Data Entry |  | Audit Reports/Trails when employee records are decentralized (record retention, l-9 and tax forms. Need legal guidance). |  |  |  | Nancy |  | Pat Amedeo
2000-05-19 | Payroll |  | Automated Time/Attendance System | Moved to FSTF from BAC, 6/15/00 | X |  |  |  | Pat Smith | Pending
2000-03-07 | End User Needs | Implemenation Issues | Automatic Encumber Salaries within SAP (not via manual funds commitment) | Possibilities in 4.6 need to be explored. | X | [5 empty] | HIGH | Info available via NuLook but departments must reference two systems to accomplish goal. | Yes
2000-03-07 | Project Mgmt |  | Back up for Anne on Help/Suggestions requests sent via SLUGO | Blinde to follow-up with ASG--Margaret |  | X |  |  | Loren Blinde | Active
2000-03-07 | Project Mgmt |  | Back up support for Security Coordinators (Anne, Dale, Julie) |  |  | X |  |  |  | Completed |  | Process is stoped if one person is not available
2000-02-15 | Payroll |  | Benefits on one-time payments (SAP philosophy is that one-time payments are not charged for benefits. Benefits are charged to home department) |  |  |  | Data Enty & Payroll
2000-04-30 | End User Needs |  | BMC's involvement with User Group(s) / training issues / communications issues |  |  |  |  | X
2000-03-16 | End User Needs | Process Improvement | Budget or funds encumbrances over multiple fiscal years. | Document fund commitments for multiple fiscal years. |  |  |  | X
2000-04-17 | Bus Manager |  | Campus communicate operational issues with MyNuLook Team |  |  |  |  | X |  | Active
2000-06-05 | Data Entry |  | Change Register - both for PA and payroll |  | X | [7 empty] | X
2000-01-13 | Data Entry |  | Clean Up on position numbers for multiple funded appointments |  |  |  | Data Entry |  | Pat Amedeo
2000-04-27 | MM |  | Commodity Listing by Vendor |  |  |  | PURCH |  | Bill Bode |  | New Enh
2000-02-08 | HR |  | Communications to campus on Reimbursement Account Changes |  |  |  | Benefits |  | Greg Clayton
2000-03-13 | End User Needs | Other | Confidentiality at Business Center Level |  |  |  |  | X
2000-04-27 | MM |  | Configure Dangerous Goods Master for Hazardous Materials |  |  |  | PURCH |  | Bill Bode |  | New Enh
2000-04-27 | MM |  | Configure SAP for Annual Physical Inventory process |  |  |  | PURCH |  | Julie Davids |  | Low |  | Yes
2000-04-27 | MM |  | Configure Scheduling Agreements/Delivery Schedules for Stock Items |  |  |  | PURCH |  | Julie Davids |  | Low |  | Yes
2000-01-13 | Data Entry |  | Conversion Issues for Stop Pay dates for May |  |  |  | Data Entry |  | Pat Amedeo | Completed |  | Pay to ex-employees
2000-04-27 | Purchasing |  | Convert existing Procurement Card Reconciliation Process to SAP |  | X |  | PURCH |  | Bill Bode |  | New Enh
2000-03-13 | End User Needs | Implemenation Issues | Create Text Field in CO/PS Planning modules to allow depts to add text to explain a budget transfer | Requires SAP development. | X | [5 empty] | Low
2000-04-27 | MM |  | Delivery Ticket Fix: 1) Reprints always print current sell price instead of price at time of shipment. 2) Same part# cannot be listed more than once. |  |  |  | PURCH |  | Julie Davids |  | Med |  | Yes
2000-04-27 | MM |  | Delivery Ticket needed for Return/credit items |  |  |  | PURCH |  | Julie Davids |  | Med |  | Yes
2000-03-07 | End User Needs | Mac Users | Development of macro for Quick Order checks for Mac Machines | Determine the longevity of QO/QP |  |  |  | X |  |  |  |  | Yes
2000-04-27 | MM |  | Documentation of Inventory Accounting Flow |  |  |  | PURCH |  | Julie Davids |  | Med |  | Yes
2000-04-24 | Purchasing |  | EDI Ordering/Billing | Develop links for data conversion between vendors and SAP | X | [6 empty] | Streamline an existing processes u-wide
2000-01-13 | Data Entry |  | Education on completing the PAF (how to complete form, knowledge on employment status of employees in relationship to other departments) |  |  |  | Data Entry |  | Pat A & Anne |  |  | Delays in process time
2000-01-13 | End User Needs |  | Education to departments on how/when to use mynulook |  |  |  |  | X
2000-04-27 | MM |  | Electronic Shopping Catalogs via Web |  |  |  | PURCH |  | Bill Bode |  | New Enh
2000-04-27 | MM |  | Eliminate extra copies that print when printing goods receipts (5 lines = 5 copies). |  |  |  | PURCH |  | Julie Davids |  | Low |  | Yes
2000-01-13 | End User Needs | Training | FI/CO, MM & Reporting - All Departments on-line by July 1 | Charge: Identify areas not on-line; purspose of end-users group |  |  |  | X | Anne Mulligan |  | HIGH
2000-04-27 | MM |  | Fix ZM04 (Download Inventory Transactions) calculations for partial fill orders. |  |  |  | PURCH |  | Julie Davids |  | Low |  | Yes
2000-01-24 | End User Needs | Implemenation Issues | Grants matching funds tracking capability within SAP | Via Access Database (work around until rolled into SAP) BMC needs to define scope of project--moved to BMC from BAC on 6/15/00. |  |  | SP-F | X | Barb Carlson & Mark Steffen |  | HIGH | Over commitment of funds and exposure at time of audit
2000-06-05 | Data Entry |  | HR / Logged changes report |  | X |  |  |  | Pat Smith |  |  |  | X
2000-03-20 | End User Needs | Implemenation Issues | Improve Leave Accural Reports (carry forward balances & dates) | More detail is needed to understand issue: |  | X |  |  | Pat Smith | Pending
2000-01-13 | End User Needs | Implemenation Issues | Improve Data on Distribution Reports (hours worked/rate paid) |  |  |  | Payroll | X |  |  |  | Departments can not validate payroll expenses
2000-01-24 | End User Needs | Implemenation Issues | Improve Line Item Description from on Campus Suppliers | Communicated to departments on 4-12-00. Responses due back 4-26-00 |  |  | Anne |  | Anne & Barb |  | Active
2000-03-07 | End User Needs | Mac Users | Improved training/documentation for mac users | Develop SAP UNL Mac User Support Group. |  |  |  | X
2000-01-24 | End User Needs | Implemenation Issues | Inability to change line item text on framework orders and stock transfer order | Develop work around for interim period Need to develop charge |  |  |  | X | Ruby Urban |  | HIGH | Not a high priority IF departments could have a user defined field. Otherwise this item would be a high priority. | Yes
2000-03-07 | End User Needs | Implemenation Issues | Incorporate Employee Payroll Distribution information with monthly ledgers (either on Line Item Detail Report or separate report) | Need to develop charge |  |  | Proj Acct | X | Barb Clouse, Carol Cartwright |  | HIGH
2000-05-05 | BAC |  | Knowledge Transfer | Transfer of knowledge from core team to others. Moved to FTSF from BAC on 6/15/00 | X |  |  |  |  | Pending
2000-04-27 | MM |  | Ledger does not show Stock Transfer PO#/Description on ledger for returns. | Katharine Susman working on CO Substitution Rule to fix. |  |  | PURCH |  | Julie Davids |  | Med |  | Yes
2000-01-13 | End User Needs | Implemenation Issues | Lotus Notes Application Databases - (workflow for pre-SAP approval processing) |  |  |  | Info Serv | X
2000-03-13 | End User Needs | Other | Lotus Notes Upgrade to 5.0 |  |  |  | Info Serv | X
2000-01-24 | End User Needs | Implemenation Issues | Mandatory requisition for on campus purchasing |  |  |  |  | X
2000-03-07 | End User Needs | Implemenation Issues | MyNuLook does not incorporate version 2 into the Adjusted Budget. | Budget Officers to determine priority of issues/course of action required |  | X | Budget |  | Tom Becker | Pending |  | Ledger Balances of no value for Faculty to use warehouse.
2000-04-24 | HR |  | Non Resident Alien |  | X | [6 empty] | Creating excessive manual processing efforts. | Yes
2000-01-13 | NuLook |  | Non-validated financial, HR, Payroll data | BMC needs to identify critical reports used to help assess importance of this issue. Moved from BAC to BMC on 6/15/00 |  |  |  | X | Mark Steffen
2000-03-07 | Project Mgmt |  | Notification to campus on UNL Business Manager Council forum for delivery of information. | Network is in development stages to include other areas: HR, Academics, Research |  | X |  |  | Nancy Kenny | Active
2000-04-30 | End User Needs | Process Improvement | NuValues |  |  |  |  | X
2000-05-19 | End User Needs | Training | On-going Efforts for Payroll Training | Possible u-wide approach to training |  |  | X |  | Pat Smith
2000-04-30 | End User Needs |  | Personnel Activity Report (PAR) | Purpose of the report and formatting of information. | X |  |  |  |  | Completed
2000-06-05 | SP - F |  | Phantom Cost Centers / WBS Elements | Sponsored Programs walk through | X |  |  |  | Barb Carlson |  |  |  | X
2000-03-15 | End User Needs | Reporting | Plans on revolving cost objects are not accurate because the amount of carryforward is not budgeted. | Suggest entering carryforward budgets or removing plan data at the cost object level. |  |  |  | X |  |  |  | Faculty have to interupt data differently on state-aid and grant reports
2000-06-05 | Data Entry |  | Position Control |  | X | [7 empty] | X
2000-03-07 | Project Mgmt |  | Possible upgrade to 4.6 SAP GUI (hardware needs, impact on documentation, campus resources for training, required use of Internet Explorer, system functionality) |  | X | [7 empty] | Yes
2000-03-07 | End User Needs | Implemenation Issues | Post Sales on Revenue Side similar to a Funds Commitment | Dale Z possible solution for depts to post journal entry to revenue/acct rec on monthly basis. Follow up needed |  |  | Acct
2000-01-24 | End User Needs | Implemenation Issues | Pre-audit from Preliminary Payroll Run |  |  |  | Payroll | X
2000-01-24 | NuLook |  | Prioritization of their activities |  |  |  | Nancy
2000-01-24 | End User Needs | Implemenation Issues | Procurement Card: 1. Not encumbered at time of purchase, 2. Increase size of text on reconciliation |  |  |  | ACCT & PURCH | X |  |  |  | Delays in posting expense against cost object
2000-05-19 | Grants |  | Prohibiting or setting limits on amount of benefits posting to Grants | Has to be done through HR module. Sends the benefits to another cost object or limit them to a pre-defined amount and sned the overage to another cost object. Moved to FTST from BAC on 6/15/00. | X |  |  |  | Barb Carlson | Active |  | Currently SP-F and IANR have to journal entry these disallowed costs: very time consuming and required identification of the affected cost objects, monitoring and journal entries
2000-03-21 | End User Needs | Implemenation Issues | Report to depts on available balance of Work Study Funds |  |  |  | Payroll & Fin Aid
2000-05-05 | Bursar |  | Request to Bursar's Office to support project accounting. | Manage expectations |  | X |  |  | Nancy Kenny | Completed
2000-04-24 | BAC |  | Resource Issues for System Enhancements |  | X | [6 empty] | Currently core team only has time to address the fires. No time to work on enhancements.
2000-02-15 | Payroll |  | Return to bi-weekly reporting |  |  |  | Payroll |  | Nancy & Dale Wolfgram
2000-03-07 | Payroll |  | Royalty Payments (Incorrect payments and expense distribution problems) |  |  |  | Data Enty & Payroll |  | Dale W, Pat A , Peggy F & Anne |  |  | Loss of money
2000-05-19 | Payroll/Data Entry |  | SAP HR Security Issues - tools for departments and Data Entry to validate input | Provide access to view check stub to Time Clerks and Data Entry staff in business units to validate data in SAP . UNL Payroll/Data Entry Directors need different security levels. Move from BAC to BFA on 6/15/00. |  |  | Data Enty & Payroll |  | Pat Smith |  |  | Need will be greater when SAP HR Module is deployed to units/departments
2000-02-08 | Data Entry |  | SAP PA Module - Infotype 0001 Screen truncates the last character of Position and Job key column. |  |  |  | Data Entry |  | Pat Amedeo |  |  | End Users will misinterpret data
2000-06-05 | Project Mgmt |  | Add UNL contact to ASG Coordinator group |  | X |  |  |  | Loren Blinde |  |  |  | X
2000-01-13 | Data Entry |  | Separation of Employees for short periods (summer) |  |  |  | Data Entry |  | Pat Amedeo & HR Sub Group
2000-02-28 | End User Needs | Implemenation Issues | Short Text/Requisition Tracking Number from MM Module does not carry forward to FI/CO module | Katherine Susman is working on a possible work around solution. Julie will keep BAC updated on progress. |  | X |  |  | Julie Davids | Active | HIGH |  | Yes
2000-03-07 | End User Needs | Reporting | Simpler common format on SAP Reports for both cost centers and WBS (Reports to complex for Administrator/Faculty to be useful) | Design sample report layout |  |  |  | X
2000-06-05 | Data Entry |  | Staffing change report |  | X |  |  |  | Pat Smith |  |  |  | X
2000-06-05 | Payroll |  | Student FICA Verification |  | X | [7 empty] | X
2000-06-05 | Accounting |  | Summary of Selected Center Activity Mgmt |  | X | [7 empty] | X
2000-04-24 | BAC |  | System Response Time | Delay in process time. Sharing of system resources with SIS | X
2000-03-20 | End User Needs | Process Improvement | Track family medical leave. | Depts need to track how much FML used regardless of vacation, sick or leave without pay. | X
2000-01-13 | End User Needs | Reporting | Training for Supervisor/Managers (via SAP or MyNuLook) |  |  |  |  | X
2000-05-04 | End User Needs | Other | Travel Contract for UNL |  |  |  |  | X
2000-04-10 | End User Needs | Training | Travel Module | Resources needed for development and testing | X | [6 empty] | Ensure UNL's participation in processes.
2000-06-05 | Payroll |  | UNL Credit union, campus rec & parking deduction interfaces |  | X | [7 empty] | X
2000-03-15 | Data Entry |  | Update mailing list for campus mail distribution list. |  |  |  | Data Entry |  | Pat Amedeo | Completed |  | New Employees or those that have moved do not receive UNL-wide mass mail (Scarlet)
2000-01-13 | HR |  | Update Policy on Vacation/Sick Accrual |  |  |  | HR |  |  |  |  | Policy does not match process
2000-03-07 | End User Needs | Implemenation Issues | Updateable Inventory Figure that would show on reports | Dale Z possible solution for depts to post journal entry to expense/inventory on monthly basis. Follow up needed |  |  | Acct
2000-01-24 | End User Needs | Process Improvement | Upload capabilities to SAP for ETV (mainly MM module) |  |  |  |  | X |  |  | Low | Will not go on-line until able to upload information.
2000-06-05 | Budget |  | Upload EDB changes to PSL |  |  |  | Budget | [5 empty] | X
2000-01-24 | End User Needs | Implemenation Issues | User definable field for project coding. Field should carry through all modules | #1 Issue that UNL Departments would like to have addressed | X | [5 empty] | HIGH |  | Yes
2000-06-05 | Data Entry |  | Wage type / cost object combination reporting |  | X |  |  |  | Pat Smith |  |  |  | X
2000-06-05 | Payroll |  | W2P 1099R files / reports / forms | May need Karen Lenzen's help | X |  |  |  | Pat Smith |  |  |  | X
2000-03-13 | End User Needs | Implemenation Issues | Windows 2000 not supportedby SAP 4.5b | ASG needs to address issue |  | X |  |  |  | Completed |  | Monitor for future problems
2000-06-05 | Data Entry |  | Workstudy fix | (Nancy checking on status) | X | [7 empty] | X
2000-03-13 | End User Needs | Implemenation Issues | Year End Encumbrances & Accruals - Accrual moved forward at the Plan 0 level. Change to Budget system to include child cost object and allow departments to initiate budget transfers in PSL | Need to have sub team review the campus desires on this issue |  |  |  | X |  |  | HIGH
2000-04-01 | End User Needs | Implemenation Issues | Year Ending Closing (carry forward blanaces, inventory blanaces & encumbrances) |  |  |  |  | X
2000-06-15 | BAC | System Issues | Coordination of SAP & Mynulook functionality & resources. How do both systems function at UNL? Need to establish priorities. |  | x | [5 empty] | HIGH
2000-06-22 | HR |  | SAP applicant tracking module for computer applicant-tracking system | HR investigating options available to created an automated system. Want SAP information for comparison purposes. (requested by Margaret Koczan) |  | X
2000-06-22 | Technical |  | File that is sent from SAP to the CSO is not correct. Problem with temp employees data |  |  |  | Info Serv |  | Donna Liss & Kent Wendel
2000-06-25 | End User Needs | Process Improvement | Process to create WBS element | Recommendation of Retro Pay subteam, start with Kate Shaner's process flow document |  |  | SP-F | X
2000-07-12 | HR |  | SAP Infotype 9001, Appointment Information, expanded to include at least one more "paid" data line of information. |  | X |  | DE |  | Pat Smith |  | HIGH | Critical need for recording eligibility of tuition remission
2000-09-27 | End User Needs | Process Improvement | Add "use/lose" vacation information to pay stub. | Time Entry On-Line users supported this issue |  |  | Payroll