## Compression - USE FOR HOMEWORK
Iteration | Step | Project Duration (workdays) | Critical Activity Shortened | New Critical Path (Y/N) | Additional Direct Cost | Cumulative Direct Cost | Cumulative Project Direct Cost | Total Project Overhead | (Liquidated Damages) Bonus | Total Project Cost (W/O Bonus) | Net Project Cost | Total Project Cost Delta (W/ Bonus)
1000
A | 1 | 24 | C | N | 100 | 100 | 1100
| 2 | 23 | A | N | 200 | 300 | 1300
B | 1 | 23 | D | Y | 350 | 350
| 2 | 20 | C | N | 100 | 450
| 3 | 15 | A | N | 200 | 650
* This is an example problem; numbers above are provided for clarification only